## IT-OPS
RCSA # | Key Process | Key Steps in Process | 2021 New Process Wording | Process ID | Key Risks | 2021 New Risk Wording | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control Description | 2021 New Control Wording | Key / Non Key | Control ID (GRC) | Control Test # | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved | Notes | SME
RCSA ID Number | Name of the key process that is being performed. | Describe the key activity or tasks performed within this process. |  | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. |  | Risk ID Number | Select the risk category based on the bankwide risk taxonomy | What is the impact of this risk? Select from: Very High, High, Moderate, Low | What is the probability of the risk occurring? Select from: Possible/Adverse, Probable/Baseline | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low | Describe the control in detail. A key control that is significant and deemed critical to a given process, and must be performed effectively to reduce the inherent risk that it is associated with, to an acceptable level. |  |  | Control ID Number |  | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often does the control occur? Select from: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing, decreasing or stable? | What are the results of this RCSA? | What is the issue or gap for this key process? | Finding ID Number | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Reference the application involved (for key risks only) | Describe the actions being taken to close the finding.
IT OPR 1 | IT Operations | Backup/Replications 1. Unisys Miser Mainframe. The Bank uses B&L Software for performing in house and offsite Tape Backup. The Bank also has replicates data to FIS. 2. Imaging system. The Bank uses the Cypress backup tool. 3. Network Backups are completed daily using SolarWinds. 4. Servers are backed up via a Data Domain Appliance. 5. Unisys Mainframe, Each day, the Database is copied, which is part of the Automated Job Scheduler. Monday through Fridays are Incremental Backups and on Saturdays a Full Back up is completed of the Production, Test and Developments environments. The Replications of the Miser system and ATMS are completed every night to FIS. 6. Imaging System. The Backup Exec is in the Automated job scheduler. Full backup nightly which are maintained in house and offsite at Iron mountain. 7. Network The automated process Backs ups are stored on the SolarWinds server in Scarsdale.. When Backup's are completed SolarWinds generates a message which is sent via email. 8. Servers - VMware in Scarsdale is backed up to Chanin, and VMware in Chanin is backed up in Scarsdale. Full Backups are completed daily as pare for the job schedule as noted on the Run Sheets. 9. Unisys Mainframe. Every day Backup tapes via the VTS module in the B&L Software tapes are generated which are sent to Iron Mountain. Within the software the backups are encrypted and a Library in maintained which tracks the location and tape retention period. 10. Network - Solarwinds resides on VMWare. The Virtualized serve is also Backed up which is retained for two weeks onsite. In addition, the physical tapes are generated and are sent off to Iron Mountain. 11. Imaging system. The Bank uses the Cypress backup tool. Full backup nightly which are maintained in house and offsite at Iron mountain. 12. Servers are replicated the alternate data center. Scarsdale to Chanin and Chain are replicated at Scarsdale. Backup tapes are sent offsite to Iron Mountain | Applications Backup 1. Unisys Miser Mainframe. The Bank uses B&L Software for performing in house and offsite Tape Backup. The Bank has replicates data to FIS. 2. Imaging system. The Bank uses the Cypress backup tool. 3. Unisys Mainframe: Each day, an automated job in the Automated Job Scheduler copies the Database. Backup schedule: (Monday through Friday) Incremental backups; (Saturday) Full Back up of Production, Test and Developments environments. The Replications of the Miser system and ATMS are completed every night to FIS. 4. Imaging System. The job "Backup Exec" is in the Automated job scheduler. Full backup is performed nightly. Back up is maintained in house and offsite at Iron mountain. 5. Unisys Mainframe. Backup tapes via the VTS module in the B&L Software tapes are generated daily and sent to Iron Mountain. Backups are encrypted. A Library is maintained to track the location and tape retention period. Network/Server (NON MISER and Imaging) Backup 1. The Bank's virtual infrastructure is backed up, using Veeam Backup & Replication software. The virtual infrastructure comprises all non-MISER servers, including the Bank's servers (e.g., network domains, files, databases) and infrastructure components (e.g., firewall rules, network tools) 2. The backup job is performed automatically daily (incremental) and weekly (full on applications) 3. The Veeam's backup operation is performed locally within the Bank's premises. The backup output is written locally to the in-house hosted Quantum appliance for local storage. 4. The backup output in the Quantum appliance is exported to Iron Mountain, using Veeam software and a secure transmission (Iron Mountain Iron Cloud network connectivity) to Iron Mountain's Secure Offline Storage Services ("SOS"). The backup export to Iron mountain is stored as "objects" for short-term (3 days) in "SOS Nearline Storage Tier" then automatically migrated to magnetic tape media for long-term storage in Iron Mountain vault. Since the objects meta data is maintained by SOS, the Bank is not exposed to the physical tape infrastructure: all access of the Data is handled through the object construct in SOS. 5. The Bank's backup data can be retrieved from the vault and ingested into the NearLine tier for the Bank's server team access. The standard response time included in the base SOS service to initiate Data recall from the Offline to NearLine storage tier is twenty-four (24) hours. An expedited recall can be requested for an additional fee to four (4) hours. Service Level Agreements and Service Level Objectives are defined in the Service Level Agreements and Service Level Objectives document. 6. Only members of the Bank's network team have access to Iron Mountain services and the Bank's backup that is stored in Iron Mountain's cloud. A request for backup data recall can only made by designated members of the Server team. 7. The prior "Windows Server Shadow Copy" services (that allowed users to restore files without the assistance of Help Desk) is now replaced with the "Quantum Volume Shadow Copy Service (VSS)". | IT-OPR-P01 | The servers, network or the mainframe could crash and data may be lost if not backed up and stored at an alternate location. | Business data may be lost and the Bank's IT assets cannot be recovered because the backup is not adequate or safely saved. This may negatively affect the Bank's resiliency and impair the bank's capability to adequately recover from unexpected business disruptions. | IT-OPR-R01 | 8.4.1 - Operational Risk - Processes - Branch and ATM Operations | Very High | Possible/Adverse | High | An Automated Job Scheduler Tool is used to back up the Data | Administration and Management of Backup Tool, Environment and Jobs The backup tool and the backup environment are appropriately configured for optimal performance and security. The backup job is monitored daily so that issues are addressed timely and appropriately. | Key | IT-OPR-C1 | IT-OPR-C1 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 4 | Low | Decreasing | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021 (2021 Updates on non-MISER) Inquired, get confirmed and obtained evidence that the back up of servers and applications is performed with Veeam Backup and Replication software. To secure the backup data, "encryption password loss protection" is enabled, with key retention period set to 4 weeks. For further efficient data protection, a locally hosted Quantum disk backup appliance is used. == From METRICSTREAM ================ (ISSUE-0000003500) "Backup restoration tests are not in place for TPG Specialty application. It is only performed on ad-hoc basis". Current status: No change. (ISSUE-0000003501) "Backup restoration tests are not in place for Bancware ALM6 application. It is only performed on ad-hoc basis." Current status: Backup test is scheduled to be performed by the end of Q4 2021. (ISSUE-0000003525) "The ability to successfully restore data and systems has not been exercised since the new backup process was effectuated". Current status: closed (ISSUE-0000003527) "The Palo Alto firewalls and Panorama management console are not backed up, but rely on a recently established manual process" Current status: Action Plan Implementation. | SA
[9 empty] | Very High | Possible/Adverse | High | The Backup Tool is Configured to occur Nightly to back up the changes that occurred and weekly for a full Backup | Back Up Schedule and Coverage The back up jobs have a schedule (daily, weekly and monthly) with the appropriate types (incremental, differential and full back up) to cover the Bank's servers and applications. | Key | IT-OPR-C2 | IT-OPR-C2 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 4 | Low | Decreasing | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021 (2021 Updates on non-MISER) Inquired, get confirmed and obtained evidence that the backup schedule is as follows: A. Chanin (daily incremental): applications and infrastructure systems (weekly full): application servers B. Scarsdale (daily incremental): application system Tier A/B, IT Infrastructure Tier A/B (weekly full): application servers C. Long Island city (daily incremental): file server | SA
[9 empty] | Very High | Possible/Adverse | High | Backup Tapes are sent offsite that contain data, so that in the event of a partial or site Loss, the backup is available for restoration. | Off-site Backup and Test of Backup A copy of the back up of the Bank's production system is stored in a geographically different location than the production system. Backup is tested frequently to verify the quality of the backup. | Key | IT-OPR-C3 | IT-OPR-C3 | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 4 | Moderate | Decreasing | Pass | (2020) Networker tool did not capture the data on the Application Servers and File Shares and therefore the data was not saved on the Tape that were sent to Iron Mountain. The log reported the Backup complete and the results appeared to contain the backup. The root cause were (1) incompatibility between the Networker and the VMware backup handler & (2) disk space issue in the backup appliance preventing the data backup to be written. The Bank should address the root cause of the tape backup failure by updating/replacing the backup software and hardware. The Bank should also enhance the backup monitoring process by testing the backup tapes. (2021 Updates) Networker was replaced by Veeam Backup & Replication. Offline backups are stored for 3 days in Iron Mountain Iron Cloud and then transferred to tapes in Iron Mountain vault. No further exceptions identified. | (2020 Update) This issue was resolved during the IT RCSA process. 1. Obtained the support and noted that the components of the Networker tool has been upgraded. We validated the automatic daily and weekly scheduler from Scarsdale to Chanin includes the File system, SQL is configured as such: - Daily Clone - Daily Backup We validated the automatic daily and weekly scheduler from Chanin to Scarsdale includes the SQL, VMWare is configured as such: - Daily Clone - Daily Backup 2. We next validated the successful completions of Clones and Backups. Clones are saved for a period of 2 weeks and Backups are saved for a period of 7 years. 3. We also reviewed Managements validation of the restored backups. This was completed by IT to ensure that the contents that are being backed up are in usable format and contain the required data. (2021 Updates) Networker was replaced by Veeam Backup & Replication. Offline backups are stored for 3 days in Iron Mountain Iron Cloud and then transferred to tapes in Iron Mountain vault. No further exceptions identified. | (2020 updates) Management has already upgraded all the components of the Networker backup system. In addition, the Bank has purchased additional storage for the backup appliance. Also, the Bank will start testing the backup tapes. (2021 Updates) Networker was replaced by Veeam Backup & Replication. Offline backups are stored for 3 days in Iron Mountain Iron Cloud and then transferred to tapes in Iron Mountain vault. No further exceptions identified. | None | None |  |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021. (2021 Updates on non-MISER) Inquired and get confirmed that offline backups are stored for 3 days in Iron Mountain Iron Cloud and then transferred to tapes in Iron Mountain vault. Further inquired and get confirmed that the testing of backup is planned, with a frequency of once a month. The test results are reviewed by the lead of the server team. | SA
IT OPR 1 | IT Operations | Data Center Physical Access 1. Scarsdale - Access to the Building main doors is managed by the Property Manager. When new access or discontinued access occurs David Friedman (Physical Security) communicates with the Property Manager to activate or deactivate an Apple Key Fob. 2. The Manhattan office. Access to the Building main doors is managed by the Property Manager. When new access or discontinued access occurs David Friedman (Physical Security) communicates with the Building Manager to activate access. 3. Scarsdale. The Data Center Access is further protected by a Key fob which is controlled by the Enterprise Access application. Reports are generated from the system that includes who has access and records and reports access events into secured areas. These reports are provided to the CTO Quarterly. 4. The alternate data center is referred to as Chanin. This Data Center is located on the 9th floor which uses the Keri Door System which access is managed by Fobs. Reports are generated from the system that includes who has access and records and reports access events into secured areas. These reports are provided to the CTO Quarterly. 5. Limited users have Administrative access to both the Enterprise Access and Keri applications to add, modify and revoke users access for the Software House application. | Data Center Physical Access 1. Scarsdale - Access to the Tenant shared Main Building main doors is managed by the Property Manager. Access to all Apple Bank doors and areas are administered by the Security Dept./Enterprise Access control system. When new access or discontinued access occurs the Security Dept. (Physical Security) will activate or deactivate an Apple Key Fob. 2. The Manhattan office. Access to the base building turnstiles is coordinated between Chanin Building management and the Security Dept. Access to all Apple Bank doors and areas is administered by the Security Department/enterprise access control system. When new access or discontinued access is requested by Department Heads or HR, the security department administers access. 3. Scarsdale. The Data Center Access is further protected by a Key fob and dual authentication biometric access device which is controlled by the Security Department/Enterprise Access application. Reports are generated from the system that includes who has access and records and reports access events into secured areas. These reports are provided to the CTO Quarterly. 4. The alternate data center is referred to as Chanin. This Data Center is located on the 9th floor which uses Key fob and dual authentication biometric access device which is controlled by the Security Department/Enterprise Access application. Reports are generated from the system that includes who has access and records and reports access events into secured areas. These reports are provided to the CTO Quarterly. 5. Enterprise Access - Only the Security Department has Administrative access to the Enterprise Access applications to add, modify and revoke users access for all corporate locations.. | IT-OPR-P02 | Logical Access to the Data center may be inconsistent to individual's functional role resulting in loss or damage to technology. | The security of the Data center and Computer rooms may be compromised because the physical access to these premises are inadequately and inappropriately granted. This may expose the Bank to adverse financial, operational and regulatory issues. | IT-OPR-R02 | 8.8.4 - Operational Risk - Terrorism, Vandalism and Physical Security | High | Probable/Baseline | High | Requirements for Physical Access to common grounds are communicated by the Security Officer to the Property Managers. | Physical Access Review and Approval Physical access to the Data Center and Computer Rooms is approved by the CTO. Bank Security Officer/Head of Physical Security and CTO review access reports. | Key | IT-OPR-C4 | IT-OPR-C4 | Preventative | Manual | Adequate | Adequate | Adequate | Transactional | Annually | 0 Not a Key Control | Moderate | Stable | Pass | None | None | None | None | None | None |  | (2021 Update) Obtained the log entries of the access granting for Chanin and Scarsdale. Determined that each access was reviewed and approved by either David Friedman or Orlando Canales. Obtained the list of access to Chanin and Scarsdale. Determined that each access was granted to a personnel with appropriate role and responsibilities | DF
IT OPR 1 | IT Operations | [7 empty] | High | Probable/Baseline | High | Physical Access is managed by Key Fob controlled outside of IT by the Security Officer. | Key Fob MFA-enabled Physical access Physical access is secured with key fobs and multi-factor authentication (MFA) that are controlled by the Bank Security Officer/Head of Physical Security. | Key | IT-OPR-C5 | IT-OPR-C5 | Preventative | Automated | Strong | Strong | Strong | Transactional | Annually | 2 | Low | Decreasing | Pass | None | None | None | None | None | None |  | (2021 Update) Inquired and get confirmed that the data centers in Scarsdale and Chanin are secured by the HID’s iCLASS read/write contactless smart card technology, the iCLASS SE Biometric and iCLASS SE Display Readers (capable of supporting up to three-factor authentication and user interaction). The key FOBs and biometric access are issued at the time the access was granted (see control OPR-C04) | DF
IT OPR 1 | IT Operations | Independent Physical Access Reviews 1. Quarterly, the Information Security Group completes a review of those individual that have access to the data centers. Access is compared with Human Resources to ensure that each is an employee. | No changes | IT-OPR-P03 | Access to the Data center may not be reviewed periodically to ensure accuracy of physical Access. | Physical access to the data center and computer rooms may be inappropriate because it has not been regularly reviewed. This may expose the Bank to adverse financial, operational and regulatory risks and issues. | IT-OPR-R03 | 8.8.4 - Operational Risk - Terrorism, Vandalism and Physical Security | High | Possible/Adverse | Moderate | Physical Access to the Data Center is independently reviewed by Information Security. | Independent Review of Physical Access Physical Access to the Data Center is independently reviewed by Information Security. | Key | IT-OPR-C6 | IT-OPR-C6 | Detective | Manual | Strong | Strong | Strong | Quarterly | Quarterly | 1 | Low | Stable | Pass | None | None | None | None | None | None |  | (2021 Update) Obtained the entry log of the data center in Chanin and Scarsdale. Inquired and receive confirmation that the entry logs were used for independent review by A. Lum in Q1 and Q2. | DF
IT OPR 1 | IT Operations | Data Center Environmental Controls 1. Scarsdale - The Data in Scarsdale has environmental controls in place to protect the technology. This includes the following devices: - Camera outside the Data Center Door to monitor access - Manual log in the Data Center to record non employees that enter - HVAC Air Conditioning System in place - Uninterruptable Power supply (UPS) in the event of an Power Spike or Failure - Battery Backup - Water Detection - Temperature Detection - SolarWinds report that send an alert for temperature changes within a range - Fire Detection - Fire Suppression 2. Chanin - The Data in Manhattan has environmental controls in place to protect the technology. This includes the following devices: - Camera outside the Data Center Door to monitor access - Manual log is not in place - HVAC Air Conditioning System in place - Uninterruptable Power supply (UPS) in the event of an Power Spike or Failure - Battery Backup - Water Detection - Temperature Detection - SolarWinds report that send an alert for temperature changes within a range - Fire Detection - Fire Suppression - Hand Held | No changes | IT-OPR-P04 | The Data Centers that contains servers, technology and devices may not be protected from environmental risks and the data and technology are subject to loss. | Servers and other hardware components in the data center and computer rooms may fail to operate as expected because the data center and computer rooms are not appropriately protected from the environmental risks. This may cause unexpected business interruptions and expose the Bank to adverse financial, operational and regulatory risk and issues. | IT-OPR-R04 | 8.8.4 - Operational Risk - Terrorism, Vandalism and Physical Security | High | Probable/Baseline | High | The Bank has set up environmental controls to protect the technology in place at the Scarsdale and Chanin Data Center. | Data Center and Computer Room Environmental Controls The Scarsdale and Chanin Data Center are adequately protected by the appropriate environment controls | Non Key | IT-OPR-C7 | IT-OPR-C7 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 1 | Low | Stable | Pass | None | None | None | None | None | None |  | (2021 Update) Inquired and received confirmation that the environmental controls have not significantly changed since last RCSA in 2020. No test was necessary in 2021. | DF/Facilities
IT OPR 1 | IT Operations | Business Application Report 1. Standard Production Reports are generated and provided to the Business Units daily. This is part of the output from the Nightly Job Schedule. 2. Reports are used by the Bank for Daily Business activities. The report contents were validated as part of the Testing when implementing the applications. | No Changes | IT-OPR-P05 | Reports may not be produced or may contain inaccurate information to meet the needs of the Business. As decisions are determined on the output misinformation could result in ineffective outcomes. | Information from business applications reports may be inaccurate or unsecured, because the production environment is not appropriately and adequately protected. This may expose the Bank to adverse financial, operational and regulatory risks and issues. | IT-OPR-R05 | 8.4.1 - Operational Risk - Processes - Branch and ATM Operations | High | Possible/Adverse | Moderate | Reports are generated directly from the Applications and are distributed to the Business Units with out alterations. | Distribution of Business Application Reports Controls are in place to ensure the integrity and confidentiality (if applicable) of business application reports when they are distributed to the Business Units from Production. | Key | IT IFR-C4 | IT-OPR-C8 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 5 days | Low | Stable | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021 | JN
[9 empty] | High | Possible/Adverse | Moderate | For each new release, upon User Acceptance testing the Reports contents are validated to ensure that the output is accurate. | Change Management of Business Application Reports Business application reports are submitted to the IT Change Management process | Key | IT IFR-C5 | IT-OPR-C9 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 0 Not a Key Control | Low | Stable | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021 | JN
IT OPR 1 | IT Operations | Monitoring of System Resource and Performance 1. Daily System Performance Metrics are produced via a report that includes: - Response time - Uptime Management - Tools and Reporting These reports are reviewed and changes to load balancing, disc space etc. are completed when necessary. | Monitoring of System Resource and Performance 1. The Bank's network devices are monitored, using SolarWinds Orion Platform 2. The network devices are discovered mainly from the routers/switches seed IP address 3. SolarWinds is configured to poll using SNMP method to monitor: hardware health, routing (virtual routing, routing table, BCP/EIGRP neighbors), CPU/Memory, EnergyWise devices, Topology Layer 2/3, VLAN. 4. The network team has a daily routine to check the following: status of backup, changes of network configuration, status of device/ interface/ application, status of VPN, status of phones on network, health check of telecom servers, real-time status of Cisco devices, using Cisco Real-Time Monitoring Tool (RTMT). | IT-OPR-P06 | Performance not monitored could lead to a degradation in performance of the use of technology.. | The production system may perform sub-optimally or degrade because it is not appropriately and adequately monitored. This may cause unexpected business interruptions and expose the Bank to adverse financial, operational and regulatory risk and issues | IT-OPR-R06 | 8.4.1 - Operational Risk - Processes - Branch and ATM Operations | High | Possible/Adverse | Moderate | Daily system performance is captured and monitored to ensure that the systems have the necessary technology resources for peak performance. | Monitoring of System Resource and Performance System resources and performance of key components of the Bank's IT infrastructure (CPU, server memory, routers, switches, bandwidth, network devices, etc.) are monitored. Issues, including possible malfunctions or disruptions are addressed timely and appropriately. | Key | IT IFR-C6 | IT-OPR-C10 | Detective | Automated | Adequate | Strong | Strong | Annually | Annually | 5 | Low | Stable | Pass | None | None | None | None | None | None |  | (2021 Updates) Obtained a list of network nodes and determined that over 230 nodes including routers, switches are subject to SOLARWINDS automated monitoring. Obtained the SOLARWINDS monitoring configuration. Determined that the polling method was SNMP to cover the following monitoring topics: hardware health, routing (virtual routing, routing table, BCP/EIGRP neighbors), CPU/Memory, EnergyWise devices, Topology Layer 2/3, VLAN. Obtained and determined that the daily checklist for the network team includes: status of backup, change of network configuration, status of device/ interface/ application, status of VPN, status of phones on network, health check of telecom servers, real-time status of Cisco devices (on RTMT). Further queries the SNOW database for network incidents since January 2021. Determined that all incidents are addressed timely and appropriately. ==== From METRIS STREAM =========================== (ISSUE-0000003236) "WirePro Branch Wire Entry Issue" Current status: (Closed) The "options values table" was locked on incorrect value. (ISSUE-0000003310) "Okta Portal Disruption" Current status: (Closed) Okta service disruption. (ISSUE-0000003421) "Branch Capture Scanning Communications Failure" Current status: (Closed) FIS traffic fail-over to primary link from backup link. (ISSUE-0000003422) "S1 Outage" Current status: (Closed) Port tested to be functional . Intermittent failures. (ISSUE-0000003432) "BAM Replication Job Failure" Current status: (Closed) Issue with SQL driver on the server (ISSUE-0000003438) "Failure in communication between WIREPRO and SQL instances prevented the wire room from automatically processing wires" Current status: (Closed) Issue with SQL driver on the server (ISSUE-0000003448) "S1 Interface to Chex system giving error in branch 9 - INC0034367". Current Status: (Closed) Correct firewall entry in the branch router | FC
IT OPR 1 | IT Operations | Performance Metric Reporting 1. Performance Reports are assembled for presentation to the CTO. This reports are provided monthly to the CTO to ensure that management is made aware of the quality of processing | Performance Metric Reporting 1. The CTO and IT Team receives weekly and monthly reports on changes in network configuration, system resource consumption and system service availability 2. In addition, the network team receives real-time alerts on infrastructure changes, system malfunctions and critical threshold levels of capacity utilization | IT-IFR-P12 | Performance metric's may not be reported to the CTO to ensure that the systems health is communicated. Without the communication, the systems performance could degrade. | The production system may perform sub-optimally or degrade because the system monitoring metrics are not reported to and reviewed at the appropriate level of management. This may cause unexpected business interruptions and expose the Bank to adverse financial, operational and regulatory risk and issues. | IT-IFR-R12 | 8.4.1 - Operational Risk - Processes - Branch and ATM Operations | High | Possible/Adverse | Moderate | Performance reports are provided to the CTO to communicate the health of the network, core and servers. | Report of Key System Metrics Key system metrics pertaining to performance, availability and reliability are reported to and reviewed by the CTO | Key | IT IFR-C20 | IT-OPR-C11 | Detective | Manual | Adequate | Strong | Adequate | Monthly | Monthly | 5 | Low | Stable | Pass | None | None | None | None | None | None |  | (2021 Updates) Obtained the weekly and monthly reports from the Network Management Tool SolarWinds Scarsdale. Determined the following details are provided: internet bandwidth consumption; node availability report (monthly); bandwidth utilization of two MPLS circuits connecting Scarsdale to the branches; and firewall capacity utilization (max. concurrent active sessions). Obtained the configurations for system alerts. Determined that alerts are set for the following: CISCO IOS (Internetwork O/S) changes, device unavailability (VPN, Node), critical utilization level (systems volume, CPU, memory), malfunctions (network hardware, data ring). Obtained two reports on network configuration changes (1 for critical, the other for non-critical). Determined that the details changes were reported (before and after). Further determined that the two reports are scheduled to be frequently generated. | FC
IT OPR 1 | IT Operations | In house Managed Systems 1. Automated Job schedules for the Miser application is in place to ensure, that the daily interfaces and backup process complete without human interaction. 2. In the event of a Job Failure or disruption, an alert is sent to the Night Operator for actions to be taken to correct the incident. 3. Daily reports are generated nightly and provided to the Agency electronically as a result of the job schedule. | In house Managed Systems (MISER) 1. Automated Job schedules for the Miser application is in place to ensure, that the daily interfaces and backup process complete without human interaction. 2. In the event of a Job Failure or disruption, an alert is sent to the Night Operator for actions to be taken to correct the incident. 3. Daily reports are generated nightly and provided to the Agency electronically as a result of the job schedule. Overnight (NON-MISER) Database Jobs 1. The overnight data jobs on the SQL Server databases are scheduled in the SQL Server Agent to be executed automatically. The SQL Server Agent is a Microsoft Windows service that stores the related job information in the SQL Server. The SQL Server Agent uses the fixed and pre-defined roles in the SQL Server to prevent access to users who are not members of the server administration team. In addition, the database subsystems and proxies ensure that the data jobs run with the minimum permissions required. 2. The server team has a roster for on-call professionals to monitor the processes. Members of the DBA team can be on call if required. 3. The jobs in the SQL Server Agent are configured so that emails are sent to the DBA teams on issues/errors with the jobs. These emails are also copied to the lines of business, which are responsible for the related jobs (and application servers). 4. Upon errors or failures in the jobs, the DBA team analyzes and resolves the issues timely and appropriately. 5. Changes in the data jobs are submitted to the IT Change Management procedures. 6. The Server Manager is copied real-time on the status and failures of the overnight data jobs in order to ensure timely and appropriate handling of any potential issues. | IT-IFR-P4 | Night processing of Interface updates, backups and Report Generation may not be completed fully, which could result in data completeness and accuracy. | The overnight process may generate incorrect results because the process is not adequately and appropriately supported by tools and processes. This may expose the Bank to adverse financial, operational and regulatory risk and issues. | IT-IFR-R4 | 8.4.1 - Operational Risk - Processes - Branch and ATM Operations | Very High | Possible/Adverse | High | An Automated Job Schedule Tool is used which enforces the system to complete the Night processing without the requirements of the Operator | Administration and Management of the Overnight Tool and Environment The tool for the overnight process is appropriately configured for optimal performance and security. The overnight environment (jobs, schedule, applications, etc.) is subject to IT Change Management process. | Key | IT IFR-C7 | IT-OPR-C12 | Preventative | Automated | Adequate | Strong | Strong | Annually | Annually | 1. Banktel 2. Q2 | Low | Decreasing | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021. (2021 Updates on non-MISER) Inquired, get confirmed and obtained evidence that the overnight data jobs are scheduled to be executed automatically in the SQL Server Agent, which is a native Microsoft SQL server service, with in-built security features. Further inquired and received confirmation that changes in the data jobs are submitted to the IT Change Management procedures. There have not been any changes since January 2021 | SA
IT OPR 1 | [8 empty] | Very High | Possible/Adverse | High | An Operator is available to support the Night Process and make any corrections in processing if necessary. An Automated control is in place to notify the Night Operator in the event of a job schedule disruptions. | Overnight Job Monitoring and Issue Management An operator monitors the overnight process. Issues are automatically reported so that they can be addressed appropriately and timely in order to minimize disruptions. | Key | IT IFR-C8 | IT-OPR-C13 | Detective | Manual | Adequate | Strong | Strong | Annually | Annually | 0 Not a Key Control | Low | Decreasing | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021. (2021 Updates on non-MISER) Inquired, get confirmed and obtained evidence that the server team has a roster for on-call professionals to monitor the processes. Members of the DBA team are on call when required. Further inquired and obtained evidence that the jobs in the SQL Server Agent are configured so that emails are sent to the DBA teams on issues/errors with the jobs. These emails are also copied to the lines of business, which are responsible for the related jobs (and application servers). | SA
IT OPR 1 | [8 empty] | Very High | Possible/Adverse | High | Reports are generated, reviewed and approved for the completion of Night Processing. | Overnight Job Status Report The report of the overnight job status is generated and reviewed after the completion of the overnight job. | Key | IT IFR-C9 | IT-OPR-C14 | Detective | Manual | Adequate | Strong | Strong | Annually | Annually | 0 Not a Key Control | Low | Decreasing | Pass | None | None | None | None | None | None |  | (2021 Updates on MISER) Inquired and get confirmed that in 2021, there were no new developments, hence no changes in MISER in anticipation of the replacement of this application. No RCSA test necessary in 2021. (2021 Updates on non-MISER) Inquired and get confirmed that the Server Manager is copied real-time on the status and failures of the overnight data jobs in order to ensure timely and appropriate handling of any potential issues. | SA

## Aggregate
2020
Risk ID | Control ID | Inherent Risk Rating | Control Rating | Residual Rating | Aggr. Residual Rating | Risk ID | Control ID | Inherent Risk Rating | Control Rating | Residual Rating | Aggr. Residual Rating
IT-OPR-R01 | IT-OPR-C1 | High | Strong | Low | Moderate | IT OPR R-1 | IT OPR C-1 | High | Strong | Moderate | Moderate
| IT-OPR-C2 |  | Strong | Low |  |  | IT OPR C-2 |  | Strong | Moderate
| IT-OPR-C3 |  | Adequate | Moderate |  |  | IT OPR C-3 |  | Strong | Moderate
IT-OPR-R02 | IT-OPR-C4 | High | Adequate | Moderate | Moderate | IT OPR R-2 | IT OPR C-4 | High | Adequate | Moderate | Moderate
| IT-OPR-C5 |  | Strong | Low |  |  | IT OPR C-5 |  | Strong | Moderate
IT-OPR-R03 | IT-OPR-C6 | Moderate | Strong | Low | Low | IT OPR R-3 | IT OPR C-6 | Moderate | Strong | Low | Low
IT-OPR-R04 | IT-OPR-C7 | High | Strong | Low | Low | IT OPR R-4 | IT OPR C-7 | Moderate | Strong | Low | Low
IT-OPR-R05 | IT-OPR-C8 | Moderate | Strong | Low | Low | IT IFR R2 | IT IFR-C4 | Moderate | Strong | Low | Low
| IT-OPR-C9 |  | Strong | Low |  |  | IT IFR-C5 |  | Strong | Low
IT-OPR-R06 | IT-OPR-C10 | Moderate | Strong | Low | Low | IT IFR R3 | IT IFR-C6 | Moderate | Strong | Low | Low
IT-IFR-R12 | IT-OPR-C11 | Moderate | Adequate | Low | Low | IT IFR R12 | IT IFR-C20 | Moderate | Adequate | Low | Low
IT-IFR-R4 | IT-OPR-C12 | High | Strong | Low | Low | IT IFR R4 | IT IFR-C7 | High | Strong | Moderate | Moderate
| IT-OPR-C13 |  | Strong | Low |  |  | IT IFR-C8 |  | Strong | Moderate
| IT-OPR-C14 |  | Strong | Low |  |  | IT IFR-C9 |  | Strong | Moderate
Risk Rating | Control Rating | Count Inherent Risk | Count Control Rating | Count Residual Risk |  | Risk Rating | Control Rating | Count Inherent Risk | Count Control Rating | Count Residual Risk
Very High | Strong | 0 | 11 | 0 |  | Very High | Strong | 0 | 12 | 0
High | Adequate | 4 | 3 | 0 |  | High | Adequate | 3 | 2 | 0
Moderate | Weak | 4 | 0 | 2 |  | Moderate | Weak | 5 | 0 | 3
Low |  | 0 |  | 6 |  | Low |  | 0 |  | 5
|  | 8 | 14 | 8 |  |  |  | 8 | 14 | 8
| Aggregate | Moderate | Strong | Low |  |  | Aggregate | Moderate | Strong | Low
|  | 21 | 19 | 22 |  |  |  | 21 | 19 | 22
RCSA 2020
| Final Assessment | High | Strong | Low |  |  |  | Inherent Risk | Control Rating | Residual Risk
[7 empty] | IT-Operations (2020) | High | Strong | Moderate
[7 empty] | IT-Infrastructure (2020) | Moderate | Strong | Low
[7 empty] | IT Operations Aggregated (2020) | Moderate | Strong | Low
RCSA 2021
[8 empty] | Inherent Risk | Control Rating | Residual Risk
[7 empty] | IT Operations Aggregated (2021) | Moderate | Strong | Low

## 2020-2021
|  |  | 2020 | [6 empty] | 2021 | [6 empty] | 2020-21 | Residual Rating Verification |  |  |  | LOOKUP Table
Control ID | Control ID (2020) | Control Description | Key/Non-Key | Inherent Risk Rating | Design Effectiveness | Operating Effectiveness | Control Rating | Test Results | Residual Rating | Key/Non-Key | Inherent Risk Rating | Design Effectiveness | Operating Effectiveness | Control Rating | Test Results | Residual Rating | Risk Trending | Inherent Risk Rating | Combination <Control-Inherent Risk> | Residual Rating (Calculated) | Matching ("L" vs. "R")? | Combination <Control-Inherent Risk>
IT-OPR-C1 | IT OPR C-1 | Administration and Management of Backup Tool, Environment and Jobs | Key | High | Strong | Strong | Strong | Pass | Moderate | Key | High | Strong | Strong | Strong | Pass | Low | Decreasing | High | Strong-High | Low | TRUE | Weak-Low | Low
IT-OPR-C2 | IT OPR C-2 | Backup Schedule | Key | High | Strong | Strong | Strong | Pass | Moderate | Key | High | Strong | Strong | Strong | Pass | Low | Decreasing | High | Strong-High | Low | TRUE | Weak-Moderate | Moderate
IT-OPR-C3 | IT OPR C-3 | Off-site Backup and Test of Backup | Key | High | Strong | Weak | Strong | Fail | Moderate | Key | High | Adequate | Adequate | Adequate | Pass | Moderate | Decreasing | High | Adequate-High | Moderate | TRUE | Weak-High | High
IT-OPR-C4 | IT OPR C-4 | Physical Access Review and Approval | Non Key | High | Adequate | Adequate | Adequate | N/A | Moderate | Key | High | Adequate | Adequate | Adequate | Pass | Moderate | Stable | High | Adequate-High | Moderate | TRUE | Weak-Very High | Very High
IT-OPR-C5 | IT OPR C-5 | Key Fob-enabled Physical Access | Key | High | Strong | Strong | Strong | Pass | Moderate | Key | High | Strong | Strong | Strong | Pass | Low | Decreasing | High | Strong-High | Low | TRUE | Adequate-Low | Low
IT-OPR-C6 | IT OPR C-6 | Independent Review of Physical Access | Key | Moderate | Strong | Strong | Strong | Pass | Low | Key | Moderate | Strong | Strong | Strong | Pass | Low | Stable | Moderate | Strong-Moderate | Low | TRUE | Adequate-Moderate | Low
IT-OPR-C7 | IT OPR C-7 | Data Center and Computer Room Environmental Controls | Key | Moderate | Strong | Strong | Strong | Pass | Low | Non Key | High | Strong | Strong | Strong | Pass | Low | Stable | High | Strong-High | Low | TRUE | Adequate-High | Moderate
IT-OPR-C8 | IT IFR-C4 | Business Application Production Report | Key | Moderate | Strong | Strong | Strong | Pass | Low | Key | Moderate | Strong | Strong | Strong | Pass | Low | Stable | Moderate | Strong-Moderate | Low | TRUE | Adequate-Very High | High
IT-OPR-C9 | IT IFR-C5 | Change Management of Business Application Production Report | Non Key | Moderate | Strong | Strong | Strong | N/A | Low | Key | Moderate | Strong | Strong | Strong | Pass | Low | Stable | Moderate | Strong-Moderate | Low | TRUE | Strong-Low | Low
IT-OPR-C10 | IT IFR-C6 | Infrastructure System Monitoring | Key | Moderate | Adequate | Strong | Strong | Pass | Low | Key | Moderate | Adequate | Strong | Strong | Pass | Low | Stable | Moderate | Strong-Moderate | Low | TRUE | Strong-Moderate | Low
IT-OPR-C11 | IT IFR-C20 | Report of Key System Metrics | Key | Moderate | Adequate | Strong | Adequate | Pass | Low | Key | Moderate | Adequate | Strong | Adequate | Pass | Low | Stable | Moderate | Adequate-Moderate | Low | TRUE | Strong-High | Low
IT-OPR-C12 | IT IFR-C7 | Administration and Management of the Overnight Tool and Environment | Key | High | Adequate | Strong | Strong | Pass | Moderate | Key | High | Adequate | Strong | Strong | Pass | Low | Decreasing | High | Strong-High | Low | TRUE | Strong-Very High | Moderate
IT-OPR-C13 | IT IFR-C8 | Overnight Job Monitoring | Non Key | High | Adequate | Strong | Strong | N/A | Moderate | Key | High | Adequate | Strong | Strong | Pass | Low | Decreasing | High | Strong-High | Low | TRUE
IT-OPR-C14 | IT IFR-C9 | Overnight Job Status Report | Non Key | High | Adequate | Strong | Strong | N/A | Moderate | Key | High | Adequate | Strong | Strong | Pass | Low | Decreasing | High | Strong-High | Low | TRUE
Risk Rating |  | Control Rating |  |  | RCSA 2020 | [6 empty] | RCSA 2021
(Numeric) | (Qualitative) | (Numeric) | (Qualitative) |  | Count Inherent Risk Rating |  |  |  | Count Control Rating |  |  | Count Inherent Risk Rating | Count Residual Risk |  |  | Count Control Rating
4 | Very High | 3 | Strong |  | 0 |  |  |  | 12 |  |  | 0 | 0 |  |  | 11
3 | High | 2 | Adequate |  | 8 |  |  |  | 2 |  |  | 9 | 0 |  |  | 3
2 | Moderate | 1 | Weak |  | 6 |  |  |  | 0 |  |  | 5 | 2 |  |  | 0
1 | Low |  |  |  | 0 |  |  |  | 14 |  |  | 0 | 12 |  |  | 14
[5 empty] | 14 | [6 empty] | 14 | 14
[5 empty] | RCSA 2020 | [6 empty] | RCSA 2021
|  | Aggregate Inherent Risk rating |  |  | 2.5714 | High | [5 empty] | 2.6429 | High
|  | Aggregate Control rating |  |  | 2.8571 | Strong | [5 empty] | 2.7857 | Strong
|  | Resulting Residual Risk rating |  |  | Low | [6 empty] | Low
[8 empty] | Validated Residual Risk rating |  |  |  |  | 1.1429 | Low
[5 empty] | 2020 | [6 empty] | 2021
[5 empty] | Design Effectiveness | Operating Effectiveness | Control Rating | Residual Risk |  |  |  | Design Effectiveness | Operating Effectiveness | Control Rating | Residual Risk
|  | Adequate |  |  | 5 | 1 | 2 | Very High | 0 |  |  | 6 | 2 | 3 | Very High | 0
|  | Strong |  |  | 8 | 11 | 11 | High | 0 |  |  | 7 | 11 | 10 | High | 0
|  | Weak |  |  | 0 | 1 | 0 | Moderate | 8 |  |  | 0 | 0 | 0 | Moderate | 2
[5 empty] | 13 | 13 | 13 | Low | 6 |  |  | 13 | 13 | 13 | Low | 12
[9 empty] | 1.5714 | [6 empty] | 1.1429
[7 empty] | Test 2020 | Test 2021 |  |  |  |  | Risk Trending
[6 empty] | Fail | 1 | 0 |  |  |  |  | Decreasing | 6
[6 empty] | Pass | 9 | 13 |  |  |  |  | Stable | 7
[7 empty] | 10 | 13 |  |  |  |  | Increasing | 0
13
Notes
1 | In 2020, IT-OPR-C3 "failed", but its control rating = "Strong" and residual risk rating = "Moderate"
2 | In 2020, 4 controls (OPR-C4, IFR-C5, IFR-C8, IFR-C9) were classified "Non-Key" and consequently not tested
3 | In 2021, all controls are classified as "Key", except OPR-C7 (environmental controls)

## Evidence request (hidden)
IT Area | Control ID | Control Short Description | Control Description | Evidence Requests | Provided By | Due Date
Back Up | IT-OPR-C1 | Administration and Management of Backup Tool, Environment and Jobs | The backup tool and the backup environment are appropriately configured for optimal performance and security. The backup job is monitored daily so that issues are addressed timely and appropriately | C1.1 Backup Tools 1.1.1 Please provide the list of backup tools (e.g., software/scripts to backup data files, databases, virtual machines). Please provide the software name, the version, the functionalities that are in use (back up, restoration, job scheduler, file transfer, etc.) 1.1.2 Please provide the related configurations for optimal performance (speed, size, reliability, etc.) and security (encryption, CRUDE access, segregation of duties, privilege access, etc.) 1.1.3 Please provide the backup coverage (what is backed up, what is not) | SA
|  |  |  | C1.2 Backup Environment 1.2.1 Please describe the backup environment: hosting servers, server connections (local/remote), back up storage (tape, file, cloud, etc.), backup log storage, etc. 1.2.2 Please provide the related configurations for optimal performance (reliability, etc.) and security (encryption, CRUDE access, segregation of duties, privilege access, etc.) | SA
|  |  |  | C1.3 Backup Job 1.3.1 Please provide the list of back up jobs, including the back up target, scripts 1.3.2 Please provide the related configurations for operations (error validation, alerts, etc.) and security (CRUDE access, privilege access, etc.) 1.3.3 Please provide the back up job/error reports that were produced in the period Jan 1 - Sep 30, 2021 (a sample of reports will be requested for testing) 1.3.4 Please provide the evidence that the reports were reviewed and remediation actions were taken (if required) | SA
| IT-OPR-C2 | Backup Schedule | The back up jobs have a daily, weekly and monthly schedule so that incremental, differential and full back up is performed, in accordance to the required Recovery Point Objective (RPO). | C2.1. Please provide the schedule of all the back up jobs, including that for full, incremental, differential mode | SA
|  |  |  | C2.2. Please provide the evidence that the schedule of all the back up jobs is in accordance to the business RPO | SA
| IT-OPR-C3 | Off-site Backup and Test of Backup | A copy of the back up of the Bank's production system is stored in a geographically different location than the production system. Backup is tested frequently to verify the quality of the backup and to ensure that restoration is in line with the required Recovery Time Objective (RTO) | C3.1. Offsite storage of back up 3.1.1 Please provide the evidence that the backup results (tape, other media, etc.) are stored remotely 3.1.2 Please provide the evidence that the transfer of the backup media to offsite storage is secured 3.1.3 Please provide the evidence that the retrieval of the backup media from offsite storage is secured | SA
|  |  |  | C3.2 Testing of backup 3.2.1 Please provide the testing methodology (testing frequency, sample approach, testing steps) 3.2.2 Please provide the recovery benchmark against the required RTO 3.2.3 Please provide the testing results since January 1, 2021 (a sample of results will be requested for testing) | SA
Physical Access | IT-OPR-C4 | Physical Access Review and Approval | Physical access to the Data Center and Computer Rooms is reviewed and approved by the Bank Security Officer/Head of Physical Security | C4.1 Review and Approval of access to data centers 4.1.1 Please provide the list of permanent access to the data centers in Scarsdale and Chanin 4.1.2 Please provide the list of temporary access to the data centers in Scarsdale and Chanin 4.1.3 Please provide the evidence of review and approval if the access is new in 2021 | David Friedman
| IT-OPR-C5 | Key Fob-enabled Physical Access | Physical access is secured with key fobs that are controlled by the Bank Security Officer/Head of Physical Security | C5.1 Data Centers are secured by key fob lock system 5.1.1 Please provide the evidence that access to the data center in Scarsdale is secured by a key fob lock system 5.1.2 Please provide the evidence that access to the data center in Chanin is secured by a key fob lock system | David Friedman
C5.2 Control of the issuance of key fobs 5.2.1 Please provide the list of key fobs that have been issued for Scarsdale and Chanin in 2021 5.2.2 Please provide the evidence of review and approval of the issuance of the key fobs
| IT-OPR-C6 | Independent Review of Physical Access | Physical access to the Data Center is independently reviewed by Information Security | C6.1 Physical access independent review 6.1.1 Please provide the evidence that the physical access to the Scarsdale data center is reviewed by Infosec in 2021 6.1.2 Please provide the evidence that the physical access to the Chanin data center is reviewed by Infosec in 2021 | David Friedman/ AL
Physical Environment | IT-OPR-C7 | Data Center and Computer Room Environmental Controls | The Scarsdale and Chanin Data Center are adequately protected by the appropriate environment controls | C7.1 The Scarsdale data center environment controls 7.1.1 Please verify that the following environment controls are in place: - Camera outside the Data Center Door to monitor access - Manual log in the Data Center to record non employees that enter - HVAC Air Conditioning System in place - Uninterruptable Power supply (UPS) in the event of an Power Spike or Failure - Battery Backup - Water Detection - Temperature Detection - SolarWinds report that send an alert for temperature changes within a range - Fire Detection - Fire Suppression 7.1.2 Please provide the evidence that the following equipment is in good maintenance: HVAC, UPS, Camera, SolarWinds report | David Friedman
C7.2 The Chanin data center environment controls 7.2.1 Please verify that the following environment controls are in place: - Camera outside the Data Center Door to monitor access - Manual log in the Data Center to record non employees that enter - HVAC Air Conditioning System in place - Uninterruptable Power supply (UPS) in the event of an Power Spike or Failure - Battery Backup - Water Detection - Temperature Detection - SolarWinds report that send an alert for temperature changes within a range - Fire Detection - Fire Suppression 7.2.2 Please provide the evidence that the following equipment is in good maintenance: HVAC, UPS, Camera, SolarWinds report
Business Application (MISER) Production | IT-OPR-C8 | Distribution of Business Application Reports | Controls are in place to ensure the integrity and confidentiality (if applicable) of business application reports when they are distributed to the Business Units from Production. | C8.1 Distribution of business application reports 8.1.1 Please provide the evidence that the reports are generated and provided to the Business Units without alteration. 8.1.2 Please confirm that the above is an output from the Nightly Job Schedule. | Judy Nagle
| IT-OPR-C9 | Change Management of Business Application Report | Business application reports are submitted to the IT Change Management process | C9.1 Change Management of business application reports 9.1.1 Please provide the log of changes in the business application reports in 2021 9.1.2 Please provide the evidence that changes to the business application reports in 2021 are submitted to change management (samples will be selected from the population of changes) | Judy Nagle
Monitoring of Infrastructure | IT-OPR-C10 | Infrastructure System Monitoring | System resources and performance of key components of the Bank's IT infrastructure (CPU, server memory, routers, switches, bandwidth, network devices, etc.) are monitored. Issues, including possible malfunctions or disruptions are addressed timely and appropriately. | C10.1 Monitoring of System Resource and Performance 10.1.1 Please provide the list of infrastructure components that are monitored for system resources and performance 10.1.2 Please provide the related monitoring configurations and procedures 10.1.3 Please provide the daily monitoring logs (or review of daily monitoring logs) in 2021. Samples will be chosen from the population of logs. C10.2 Issue Management 10.2.1 Please provide evidence that issues are addressed timely and appropriately in 2021 | FC
| IT-OPR-C11 | Report of Key System Metrics | Key system metrics pertaining to performance, availability and reliability are reported to and reviewed by the CTO | C11.1 Key system metrics 11.1.1 Please provide the list of key system metrics by category: performance, availability, reliability, other. 11.1.2 Please provide the rationale (what measurements and why) and the coverage (which systems/components are covered? which are not? why?) 11.1.3 Please provide the metrics-related alerts (if any), including: the condition or threshold for alert, the related action C11.2 Report of Key system metrics 11.2.1 Please provide the list of reports and the frequency of reporting (a sample of reports will be requested for testing) 11.2.2 Please provide evidence of the actions taken (if any) following the review of the reports | FC
Overnight Job | IT-OPR-C12 | Administration and Management of the Overnight Tool and Environment | The tool for the overnight process is appropriately configured for optimal performance and security. The overnight environment (jobs, schedule, applications, etc.) is subject to IT Change Management process. | C12.1 Overnight Tools 12.1.1 Please provide the list of tools used for overnight jobs (e.g., software/scripts to schedule jobs, issue tracking, hosting machines, etc.). Please provide the software name, the version, the functionalities that are in use (job scheduler, issue tracking, etc.) 12.1.2 Please provide the related configurations for optimal performance (speed, size, reliability, etc.) and security (encryption, CRUDE access, segregation of duties, privilege access, etc.) | FC
|  |  |  | C12.2 Overnight Job Environment 12.2.1 Please describe the overnight job environment: applications, hosting servers, file storage (if any), etc. 12.2.2 Please provide the related configurations for optimal performance (reliability, etc.) and security (encryption, CRUDE access, segregation of duties, privilege access, etc.) | FC
|  |  |  | C12.3 Overnight Job 12.3.1 Please provide the list of overnight jobs, including the job description, scripts 12.3.2 Please provide the related configurations for operations (error validation, alerts, etc.) and security (CRUDE access, privilege access, etc.) 12.3.3 Please provide the change management procedures related to overnight jobs (change request, approval, testing, etc.) - Sample of changes will be requested based on the population of changes in overnight job since Jan 1, 2021 | FC
| IT-OPR-C13 | Overnight Job Monitoring | An operator monitors the overnight process. Issues are automatically reported so that they can be addressed appropriately and timely in order to minimize disruptions | C13.1 Overnight Job Monitoring Team 13.1.1 Please provide the job monitoring roster (name, day/time on duty, etc.) 13.1.2 Please provide a description of roles and responsibilities 13.1.3 Please provide a call tree, contact details, etc. C13.2 Overnight Job Issue Management and Problem Management 13.2.1 Please provide the issue management and problem management procedures, including: - definition of issue and problem - detection/reporting/logging of issue and p - escalation, resolution, closing, etc. | FC
| IT-OPR-C14 | Overnight Job Status Report | The report of the overnight job status is generated and reviewed after the completion of the overnight job | C14.1 Overnight Job Status 14.1.1 Please provide the list of overnight job/error reports that were produced in the period Jan 1 - Sep 30, 2021 (a sample of reports will be selected for testing) 14.1.2 Please provide the evidence that the reports were reviewed and remediation actions were taken (if required) | FC

## Impact & Likelihood Matrix
| Frequency |  | Financial Impact
| Possible / Adverse Stress | Probable / Baseline Conditions | Profit and Loss Impact | Core Equity Impact | Balance Sheet Impact
Frequency | Event may occur over a business cycle (e.g. within 5~10 years) | Event occurs in business-as-usual situations |  | (CET-1)
Definition: |  | (e.g. every year)
Impact | VH | VH | >$5mm (~ 5% Earnings) | > 50 bps | > 5%
| H | H | $2mm - $5mm | 20 bps - 50 bps | 2% - 5%
| M | M | $1mm - $2mm | 10 bps - 20 bps | 1% - 2%
| L | L | < $1mm | < 10 bps | < 1%
| Frequency |  | Non-Financial Impact
| Possible / Adverse Stress | Probable / Baseline Conditions | Regulatory Impact | Customer Impact | Reputational Impact
Impact | VH | VH | Significant regulatory scrutiny; potential loss of business license; significant fines | Significant impact / loss of customers; likely litigation / compensation claims; significant loss of deposits | Trustee impact, deterioriation of Bank owner's value
| H | H | Regulatory scrutiny; possible legal action/regulatory fines; likely to result in improvement order | Potential financial detriment to customers / loss of customers | Negative media coverage in general public
| M | M | Internal compliance issues; possibly reportable to regulator; could result in improvement order | Moderate impact to customers, limited to a relatively small number | Negative coverage within industry
| L | L | Disciplinary warning; minimal regulator action | Minimal potential for customers impact | Negative press unlikely
Materiality Framework During Exceptional Situations
| Frequency |  | Financial Impact
| Remote / Severe Stress |  | Profit and Loss Impact | Core Equity Impact | Balance Sheet Impact
Frequency | Event occurs in exceptional situations |  |  | (CET-1)
Definition: | (e.g. tail risk, beyond 10 years)
Impact | VH |  | >$10mm (~ 10% Earnings) | > 100 bps | > 10%
| H |  | $4mm - $10mm | 40 bps - 100 bps | 4% - 10%
| M |  | $2mm - $4mm | 20 bps - 40 bps | 2% - 4%
| L |  | < $2mm | < 20 bps | < 2%

## Scope (hidden)
IT Area | Control ID | Control Description | Review Scope 2021 | Control ID (2020) | Test Results (2020) | Residual Rating (2020)
Back Up | IT-OPR-C1 | Administration and Management of Backup Tool, Environment and Jobs | Increased scope from RCSA 2020 - Backup Tool/Environment configuration (security, performance) - Monitoring, Issue management of backup jobs | IT OPR C-1 | Pass | Moderate | Exclude MISER -Only file/sever (non M/F) backup) | 2020: Networker NOW Veeam
| IT-OPR-C2 | Backup Schedule | Increased scope from RCSA 2020 - Strategy for incremental, differential, full backup - Alignment with business RPO (Recovery Point Objective) | IT OPR C-2 | Pass | Moderate | Exclude MISER
| IT-OPR-C3 | Off-site Backup and Test of Backup | Increased scope from RCSA 2020 - Offsite storage - Backup testing frequency - Alignment with business RTO (Recovery Time Objective) | IT OPR C-3 | Fail | Moderate | Exclude MISER | Iron Mountain? AWS?
Physical Access | IT-OPR-C4 | Physical Access Review and Approval | No change in scope from RCSA 2020 - Review and approval of physical access -This control was deemed NON-KEY and therefore NOT tested in 2020 | IT OPR C-4 | Not Tested | Moderate | No Change
| IT-OPR-C5 | Key Fob-enabled Physical Access | No change in scope from RCSA 2020 -Physical access secured with key FOB  | IT OPR C-5 | Pass | Moderate | Enhancement: Biometrics
| IT-OPR-C6 | Independent Review of Physical Access | No change in scope from RCSA 2020 -Physical access independently reviewed by InfoSec  | IT OPR C-6 | Pass | Low | Some Enhancements - AL now performs independent review
Physical Environment | IT-OPR-C7 | Data Center and Computer Room Environmental Controls | No change in scope from RCSA 2020 -Environmental controls | IT OPR C-7 | Pass | Low | No major changes/ Minor enhancements
Business Application (MISER) Production | IT-OPR-C8 | Business Application Production Report | No change in scope from RCSA 2020 -Integrity and confidentiality of business application reports | IT IFR-C4 | Pass | Low | Exclude MISER
| IT-OPR-C9 | Change Management of Business Application Production Report | No change in scope from RCSA 2020 -Change management of business application reports -This control was deemed NON-KEY and therefore NOT tested in 2020 | IT IFR-C5 | Not Tested | Low | Exclude MISER
Monitoring of Infrastructure | IT-OPR-C10 | Infrastructure System Monitoring | Increased scope from RCSA 2020 -Monitoring of system resources and performance -Coverage of "key" components (router, switch, server, CPU, memory, etc.) -Management of issues that result from monitoring | IT IFR-C6 | Pass | Low | Exclude MISER
| IT-OPR-C11 | Report of Key System Metrics | No change in scope from RCSA 2020 -Report of system metrics to CTO | IT IFR-C20 | Pass | Low | Exclude MISER
Overnight Job | IT-OPR-C12 | Administration and Management of the Overnight Tool and Environment | Increased scope from RCSA 2020 -Overnight Tool/Environment configuration (security, performance) -Change management  | IT IFR-C7 | Pass | Moderate | Exclude MISER | Banktel - Q2 interfaces - Datawarehouse?
| IT-OPR-C13 | Overnight Job Monitoring | No change in scope from RCSA 2020 -Overnight job operator -Monitoring, Issue management of overnight jobs -This control was deemed NON-KEY and therefore NOT tested in 2020 | IT IFR-C8 | Not Tested | Moderate | Exclude MISER
| IT-OPR-C14 | Overnight Job Status Report | No change in scope from RCSA 2020 -Review of overnight job reports -This control was deemed NON-KEY and therefore NOT tested in 2020 | IT IFR-C9 | Not Tested | Moderate | Exclude MISER

## 2020 Operations
RCSA # | Key Process | Key Steps in the Process | Process ID | Key Risks | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control Description | Key or Non Key | Control ID | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved | Notes
RCSA ID Number | Name of the key process that is being performed. | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bankwide risk taxonomy | What is the impact of this risk? Select from: Very High , High, Medium, Low | What is the probability of the risk occurring? Select from: Possible/Adverse Stress, Probable/Baseline Conditions | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low | Describe the control in detail. A key control that is significant and deemed critical to a given process, and must be performed effectively to reduce the inherent risk that it is associated with, to an acceptable level. | Is this a Key Control? Select From: Key, Non Key | Control ID Number | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often is this Control invoked? Select From: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing or decreasing? Select from: Increasing Decreasing Stable | What are the results of this RCSA? | What is the issue or gap for this key process? | What is the issue or gap for this key process? | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Which application is performing the key control
IT OPR 1 | IT Operations | Backup/Replications 1. Unisys Miser Mainframe. The Bank uses B&L Software for performing in house and offsite Tape Backup. The Bank also has replicates data to FIS. 2. Imaging system. The Bank uses the Cypress backup tool. 3. Network Backups are completed daily using SolarWinds. 4. Servers are backed up via a Data Domain Appliance. | IT OPR P-1 | The servers, network or the mainframe could crash and data may be lost if not backed up and stored at an alternate location. | IT OPR R-1 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | An Automated Job Scheduler Tool is used to back up the Data | Key | IT OPR C-1 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 4 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | 5. Unisys Mainframe, Each day, the Database is copied, which is part of the Automated Job Scheduler. Monday through Fridays are Incremental Backups and on Saturdays a Full Back up is completed of the Production, Test and Developments environments. The Replications of the Miser system and ATMS are completed every night to FIS. 6. Imaging System. The Backup Exec is in the Automated job scheduler. Full backup nightly which are maintained in house and offsite at Iron mountain. 7. Network The automated process Backs ups are stored on the SolarWinds server in Scarsdale.. When Backup's are completed SolarWinds generates a message which is sent via email. 8. Servers - VMware in Scarsdale is backed up to Chanin, and VMware in Chanin is backed up in Scarsdale. Full Backups are completed daily as pare for the job schedule as noted on the Run Sheets. |  |  |  |  | Very High | Possible/Adverse Stress | High | The Backup Tool is Configured to occur Nightly to back up the changes that occurred and weekly for a full Backup | Key | IT OPR C-2 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 4 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | 9. Unisys Mainframe. Every day Backup tapes via the VTS module in the B&L Software tapes are generated which are sent to Iron Mountain. Within the software the backups are encrypted and a Library in maintained which tracks the location and tape retention period. 10. Network - Solarwinds resides on VMWare. The Virtualized serve is also Backed up which is retained for two weeks onsite. In addition, the physical tapes are generated and are sent off to Iron Mountain. 11. Imaging system. The Bank uses the Cypress backup tool. Full backup nightly which are maintained in house and offsite at Iron mountain. 12. Servers are replicated the alternate data center. Scarsdale to Chanin and Chain are replicated at Scarsdale. Backup tapes are sent offsite to Iron Mountain |  |  |  |  | Very High | Possible/Adverse Stress | High | Backup Tapes are sent offsite that contain data, so that in the event of a partial or site Loss, the backup is available for restoration. | Key | IT OPR C-3 | Preventative | Manual | Strong | Weak | Strong | Annually | Annually | 4 | Moderate | Stable | Fail | Networker tool did not capture the data on the Application Servers and File Shares and there for the data was not saved on the Tape that were sent to Iron Mountain. The log reported the Backup complete and the results appeared to contain the backup. The root cause were (1) incompatibility between the Networker and the WMWare backup handler & (2) disk space issue in the backup appliance preventing the data backup to be written. The Bank should address the root cause of the tape backup failure by updating/replacing the backup software and hardware. The Bank should also enhance the backup monitoring process by testing the backup tapes. | IT OPR-F1 | This issue was resolved during the IT RCSA process. 1. Obtained the support and noted that the components of the Networker tool has been upgraded. We validated the automatic daily and weekly scheduler from Scarsdale to Chanin includes the Filesystem, SQL is configured as such: - Daily Clone - Daily Backup We validated the automatic daily and weekly scheduler from Chanin to Scarsdale includes the SQL, VMWare is configured as such: - Daily Clone - Daily Backup 2. We next validated the successful completions of Clones and Backups. Clones are saved for a period of 2 weeks and Backups are saved for a period of 7 years. 3. We also reviewed Managements validation of the restored backups. This was completed by IT to ensure that the contents that are being backed up are in usable format and contain the required data. | Management has already upgraded all the components of the Networker backup system. In addition, the Bank has purchased additional storage for the backup appliance. Also, the Bank will start testing the backup tapes. ( In the long term, Networker will be replaced by Veeam and tape backups will be replaced by backup to the cloud). | N/A | N/A
IT OPR 1 | IT Operations | Data Center Physical Access 1. Scarsdale - Access to the Building main doors is managed by the Property Manager. When new access or discontinued access occurs David Friedman (Physical Security) communicates with the Property Manager to activate or deactivate an Apple Key Fob. 2. The Manhattan office. Access to the Building main doors is managed by the Property Manager. When new access or discontinued access occurs David Friedman (Physical Security) communicates with the Building Manager to activate access. | IT OPR P-2 | Logical Access to the Data center may be inconsistent to individual's functional role resulting in loss or damage to technology. | IT OPR R-2 | 8.4.10 - Operational Risk - Systems - Natural Disasters, Terrorism, Vandalism and Physical Security | High | Probable/Baseline Conditions | High | Requirements for Physical Access to common grounds are communicated by the Security Officer to the Property Managers. | Non Key | IT OPR C-4 | Preventative | Manual | Adequate | Adequate | Adequate | Transactional | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT OPR 1 |  | 3. Scarsdale. The Data Center Access is further protected by a Key fob which is controlled by the Enterprise Access application. Reports are generated from the system that includes who has access and records and reports access events into secured areas. These reports are provided to the CTO Quarterly. 4. The alternate data center is referred to as Chanin. This Data Center is located on the 9th floor which uses the Keri Door System which access is managed by Fobs. Reports are generated from the system that includes who has access and records and reports access events into secured areas. These reports are provided to the CTO Quarterly. 5. Limited users have Administrative access to both the Enterprise Access and Keri applications to add, modify and revoke users access for the Software House application. |  |  |  |  | High | Possible/Adverse Stress | High | Physical Access is managed by Key Fob controlled outside of IT by the Security Officer. | Key | IT OPR C-5 | Preventative | Automated | Strong | Strong | Strong | Transactional | Annually | 2 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT OPR 1 | IT Operations | Independent Physical Access Reviews 1. Quarterly, the Information Security Group completes a review of those individual that have access to the data centers. Access us compared with Human Resources to ensure that each is an employee. | IT OPR P-3 | Access to the Data center may not be reviewed periodically to ensure accuracy of physical Access | IT OPR R-3 | 8.4.5 - Operational Risk - Systems - Identity Access Management | High | Possible/Adverse Stress | Moderate | Physical Access to the Data Center is independently reviewed by Information Security. | Key | IT OPR C-6 | Detective | Manual | Strong | Strong | Strong | Quarterly | Quarterly | 1 | Low | Decreasing | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT OPR 1 | IT Operations | Data Center Environmental Controls 1. Scarsdale - The Data in Scarsdale has environmental controls in place to protect the technology. This includes the following devices: - Camera outside the Data Center Door to monitor access - Manual log in the Data Center to record non employees that enter. - HVAC Air Conditioning System in place - Uninterruptable Power supply (UPS) in the event of an Power Spike or Failure - Battery Backup - Water Detection - Temperature Detection - SolarWinds report that send an alert for temperature changes within a range - Fire Detection - Fire Suppression | IT OPR P-4 | The Data Centers that contains servers, technology and devices may not be protected from environmental risks and the data and technology are subject to loss. | IT OPR R-4 | 8.4.10 - Operational Risk - Systems - Natural Disasters, Terrorism, Vandalism and Physical Security | High | Possible/Adverse Stress | Moderate | The Bank has set up environmental controls to protect the technology in place at the Scarsdale and Chanin Data Center. | Key | IT OPR C-7 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 1 | Low | Decreasing | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2. Chanin - The Data in Manhattan has environmental controls in place to protect the technology. This includes the following devices: - Camera outside the Data Center Door to monitor access - Manual log is not in place - HVAC Air Conditioning System in place - Uninterruptable Power supply (UPS) in the event of an Power Spike or Failure - Battery Backup - Water Detection - Temperature Detection - SolarWinds report that send an alert for temperature changes within a range - Fire Detection - Fire Suppression - Hand Held

## 2020 Infrastructure
RCSA # | Key Process | Key Steps in the Process | Process ID | Key Risks | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control | Key or Non Key | Control ID | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved | Notes
RCSA ID Number | Name of the key process that is being performed. | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bankwide risk taxonomy | What is the impact of this risk? Select from: Very High , High, Medium, Low | What is the probability of the risk occurring? Select from: Possible/Adverse Stress, Probable/Baseline Conditions | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low | Describe the control in detail. A key control that is significant and deemed critical to a given process, and must be performed effectively to reduce the inherent risk that it is associated with, to an acceptable level. | Is this a Key Control? Select From: Key, Non Key | Control ID Number | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often is this Control invoked? Select From: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing or decreasing? Select from: Increasing Decreasing Stable | What are the results of this RCSA? | What is the issue or gap for this key process? | Issue Number | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Which application is performing the key control
IT IFR 1 | IT Infrastructure | Access Request/Change/Terminations (logical access) 1.The new, change and Termination access process is decentralized. Certain applications/systems go through a central repository for access requests and changes, however not all. In addition, do to the vast number of applications, the logical access may not be role based. 2. Miser, WirePro, BAM and FCM - New, Change and Termination Access changes follow the same process. Request for Access change is initiated by a Business Unit Leader, which is documented in the same system. There are separate forms, however each provides for a historical record of the event. 3. Role Based permissions are designed and user access is granted based on the individuals responsibility. Should additional access be required outside the defined roles | IT IFR P1 | Individual may have excessive or unauthorized operating system, database, network or application access. This permits individuals to perform transaction and function that may be inconsistently with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | User access is authorized and appropriately established for all in-scope applications. Controls relating to appropriate segregation of duties over requesting and granting access to systems and data exist and are followed. | Key | IT IFR-C1 | Preventative | Manual | Weak | Weak | Weak | Daily | Daily | 0 | Very High | Increasing | Fail | A centralized approach for capturing and recording all access change requests has not been established. | IT IFR-F1 | Having a centralized approach for access management would provide for a uniform approach over all applications. | The Bank will prepare a business case and a formal proposal to centralize access management and role-based access for all applicable applications in one area that will be reviewed by senior management for the next steps. | Debi Gupta | Business case and proposal to be presented by 6/30/2021 |  | Access recertification will be performed annually to enusre that all logical accesses are appropiately authorized.
[7 empty] | Very High | Probable/Baseline Conditions | Very High | A record of all users access is maintained in the ticketing system which contains an audit trail for all change in access requirements. | Key | IT IFR-C2 | Preventative | Manual | Weak | Weak | Weak | Annually | Annually | 25 15- New /Changed Access 10-Terminated Users | Very High | Increasing | Fail | The Help Desk ticket system is not consistently used for New, modified and Terminated changes. | IT IFR-F2 | A formal request for access ticketing system should be used for all access requests, changes and terminations to provide for a permeant record of all access change events. | The Bank will deploy ServiceNow for centralizing a ticketing system for all access changes. This include employee on-boarding and off-boarding and other access changes recorded through ServiceNow. This include integration with the Bank's HRIS System ( ADP ). | Debi Gupta | 2021-06-30 | ServiceNow | In the interim, the Bank will comtinue to use AppleNet ( and its successor ServiceNow) to manually record all access changes.
[7 empty] | Very High | Probable/Baseline Conditions | Very High | Role Base permission is in place for limited applications to ensure a consistent approach for access is used. Role Based permissions over all applications has not been established. This is a control design deficiency. | Key | IT IFR-C3 | Preventative | Automated | Weak | Weak | Weak | Annually | Annually | 4 | Very High | Increasing | Fail | Access may not be a role based approach which depends on the application. This issue is reflective of a decentralized strategy for Application Access Management. | IT IFR-F3 | The use of Role Based Security for all applications should be implemented to provide for consistently in access requirements based on the user job function. Further, role based access decreases the risk of inappropriate access and improves overall access security. | The Bank will prepare a business case and a formal proposal to centralize access management and role-based access for all applicable applications in one area that will be reviewed by senior management for the next steps. | Debi Gupta | Business case and proposal to be presented by 6/30/2021 |  | Access recertification will be performed annually to enusre that all logical accesses are appropriately authorized.
IT IFR 1 | IT Infrastructure | Application Baseline 1. Standard Production Reports are generated and provided to the Business Units daily. This is part of the output from the Nightly Job Schedule. 2. Reports are used by the Bank for Daily Business activities. The report contents were validated as part of the Testing when implementing the applications. | IT IFR P2 | Reports may not be produced or may contain inaccurate information to meet the needs of the Business. As decisions are determined on the output misinformation could result in ineffective outcomes. | IT IFR R2 | 8.4.6 - Operational Risk - Systems - Data Integrity and Quality | High | Possible/Adverse Stress | Moderate | Reports are generated directly from the Applications and are distributed to the Business Units with out alterations. | Key | IT IFR-C4 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 5 days | Low | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | High | Possible/Adverse Stress | Moderate | For each new release, upon User Acceptance testing the Reports contents are validated to ensure that the output is accurate. | Non Key | IT IFR-C5 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 0 Not a Key Control | Low | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Uptime/Performance 1. Daily System Performance Metrics are produced via a report that includes: - Response time - Uptime Management - Tools and Reporting These reports are reviewed and changes to load balancing, disc space etc. are completed when necessary. | IT IFR P3 | Performance not monitored could lead to a degradation in performance of the use of technology. | IT IFR R3 | 8.4.6 - Operational Risk - Systems - Data Integrity and Quality | High | Possible/Adverse Stress | Moderate | Daily system performance is captured and monitored to ensure that the systems have the necessary technology resources for peak performance. | Key | IT IFR-C6 | Detective | Automated | Adequate | Strong | Strong | Annually | Annually | 1 - Miser 1 - Network | Low | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | In house Managed Systems 1. Automated Job schedules for the Miser application is in place to ensure, that the daily interfaces and backup process complete without human interaction. 2. In the event of a Job Failure or disruption, an alert is sent to the Night Operator for actions to be taken to correct the incident. 3. Daily reports are generated nightly and provided to the Agency electronically as a result of the job schedule. | IT IFR P4 | Night processing of Interface updates, backups and Report Generation may not be completed fully, which could result in data completeness and accuracy. | IT IFR R4 | 8.4.6 - Operational Risk - Systems - Data Integrity and Quality | Very High | Possible/Adverse Stress | High | An Automated Job Schedule Tool is used which enforces the system to complete the Night processing without the requirements of the Operator | Key | IT IFR-C7 | Preventative | Automated | Adequate | Strong | Strong | Annually | Annually | 1. Banktel 2. Q2 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | An Operator is available to support the Night Process and make any corrections in processing if necessary. An Automated control is in place to notify the Night Operator in the event of a job schedule disruptions. | Non Key | IT IFR-C8 | Detective | Manual | Adequate | Strong | Strong | Annually | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | Reports are generated, reviewed and approved for the completion of Night Processing | Non Key | IT IFR-C9 | Detective | Manual | Adequate | Strong | Strong | Annually | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | New Devices Added/Captured (NAC) 1. A NAC is not in place and this is a Self Identified Issue | IT IFR P5 | Devices could be attached to the Banks Network and go undiscovered. This could result in loss of control over the Network and further infiltrate systems and applications. | IT IFR R5 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | A Network Access Control (NAC) has not been implemented. This is a self identified control GAP | Key | IT IFR-C10 | Detective | Automated | Weak | Weak | Weak | Transactional | Annually | NAC | Very High | Increasing | Fail | The Bank has not implemented a Network Access Control to automatically detect and report devices that are attached the Bank's Network. | IT IFR-F4 | The Bank should implement a NAC to have real-time visibility of devices, users and applications that are accessing network. Such devices would provide the Bank the ability to immediately respond to unknown network events. | The Bank will implement a Network Access Control device ( NAC ) | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Network Segmentation 1. The Network has not been segmented and therefore is not in place and this is a Self Identified Issue | IT IFR P6 | Proper Network Segmentation would reduce the Network Attack impacts. Without an effective approach management may not be able to minimize the impact in the event of a malicious attack. | IT IFR R6 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | The Bank has not implemented Network Segmentation which would provide the Bank the ability to implement stronger security measures. | Key | IT IFR-C11 | Preventative | Automated | Weak | Weak | Weak | Transactional | Annually | Segmented Network | Very High | Increasing | Fail | The Bank has not implemented Network Segmentation to improve the security posture of the Bank. Network Segmentation will limit the range of access provided to individuals that gain Network Access. | IT IFR-F5 | The Bank should develop a strategic approach which may include service providers and tools. The Network should then separated and to into zones to secure each and limit and manage lateral movement. | The Bank is implementing a DMZ and at the same time, executing a plan for network segmentation that is currently under way. | Debi Gupta | 2020-12-31
IT IFR 1 | IT Infrastructure | Vendor Supported Systems 1. The Bank maintains an inventory of all IT Service Providers for monitoring contract maturity dates which includes key contacts. The inventory is updated as changes in relationships occur and is reviewed annually. This will be covered in a separate Vendor Management Risk Assessment 2. Service Providers do not have access to any of the systems. This control prevents Third Party relationships for modifying data, software and parameters. | IT IFR P7 | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | The Bank has a separate Vendor Management program outside of IT. | Non Key | IT IFR-C12 | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 0 Not a Key Control | Low | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | High | Possible/Adverse Stress | Moderate | Service providers are not permitted access by the Bank. When vendors are provided access is monitored and revoked up on completion of the effort. Contractors are provided access and access is disabled at 90 days, where approvals are required for the contractor to continue to have access. | Key | IT IFR-C13 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 4 | Low | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Network Administrator Rights 1. Network Administrators access is restricted and reviewed to ensure that access is consistent with each users functional role. | IT IFR P8 | Unauthorized persons may have Administrator rights and therefore could impact data integrity. | IT IFR R8 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | Access to privileged Network accounts is limited to appropriate individuals. | Key | IT IFR-C14 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 100% Domain Admins | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Single Sign on 1.The Bank has not implemented Single Sign. This is a self identified issue. | IT IFR P9 | Users access may be not be tied to a single sign on solution, which increases the risk to the Bank via multiple paths of access to the Banks Systems | IT IFR R9 | 8.4.5 - Operational Risk - Systems - Identity Access Management | High | Probable/Baseline Conditions | High | The Bank has not implemented Single Sign. This is due to the distributed approach of managing application access and that some of those systems do not adopt Active Directory Security Policy. | Key | IT IFR-C15 | Preventative | Manual | Weak | Weak | Weak | Annually | Annually | Single Sign on | High | Increasing | Fail | Single Sign on has not been implemented. While many applications adopt Active Directory Security, not all do. This is due to the decentralized approach for application management. Through discussions, as applications are upgraded/replaced these are required to adopt the AD Security Policy. | IT IFR-F6 | The Bank should continue to upgrade and replace the applications with those that can be bound to Active Directory. | The Bank will continue to implement single sign-on for all applications that support SSO with Active Directory. However, there are legacy applications ( like the core Miser ) and some outsourced applications that would not support SSO with Active Directory and can't be migrated or converted easily, without business impact. | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Remote Access 1. Remote access is provided to limited Users of which these are provided access via VPN which are defined in Active Directory via LDAP which are authenticated via Okta Multifactor Authentication. | IT IFR P10 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Systems as controls may not be in place to authenticate remote access users. | IT IFR R10 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | Users access is controlled via the Virtual Private Network, of which all user who remote access in are authenticated via Okta multifactor authentication. | Key | IT IFR-C16 | Preventative | Automated | Strong | Strong | Strong | Transactional | Annually | 1 Okta Configuration 5 Remote Access Requests | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Firewall Management 1, Firewall changes are driven through requests or security related activities and are communicated on a manual form by the Network Group to the Information Security Group prior to change. Upon approval only authorized individuals can make changes to firewall. 2. The Information Security Group reviews the manual form and approves the change. This is communicated back to the Network Group via email. 3. The Solar Winds tool completes a nightly spool of which the report on firewall changes is sent to the Information Security group where each change on the report is reconciled back to the Ticket. | IT IFR P11 | Access may not be appropriately restricted to the firewall which could lead to unauthorized changes. | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | The firewall is configured to limit the number of users who can make changes. | Key | IT IFR-C17 | Preventative | Manual | Adequate | Strong | Adequate | Transactional | Annually | 1. Firewall Permissions 2. Sample Changes | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | The Solar Winds Tool is used to provide performance monitoring and capture changes | Non Key | IT IFR-C18 | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | All Firewall Changes are reviewed by the Info Sec Group and are reconciled back to the Solar Winds Report | Key | IT IFR-C19 | Detective | Automated | Adequate | Strong | Adequate | Transactional | Annually | 2. Sample Changes 1 SolarWinds Report Reconciliation | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Performance Metric Reporting 1. Performance Reports are assembled for presentation to the CTO. This reports are provided monthly to the CTO to ensure that management is made aware of the quality of processing | IT IFR P12 | Performance metric's may not be reported to the CTO to ensure that the systems health is communicated. Without the communication, the systems performance could degragate. | IT IFR R12 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | High | Possible/Adverse Stress | Moderate | Performance reports are provided to the CTO to communicate the health of the network, core and servers. | Key | IT IFR-C20 | Detective | Manual | Adequate | Strong | Adequate | Monthly | Monthly | 2 | Low | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Virus Protection 1. For non Core Application Symantec monitoring is being completed. This is primarily used to ensure that Virus definitions and Advanced Protection are up to date on workstations and servers. | IT IFR P13 | IT resources could be compromised and business operations could be disrupted due to a virus without effective updates to servers and workstations. | IT IFR R13 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | Symantec Security Monitoring Tool has been implemented and is used to capture virus protection security events for workstations and servers. | Key | IT IFR-C21 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | 1 Symantec Report | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Patch Management 1. The KACE tool is used to identify the Patch requirements for the Bank's Technology. 2. Once the patch is obtained each week the change/update is scheduled and applied to the appropriate server, workstation, printer and/or network component. | IT IFR P14 | Without an effective patch management identification process IT resources could be compromised and business operations could be disrupted. | IT IFR R14 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | Security threats and vulnerabilities are identified and assessed through the use of a tool. | Key | IT IFR-C22 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | 1 KACE Report | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Email 1. Email is controlled and managed by the BNK through a relationship with Google of which the G-Suite tools are used. All new users that require access go through the access control process as noted above. 2. The email System has controls in place to restrict unauthorized individuals from communicating with the Agency. Further the email scans for each outgoing for Not Public Information (NPI). | IT IFR P15 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Email System. Further, malware could be introduced which could lead to a disruption in processing | IT IFR R15 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | The Email Server is outsourced to G-Suite of which security controls are in place to monitor content that is leaving the Bank the contains NPI | Key | IT IFR-C23 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | 3 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Inherent Risk Rating (hidden)
Inherent Risk Determination
If the Probabliity = Possible/ Adverse Stress, then the Inherent Risk Value is reduced 1 level from from the Impact Rating
If the Probablity = If Probable/Baseline Conditions the Inherent Risk Value the same as the Impact Rating

## Lists for Data Validation
Risk Taxonomy | Impact Rating | Probability Rating | Inherent Risk Rating | Type of Control (Preventive or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Testing Frequency | Residual Risk Rating | Direction of Risk | Key/Non Key | Control Occurrence
1.1.0 - Credit Risk - Counterparty | Very High | Possible/Adverse | Very High | Preventative | Automated | Strong | Strong | Strong | Daily | Very High | Increasing | Key | Daily
1.2.0 - Credit Risk - Concentration | High | Probable/Baseline | High | Detective | Manual | Adequate | Adequate | Adequate | Weekly | High | Decreasing | Non Key | Weekly
1.3.0 - Credit Risk - Settlement | Moderate |  | Moderate |  |  | Weak | Weak | Weak | Monthly | Moderate | Stable |  | Monthly
1.4.0 - Credit Risk - Collateral / Credit Mitigation | Low |  | Low | [5 empty] | Quarterly | Low |  |  | Quarterly
2.1.0 - Liquidity Risk - Funding Liquidity | [8 empty] | Annually |  |  |  | Annually
2.2.0 - Liquidity Risk - Non Traded Market | [8 empty] | Transactional |  |  |  | Transactional
3.1.0 - Capital Risk - Capital Adequacy
4.1.1 - Market Risk - Interest Rate - Delta
4.1.2 - Market Risk - Interest Rate - Gamma (Convexity)
4.1.3 - Market Risk - Interest Rate - Vega
4.1.4 - Market Risk - Interest Rate - Theta
4.1.5 - Market Risk - Interest Rate - Correlation
4.1.6 - Market Risk - Interest Rate - Event
4.1.7 - Market Risk - Interest Rate - Discount Rate
4.1.8 - Market Risk - Interest Rate - Prepayment
4.2.1 - Market Risk - Foreign Exchange/Currency - Delta
4.2.2 - Market Risk - Foreign Exchange/Currency - Gamma (Convexity)
4.2.3 - Market Risk - Foreign Exchange/Currency - Vega
4.2.4 - Market Risk - Foreign Exchange/Currency - Theta
4.2.5 - Market Risk - Foreign Exchange/Currency - Correlation
4.2.6 - Market Risk - Foreign Exchange/Currency - Event
4.3.1 - Market Risk - Equity - Delta
4.3.2 - Market Risk - Equity - Gamma (Convexity)
4.3.3 - Market Risk - Equity - Vega
4.3.4 - Market Risk - Equity - Theta
4.3.5 - Market Risk - Equity - Correlation
4.3.6 - Market Risk - Equity - Event
4.3.7 - Market Risk - Equity - Dividend
4.3.8 - Market Risk - Equity - Borrow Cost
4.4.1 - Market Risk - Commodity - Delta
4.4.2 - Market Risk - Commodity - Gamma (Convexity)
4.4.3 - Market Risk - Commodity - Theta
4.4.4 - Market Risk - Commodity - Correlation
4.4.5 - Market Risk - Commodity - Event
5.1.0 - Model Risk - Intrinsic Uncertainty
5.2.0 - Model Risk - Model Design
5.3.0 - Model Risk - Model Usage
5.4.0 - Model Risk - Model Documentation
5.5.0 - Model Risk - Model Validation
6.1.0 - Business Risk - Failure to Meet Earnings Target
6.2.0 - Business Risk - Failure to Adapt to Long-Term Strategic Trends
6.3.0 - Business Risk - New Business and Change Management
6.4.0 - Business Risk - Investment
7.1.1.1 - Reputational Risk - Product - Product Liability - Financial Product Safety
7.1.1.2 - Reputational Risk - Product - Product Liability - Responsible Investment
7.2.1.1 - Reputational Risk - Environmental - Climate Change - Greenhouse Gas (GHG) Emissions
7.2.2.1 - Reputational Risk - Environmental - Natural Resources - Operating from Resource Stressed Locations - Water availability, etc.
7.2.3.1 - Reputational Risk - Environmental - Pollution and Waste - Carbon Footprint
7.2.3.2. - Reputational Risk - Environmental - Pollution and Waste - Energy Efficiency
7.3.1.1 - Reputational Risk - Societal - Human Capital - Diversity and Inclusion (MBE owned, etc.)
7.3.1.2 - Reputational Risk - Societal - Human Capital - Health and Safety
7.3.1.3 - Reputational Risk - Societal - Human Capital - Economic Contribution - Community Re-investment
7.4.1.1 - Reputational Risk - Governance - Corporate Behavior - Anti Bribery Policy
7.4.1.2 - Reputational Risk - Governance - Corporate Behavior - Anti Corruption Policy
7.4.1.3 - Reputational Risk - Governance - Corporate Behavior - Protected Ethics Advice & Reporting Mechanisms
8.1.1 - Operational Risk - Financial Crime - Fraud, Theft or Misappropriation of Assets
8.1.2 - Operational Risk - Financial Crime - Data Theft or Misuse
8.1.3 - Operational Risk - Financial Crime - Data Protection & Customer Confidentiality
8.1.4 - Operational Risk - Financial Crime - False Representation & Suitability and Appropriateness
8.1.5 - Operational Risk - Financial Crime - AML ¦ BSA
8.1.6 - Operational Risk - Financial Crime - Sanctions
8.2.1 - Operational Risk - Compliance - Branch and ATM Operations
8.2.2 - Operational Risk - Compliance - Funds Deposit and Transfers/Transactions
8.2.3 - Operational Risk - Compliance - Credit Origination
8.2.4 - Operational Risk - Compliance - Account Setup and Opening
8.2.5 - Operational Risk - Compliance - Customer Communications and Marketing Material
8.2.6 - Operational Risk - Compliance - Account Maintenance and Servicing
8.2.7 - Operational Risk - Compliance - Customer Protection
8.2.8 - Operational Risk - Compliance - Record Keeping and Customer Reporting
8.2.9 - Operational Risk - Compliance - Corporate/Business Practices
8.2.10 - Operational Risk - Compliance - Regulatory Reporting
8.2.11 - Operational Risk - Compliance - Internal Reporting and Monitoring
8.3.1 - Operational Risk - People and Conduct - Employment Laws and HR Practices
8.3.2 - Operational Risk - People and Conduct - Discrimination, Harassment or Bullying
8.3.3 - Operational Risk - People and Conduct - Diversity, Code of Conduct and Ethical Behavior
8.3.4 - Operational Risk - People and Conduct - Compliance with Policies and Procedures
8.4.1 - Operational Risk - Processes - Branch and ATM Operations
8.4.2 - Operational Risk - Processes - Funds Deposit and Transfers/Transactions
8.4.3 - Operational Risk - Processes - Credit Origination
8.4.4 - Operational Risk - Processes - Account Setup and Opening
8.4.5 - Operational Risk - Processes - Customer Communications and Marketing Material
8.4.6 - Operational Risk - Processes - Account Maintenance and Servicing
8.4.7 - Operational Risk - Processes - Customer Protection
8.4.8 - Operational Risk - Processes - Record Keeping and Customer Reporting
8.4.9 - Operational Risk - Processes - Corporate/Business Practices
8.4.10 - Operational Risk - Processes - Regulatory Reporting
8.4.11 - Operational Risk - Processes - Internal Reporting and Monitoring
8.5.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability
8.5.2 - Operational Risk - Systems - Application Maintenance, Asset Management and Change Control
8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing
8.5.4 - Operational Risk - Systems - End User Computing
8.5.5 - Operational Risk - Systems - Identity Access Management
8.5.6 - Operational Risk - Systems - Data Integrity and Quality
8.5.7 - Operational Risk - Systems - Data Architecture and Governance
8.6.1 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Selection
8.6.2 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Contracting
8.6.3 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Due Diligence
8.6.4 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Inadequate Monitoring
8.6.5 - Operational Risk - Third Party Suppliers, Vendors and Outsourcing - Supplier Failure
8.6.6 - Operational Risk - Third Party Suppliers, Vendors and outsourcing - Fourth Party
8.6.7 - Operational Risk - Third Party Suppliers, Vendors and Outsourcing - Offboarding
8.7.1 - Operational Risk - Cyber - Appropriate Hardening
8.7.2 - Operational Risk - Cyber - Secure Configuration/ Configuration Management
8.7.3 - Operational Risk - Cyber - Patch Management
8.7.4 - Operational Risk - Cyber - Security Architecture
8.7.5 - Operational Risk - Cyber - Vulnerability Management/ Zero-Day Vulnerabilities
8.7.6 - Operational Risk - Cyber - Anomalies & Events
8.7.7 - Operational Risk - Cyber - Protective Technology
8.7.8 - Operational Risk - Cyber - Security Continuous Monitoring
8.8.1 - Operational Risk - Resiliency - Business Continuity Plan
8.8.2 - Operational Risk - Resiliency - Disaster Recovery
8.8.3 - Operational Risk - Resiliency - Backups
8.8.4 - Operational Risk - Resiliency - Terrorism, Vandalism and Physical Security
8.8.4 - Operational Risk - Terrorism, Vandalism and Physical Security

## Testing Frequency (hidden)
Control Frequency | Assumed Population size | Minimum Sample Size
Annual | 1 | 1
Quarterly | 4 | 2
Monthly | 12 | 3
Weekly | 52 | 5
Daily | 250 | 20

## Residual Risk Rating (hidden)
Residual Risk
| Weak | Low | Moderate | High | Very High
Control | Adequate | Low | Low | Moderate | High
| Strong | Low | Low | Low | Moderate
|  | Low | Moderate | High | Very High
Inherent Risk

## Control Rating (hidden)
Control Rating
Operating Effectiveness
|  | Strong | Adequate | Weak
Design Effectiveness | Strong | Strong | Adequate | Weak
| Adequate | Adequate | Adequate | Weak
| Weak | Weak | Weak | Weak