## IF2021
RCSA # | Process Domain | Initial Questions | Key Process | Key Steps in Process | Process ID | Key Risks | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control Description | Control ID | Key or Non Key | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved
RCSA ID Number | Name of the key process that is being performed. |  |  | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bank wide risk taxonomy | What is the impact of this risk? Select from: Very High , High, Medium, Low | What is the probability of the risk occurring? Select from: Possible/Adverse Stress, Probable/Baseline Conditions | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low |  | Control ID Number | Is this a Key Control? Select From: Key, Non Key | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often is this Control invoked? Select From: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing or decreasing? Select from: Increasing Decreasing Stable | What are the results of this RCSA? | What is the issue or gap for this key process? | Issue Number | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Which application is performing the key control
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) | Logical User Access 1.The new, change and Termination access process is decentralized. Certain applications/systems go through a central repository for access requests and changes, however not all. In addition, do to the vast number of applications, the logical access may not be role based. 2. Miser, WirePro, BAM and FCM - New, Change and Termination Access changes follow the same process. Request for Access change is initiated by a Business Unit Leader, which is documented in the same system. There are separate forms, however each provides for a historical record of the event. 3. Role Based permissions are designed and user access is granted based on the individual's responsibility. Should additional access be required outside the defined roles, a request needs to be submitted, reviewed and approved accordingly. This additionally granted access will be reviewed annually, following the Bank's standard user access review process. | IT IFR P1 | Individuals may have excessive or unauthorized access to operating system, database, network or application. This permits individuals or malicious parties with access to the individuals' account to perform functions and execute transactions that may be inconsistent with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | User access is authorized and an IAM (Identity Access Management) process is established for all networked and applications. This includes maintaining the proper segregation of duties between approved and implementer of any user change. (Control wording updated in 2021) | IT IFR-C1 | Key | Preventative | Manual | Adequate | Adequate | Adequate | Transactional | Quarterly | 25 15- New /Changed Access 10-Terminated Users | High | Decreasing | Pass
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) |  | IT IFR P1 | Individuals may have excessive or unauthorized access to operating system, database, network or application. This permits individuals or malicious parties with access to the individuals' account to perform functions and execute transactions that may be inconsistent with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | A record of all users access is maintained in the ticketing system which contains an audit trail for all change in access requirements (Add, Changes, Terminations of Users). | IT IFR-C2 | Key | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 25 15- New /Changed Access 10-Terminated Users | High | Decreasing | Pass
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) |  | IT IFR P1 | Individuals may have excessive or unauthorized access to operating system, database, network or application. This permits individuals or malicious parties with access to the individuals' account to perform functions and execute transactions that may be inconsistent with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | Role Base permission is in place for critical applications to ensure that a user as access in accordance with their job functions. (Control wording updated in 2021) | IT IFR-C3 | Key | Preventative | Automated | Adequate | Adequate | Adequate | Annually | Annually | 5 | High | Decreasing | Pass
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) | Network Privilege Access 1. Network Administrators access is restricted and reviewed to ensure that access is consistent with each users functional role. 2. An Active directory group - "network admin" - is created and this grants access to network devices. Additional authorization is provide via OKTA for Multi Factor Authentication. | IT IFR P8 | Access to the privilege accounts of the Bank's infrastructure, if unauthorized or inadequately managed, may expose the Bank to privilege misuse and attacks from both internal and external malicious actors | IT IFR R8 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Moderate | Possible/Adverse Stress | Low | Access to privileged Network accounts is limited to appropriate individuals | IT IFR-C14 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 100% Domain Admins | Low | Decreasing | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) | Single Sign-On 1. Bank has implemented OKTA as a single sign on. OKTA ties into active directory for user sign-on information. 2. When a new application is purchase a review is done to determine if the application can be integrated into OKTA pool for single sign-on. 3. The application pool contains all applications that utilize single sign -on | IT IFR P9 | Users access may not be tied to a single sign on solution, which increases the risk to the Bank via multiple paths of access to the Banks Systems. | IT IFR R9 | 8.4.5 - Operational Risk - Systems - Identity Access Management | High | Probable/Baseline Conditions | High | The Bank implements Single-Sign On, which would provide the ability to implement stronger security measures. (Control wording updated in 2021) | IT IFR-C15 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | Single Sign on | Low | Decreasing | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Network Access Control | Network Access Control Access to the network will comply to the network security policy. This includes the pre-admission and post-admission security policy that determines where users and devices can go in the network and what they can do once admitted into the network. | IT IFR P5 | Devices could be attached to the Banks Network and go undiscovered. This could result in loss of control over the Network and further infiltrate systems and applications. | IT IFR R5 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | The Bank has implemented Network Access Control (NAC) which would provide the Bank the ability to implement stronger security measures. (Control wording updated in 2021) | IT IFR-C10 | Key | Preventative | Automated | Weak | Weak | Weak | Transactional | Annually | Segmented Network | Very High | Stable | Fail | (2020 Issue) The Bank has not completed the Network Access Control (NAC) project. Consequently, the rating of this control remained unchanged from that of 2020. | IT IFR-F4 | (2020) The Bank should develop a strategic approach which may include service providers and tools. The Network should then separated and to into zones to secure each and limit and manage lateral movement. | (2020) The Bank is implementing the NAC project, due to conclude end of June 2021 (2021 update) The target date is updated to 10/31. (ISSUE-0000001632) | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Network Architecture | Network Segmentation Network architecture is designed according to the security principles: domain separation and layering. Domain separation separates network traffic into network segments to mitigate the risk of adversary learning about network design. Network layering segregates the functions (e.g. OSI seven layers) to provide better security assurance. | IT IFR P6 | Proper Network Segmentation would reduce the Network Attack impacts. Without an effective approach, management may not be able to minimize the impact in the event of a malicious attack. | IT IFR R6 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | The Bank has implemented Network Segmentation which would provide the Bank the ability to implement stronger security measures. (Control wording updated in 2021) | IT IFR-C11 | Key | Preventative | Automated | Weak | Weak | Weak | Transactional | Annually | Segmented Network | Very High | Stable | Fail | (2020 Issue) The Bank has not completed the Network Segmentation project. Consequently, the rating of this control remained unchanged from that of 2020. | IT IFR-F5 | (2020) The Bank should develop a strategic approach which may include service providers and tools. The Network should then separated and to into zones to secure each and limit and manage lateral movement. | (2020) The Bank is implementing the network segmentation project, due to conclude end of June 2021. (2021 update) The target date is updated to 11/30 (ISSUE-0000001526) | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Vendor Security | IT Vendor Management 1. The Bank maintains an inventory of all IT Service Providers for monitoring contract maturity dates which includes key contacts. The inventory is updated as changes in relationships occur and is reviewed annually. This will be covered in a separate Vendor Management Risk Assessment | IT IFR P7 | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | Access is only granted to employees of a Service Provider that is listed in ABS Vendor Management's "vendor list". (Control wording updated in 2021) | IT IFR-C12 | Key | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 1 | Low | Decreasing | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Vendor Security | Third Party Network Access 2. Service Providers do not have access to any of the systems. This control prevents Third Party relationships for modifying data, software and parameters. | IT IFR P7 | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | Service providers are not permitted access to the Bank. When vendors are provided access, it is monitored and revoked up on completion. Contractors are provided access and access is disabled at 90 days, where approvals are required for the contractor to continue to have access. (Control wording updated in 2021) | IT IFR-C13 | Key | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 8 accounts granted to non-permanent employees + all access to CORE applications | Low | Decreasing | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Network Security | Remote Access 1. Remote access is provided to limited Users of which these are provided access via VPN which are defined in Active Directory via LDAP which are authenticated via Okta Multifactor Authentication. | IT IFR P10 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Systems as controls may not be in place to authenticate remote access users. | IT IFR R10 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Moderate | Possible/Adverse Stress | Low | Remote access communications to the Bank’s Corporate Systems are authenticated, encrypted and monitored. Remote access to ABS information assets using bank-issued devices is secured by Virtual Private Network (VPN). Authentication of remote access using bank-issued devices is secured by MFA (multi-factor authentication) in OKTA, which is integrated with ABS Active Directory. Idle access session requires user to re-authenticate Remote access to ABS information assets using non bank-issued devices is secured by Virtual Desktop Infrastructure (VDI). Remote Desktop Protocol (“RDP”) to connect to their Computing Devices is restricted (Control wording updated in 2021) | IT IFR-C16 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | Okta Configuration VPN Configuration | Low | Decreasing | Pass | N/A | N/A | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Change Control and Configuration Management | Firewall Management Firewall changes 1. Requests for changes are made to the networking infrastructure group for a firewall change. 2. Networking performs a due diligence which includes inspecting the current rules to determine if there is a rule that is already current and can address the request. 3. The group ensures that the request is complete – source and destination IP, Port Opening etc. 4. Network infrastructure completes a firewall request form and submits to Info security for their approval. Form is emailed to Info sec general mail box – At the same time a service now ticket is generated at the same time. 5. The change is presented and approved by the CAB - Documentation is discussed reviewed and attached to the service now change ticket. 6. Once the request is approved at the CAB meeting the change is tested within a window. 7. Testing is provided at end of implementation window. 8. Validation is performed by info security of all fire wall changes. | IT IFR P11 | Access may not be appropriately restricted to the firewall which could lead to unauthorized changes. Palo Alto / CISO FTD - FirePower Threat Defense Only the Networking group is authorized to make changes to the firewall configuration. Info Security has only read access to the firewall configuration/rule sets. | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | Access to firewalls is restricted to designated IT professionals. All changes to the firewalls must follow the Bank's Change Management Policy (Control wording updated in 2021) | IT IFR-C17 | Key | Preventative | Manual | Adequate | Adequate | Adequate | Transactional | Annually | 1. Firewall Permissions 2. Sample Changes | Moderate | Stable | Pass | None | None | None | None | None | None | Palo Alto / CISO FTD - FirePower Threat Defense
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending |  |  | IT IFR P11 |  | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Moderate | Possible/Adverse Stress | Low | The Solar Winds Tool is used to provide performance monitoring and capture changes | IT IFR-C18 | Non Key | Preventative | Automated | Adequate | Adequate | Adequate | Annually | Annually | 0 Not a Key Control | Low | Decreasing | Pass | None | None | None | None | None | None | Palo Alto / CISO FTD - FirePower Threat Defense
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending |  |  | IT IFR P11 |  | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | A reconcilliation is performed between the changes in Firewall rules and the Solar Wind Log. (Control wording updated in 2021) | IT IFR-C19 | Key | Detective | Automated | Adequate | Adequate | Adequate | Transactional | Annually | 2. Sample Changes 1 SolarWinds Report Reconciliation | Moderate | Stable | Pass |  | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Threat and Vulnerability Management (Infrastructure) | Virus and Malicious Software Protection 1. For non Core Application Symantec monitoring is being completed. This is primarily used to ensure that Virus definitions and Advanced Protection are up to date on workstations and servers. | IT IFR P13 | IT resources could be compromised and business operations could be disrupted due to a virus without effective updates to servers and workstations | IT IFR R13 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | High | Possible/Adverse Stress | Moderate | All network devices have an endpoint protection solution installed. Daily automatic local scans for potential threats are scheduled. Anti-malware software and definition files are set to automatically receive the latest updates. The ability to disable or remove anti-malware programs is restricted. (Control wording updated in 2021) | IT IFR-C21 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 1 Symantec Report | Low | Decreasing | Pass | None | None | None | None | None | None | Symantec
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Threat and Vulnerability Management (Infrastructure) | Patch Management 1. The KACE tool is used to identify the Patch requirements for the Bank's Technology. 2. Patches are tested in development environment and confirmation is received from the end users before being moved to production. This done on Patch Tuesday of where the released patches are reviewed and scheduled. 3. A Daily report that is run to determined status of patches – the results are then match to KACE to schedule implementation of patches based on the schedule – Wednesdays and Friday. Workstations are schedule during the week. | IT IFR P14 | Without an effective patch management identification process IT resources could be compromised and business operations could be disrupted. | IT IFR R14 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Moderate | Possible/Adverse Stress | Low | Required security patches are regularly identified and assessed by regularly reviewing and assessing threats and vulnerabilities Security patches are tested before being installed to the production environment . A remediation/validation scan is performed to ensure that the vulnerabilities are eliminated due to the installation of the patch (Control wording updated in 2021) | IT IFR-C22 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 1 KACE Report | Low | Decreasing | Pass | None | None | None | None | None | None | KACE
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Information Transfer | Email 1. Email is controlled and managed by the BNK through a relationship with Google of which the G-Suite tools are used. All new users that require access go through the access control process as noted above. 2. The email System has controls in place to restrict unauthorized individuals from communicating with individuals and entities outside of the Bank. In addition, the email system shall scan for, then prevent all unauthorized outgoing messages containing Not Public Information (NPI). | IT IFR P15 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Email System. Further, malware could be introduced which could lead to a disruption in processing | IT IFR R15 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | E-mails and e-mail systems are protected from unauthorized access, modification or denial of service, spam and phishing emails, malicious e-mails, attachments and the leaking of non-public information. E-mails with non-public information must be authorized. Its information is masked or encrypted. (Control wording updated in 2021) | IT IFR-C23 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 1 GMAIL Configuration 1 NETSKOPE Configuration 1 VIRTRU Configuration | Low | Stable | Pass | None | None | None | None | None | None | GMAIL, NETSPOKE, VIRTRU

## Aggregate
2021 | [6 empty] | 2020
Risk ID | Control ID | Inherent Risk Rating | Control Rating | Residual Rating | Aggr. Residual Rating | Risk | Risk ID | Control ID | Inherent Risk Rating | Control Rating | Residual Rating | Aggr. Residual Rating
IT IFR R1 | IT IFR-C1 | Very High | Adequate | High | High | Individual may have excessive or unauthorized operating system, database, network or application access. This permits individuals to perform transaction and function that may be inconsistently with the individuals job function. | IT IFR R1 | IT IFR-C1 | Very High | Weak | Very High | Very High
| IT IFR-C2 |  | Adequate |  |  |  |  | IT IFR-C2 |  | Weak | Very High
| IT IFR-C3 |  | Adequate |  |  |  |  | IT IFR-C3 |  | Weak | Very High
IT IFR R8 | IT IFR-C14 | Low | Strong | Low | Low | Reports may not be produced or may contain inaccurate information to meet the needs of the Business. As decisions are determined on the output misinformation could result in ineffective outcomes. | IT IFR R2 | IT IFR-C4 | Moderate | Strong | Low | Low | Now in IT-OPS
IT IFR R9 | IT IFR-C15 | High | Strong | Low | Low |  |  | IT IFR-C5 |  | Strong | Low |  | Now in IT-OPS
IT IFR R5 | IT IFR-C10 | Very High | Weak | Very High | Very High | Performance not monitored could lead to a degradation in performance of the use of technology. | IT IFR R3 | IT IFR-C6 | Moderate | Strong | Low | Low | Now in IT-OPS
IT IFR R6 | IT IFR-C11 | Very High | Weak | Very High | Very High | Night processing of Interface updates, backups and Report Generation may not be completed fully, which could result in data completeness and accuracy. | IT IFR R4 | IT IFR-C7 | High | Strong | Moderate | Moderate | Now in IT-OPS
IT IFR R7 | IT IFR-C12 | Moderate | Adequate | Low | Low |  |  | IT IFR-C8 |  | Strong | Moderate |  | Now in IT-OPS
| IT IFR-C13 |  | Strong |  |  |  |  | IT IFR-C9 |  | Strong | Moderate |  | Now in IT-OPS
IT IFR R10 | IT IFR-C16 | Low | Strong | Low | Low | Devices could be attached to the Banks Network and go undiscovered. This could result in loss of control over the Network and further infiltrate systems and applications. | IT IFR R5 | IT IFR-C10 | Very High | Weak | Very High | Very High
IT IFR R11 | IT IFR-C17 | High | Adequate | Moderate | Moderate | Proper Network Segmentation would reduce the Network Attack impacts. Without an effective approach management may not be able to minimize the impact in the event of a malicious attack. | IT IFR R6 | IT IFR-C11 | Very High | Weak | Very High | Very High
| IT IFR-C18 |  | Adequate |  |  | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | IT IFR-C12 | Moderate | Adequate | Low | Low
| IT IFR-C19 |  | Adequate |  |  |  |  | IT IFR-C13 |  | Strong | Low
IT IFR R13 | IT IFR-C21 | Moderate | Strong | Low | Low | Unauthorized persons may have Administrator rights and therefore could impact data integrity. | IT IFR R8 | IT IFR-C14 | High | Strong | Moderate | Moderate
IT IFR R14 | IT IFR-C22 | Low | Strong | Low | Low | Users access may be not be tied to a single sign on solution, which increases the risk to the Bank via multiple paths of access to the Banks Systems | IT IFR R9 | IT IFR-C15 | High | Weak | High | High
IT IFR R15 | IT IFR-C23 | High | Strong | Low | Low | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Systems as controls may not be in place to authenticate remote access users. | IT IFR R10 | IT IFR-C16 | High | Strong | Moderate | Moderate
[6 empty] | Access may not be appropriately restricted to the firewall which could lead to unauthorized changes. | IT IFR R11 | IT IFR-C17 | High | Adequate | Moderate | Moderate
[8 empty] | IT IFR-C18 |  | Adequate | Moderate
[8 empty] | IT IFR-C19 |  | Adequate | Moderate
[6 empty] | Performance metric's may not be reported to the CTO to ensure that the systems health is communicated. Without the communication, the systems performance could degragate. | IT IFR R12 | IT IFR-C20 | Moderate | Adequate | Low | Low | Now in IT-OPS
[6 empty] | IT resources could be compromised and business operations could be disrupted due to a virus without effective updates to servers and workstations. | IT IFR R13 | IT IFR-C21 | High | Strong | Moderate | Moderate
[6 empty] | Without an effective patch management identification process IT resources could be compromised and business operations could be disrupted. | IT IFR R14 | IT IFR-C22 | High | Strong | Moderate | Moderate
[6 empty] | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Email System. Further, malware could be introduced which could lead to a disruption in processing | IT IFR R15 | IT IFR-C23 | High | Strong | Moderate | Moderate
Risk Rating | Control Rating | Count Inherent Risk | Count Control Rating | Count Residual Risk |  |  | Risk Rating | Control Rating | Count Inherent Risk | Count Control Rating | Count Residual Risk
Very High | Strong | 3 | 7 | 2 |  |  | Very High | Strong | 3 | 12 | 3
High | Adequate | 3 | 7 | 1 |  |  | High | Adequate | 8 | 5 | 1
Moderate | Weak | 2 | 2 | 1 |  |  | Moderate | Weak | 4 | 6 | 7
Low |  | 3 |  | 7 |  |  | Low |  | 0 |  | 4
|  | 11 | 16 | 11 |  |  |  |  | 15 | 23 | 15
| Aggregate | Low | Adequate | Low |  |  |  | Aggregate | High | Strong | Moderate
|  | 33 | 31 | 33 |  |  |  |  | 31 | 30 | 32
| Final Assessment | High | Adequate | Moderate |  |  |  | Final Assessment | High | Strong | Moderate

## Result2020-21
|  |  |  | RCSA 2020 | [5 empty] | RCSA 2021
Process | Control Short Name | Control ID | Inherent Risk ID | Inherent Risk Rating | Residual Risk Rating | Design Effectiveness | Operating Effectiveness | Control Rating |  | Inherent Risk Rating | Residual Risk Rating | Design Effectiveness | Operating Effectiveness | Control Rating | Test Results | Residual Rating Verification |  |  |  | LOOKUP Table
[9 empty] | Tested? | [6 empty] | Inherent Risk Rating | Combination <Control-Inherent Risk> | Residual Rating (Calculated) | Matching? | Combination <Control-Inherent Risk> | Residual risk
IT IFR P1 Users Access Change and Term | Logical Access | IT IFR-C1 | IT IFR R1 | Very High | Very High | Weak | Weak | Weak | Yes | Very High | High | Adequate | Adequate | Adequate | Pass | Very High | Adequate-Very High | High | TRUE | Weak-Low | Low
| SNOW | IT IFR-C2 | IT IFR R1 | Very High | Very High | Adequate | Adequate | Adequate | Yes | Very High | High | Adequate | Adequate | Adequate | Pass | Very High | Adequate-Very High | High | TRUE | Weak-Moderate | Moderate
| RBA | IT IFR-C3 | IT IFR R1 | Very High | Very High | Weak | Weak | Weak | Yes | Very High | High | Adequate | Adequate | Adequate | Pass | Very High | Adequate-Very High | High | TRUE | Weak-High | High
IT IFR P5 Network Access Control | NAC | IT IFR-C10 | IT IFR R5 | Very High | Very High | Weak | Weak | Weak | No | Very High | Very High | Weak | Weak | Weak | Fail | Very High | Weak-Very High | Very High | TRUE | Weak-Very High | Very High
IT IFR P6 Network Segmentation | Network Segmentation | IT IFR-C11 | IT IFR R6 | Very High | Very High | Weak | Weak | Weak | No | Very High | Very High | Weak | Weak | Weak | Fail | Very High | Weak-Very High | Very High | TRUE | Adequate-Low | Low
IT IFR P7 Vendor Supported Systems | Vendor Management | IT IFR-C12 | IT IFR R7 | Moderate | Low | Adequate | Adequate | Adequate | No | Moderate | Low | Adequate | Adequate | Adequate | Pass | Moderate | Adequate-Moderate | Low | TRUE | Adequate-Moderate | Low
| Third Party Access | IT IFR-C13 | IT IFR R7 | Moderate | Low | Strong | Strong | Strong | Yes | Moderate | Low | Strong | Strong | Strong | Pass | Moderate | Strong-Moderate | Low | TRUE | Adequate-High | Moderate
IT IFR P8 Network Admistration | Privileged Access | IT IFR-C14 | IT IFR R8 | High | Moderate | Strong | Strong | Strong | Yes | Low | Low | Strong | Strong | Strong | Pass | Low | Strong-Low | Low | TRUE | Adequate-Very High | High
IT IFR P9 Single Signon | Single Sign On | IT IFR-C15 | IT IFR R9 | High | High | Weak | Weak | Weak | Yes | High | Low | Strong | Strong | Strong | Pass | High | Strong-High | Low | TRUE | Strong-Low | Low
IT IFR P10 Remote Access | Remote Access | IT IFR-C16 | IT IFR R10 | High | Moderate | Strong | Strong | Strong | Yes | Low | Low | Strong | Strong | Strong | Pass | Low | Strong-Low | Low | TRUE | Strong-Moderate | Low
IT IFR P11 Firewall Management | Firewall Change Management | IT IFR-C17 | IT IFR R11 | High | Moderate | Adequate | Adequate | Adequate | Yes | High | Moderate | Adequate | Adequate | Adequate | Pass | High | Adequate-High | Moderate | TRUE | Strong-High | Low
| Firewall Change Monitoring | IT IFR-C18 | IT IFR R11 | High | Moderate | Adequate | Adequate | Adequate | No | Low | Low | Adequate | Adequate | Adequate | Pass | Low | Adequate-Low | Low | TRUE | Strong-Very High | Moderate
| Firewall Auditing | IT IFR-C19 | IT IFR R11 | High | Moderate | Adequate | Adequate | Adequate | Yes | High | Moderate | Adequate | Adequate | Adequate | Pass | High | Adequate-High | Moderate | TRUE
IT IFR P13 Virus Protection | Virus Protection | IT IFR-C21 | IT IFR R13 | High | Moderate | Strong | Strong | Strong | Yes | Moderate | Low | Strong | Strong | Strong | Pass | Moderate | Strong-Moderate | Low | TRUE
IT IFR P14 Patch Management | Patch Management | IT IFR-C22 | IT IFR R14 | High | Moderate | Strong | Strong | Strong | Yes | Low | Low | Strong | Strong | Strong | Pass | Low | Strong-Low | Low | TRUE
IT IFR P15 Email | Email security | IT IFR-C23 | IT IFR R15 | High | Moderate | Strong | Strong | Strong | Yes | High | Low | Strong | Strong | Strong | Pass | High | Strong-High | Low | TRUE
IT IFR P2 Application Baseline | Business Reports Distribution | IFR-C4 |  | Moderate | Low | Strong | Strong | Strong | Yes |  |  | Moved to Operations
| Business Reports UAT | NK IFR-C5 |  | Moderate | Low | Strong | Strong | Strong | No |  |  | Moved to Operations
IT IFR P3 Uptime Performance | Performance Monitoring | IFR-C6 |  | Moderate | Low | Strong | Strong | Strong | Yes |  |  | Moved to Operations
IT IFR P4 In house Managed Systems | Automated Job | IFR-C7 |  | High | Moderate | Adequate | Adequate | Adequate | Yes |  |  | Moved to Operations
| Night Process Ops | NK IFR-C8 |  | High | Moderate | Adequate | Adequate | Adequate | No |  |  | Moved to Operations
| Night Process Report | NK IFR-C9 |  | High | Moderate | Adequate | Adequate | Adequate | No |  |  | Moved to Operations
IT IFR P12 Performance Metric Reporting | Health Metrics Report | IFR-C20 |  | Moderate | Low | Adequate | Adequate | Adequate | Yes |  |  | Moved to Operations
Risk Rating |  | Control Rating |  | RCSA 2020 | [5 empty] | RCSA 2021
(Numeric) | (Qualitative) | (Numeric) | (Qualitative) | Count Inherent Risk Rating |  |  |  | Count Control Rating |  | Count Inherent Risk Rating | Count Residual Risk |  |  | Count Control Rating
4 | Very High | 3 | Strong | 5 |  |  |  | 6 |  | 5 | 2 |  |  | 7
3 | High | 2 | Adequate | 9 |  |  |  | 5 |  | 4 | 3 |  |  | 7
2 | Moderate | 1 | Weak | 2 |  |  |  | 5 |  | 3 | 2 |  |  | 2
1 | Low |  |  | 0 |  |  |  | 16 |  | 4 | 9 |  |  | 16
|  |  |  | 16 | [5 empty] | 16 | 16
|  |  |  | RCSA 2020 | [5 empty] | RCSA 2021
|  | Aggregate Inherent Risk rating |  | 3.1875 | High |  |  |  |  | 2.625 | High
|  | Aggregate Control rating |  | 2.0625 | Adequate |  |  |  |  | 2.3125 | Adequate
|  | Resulting Residual Risk rating |  | Moderate | [5 empty] | Moderate
[7 empty] | Validated Residual Risk rating |  |  |  | 1.875 | Moderate

## IT-Infrastructure (w Notes) (hidden)
RCSA # | Process Domain | Initial Questions | Key Process | Key Steps in Process | Process ID | Key Risks | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control Description | Control ID | Key or Non Key | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved | Notes
RCSA ID Number | Name of the key process that is being performed. |  |  | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bank wide risk taxonomy | What is the impact of this risk? Select from: Very High , High, Medium, Low | What is the probability of the risk occurring? Select from: Possible/Adverse Stress, Probable/Baseline Conditions | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low |  | Control ID Number | Is this a Key Control? Select From: Key, Non Key | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often is this Control invoked? Select From: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing or decreasing? Select from: Increasing Decreasing Stable | What are the results of this RCSA? | What is the issue or gap for this key process? | Issue Number | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Which application is performing the key control
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) | Logical User Access 1.The new, change and Termination access process is decentralized. Certain applications/systems go through a central repository for access requests and changes, however not all. In addition, do to the vast number of applications, the logical access may not be role based. 2. Miser, WirePro, BAM and FCM - New, Change and Termination Access changes follow the same process. Request for Access change is initiated by a Business Unit Leader, which is documented in the same system. There are separate forms, however each provides for a historical record of the event. 3. Role Based permissions are designed and user access is granted based on the individual's responsibility. Should additional access be required outside the defined roles, a request needs to be submitted, reviewed and approved accordingly. This additionally granted access will be reviewed annually, following the Bank's standard user access review process. | IT IFR P1 | Individuals may have excessive or unauthorized access to operating system, database, network or application. This permits individuals or malicious parties with access to the individuals' account to perform functions and execute transactions that may be inconsistent with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | User access is authorized and an IAM (Identity Access Management) process is established for all networked and applications. This includes maintaining the proper segregation of duties between approved and implementer of any user change. (Control wording updated in 2021) | IT IFR-C1 | Key | Preventative | Manual | Weak | Adequate | Weak | Transactional | Quarterly | 25 15- New /Changed Access 10-Terminated Users | Very High | Decreasing | Pass | (2020 Issue) A centralized approach for capturing and recording all access change requests has not been established. (2021 Update) Issue-0000001389 is closed | IT IFR-F1 | (2020) Having a centralized approach for access management would provide for a uniform approach over all applications (2021 Update) Issue-0000001389 is closed | (2020) The Bank will prepare a business case and a formal proposal to centralize access management and role-based access for all applicable applications in one area that will be reviewed by senior management for the next steps. (2021 Update) Issue-0000001389 is closed | Debi Gupta | Business case and proposal to be presented by 6/30/2021 |  | Access recertification will be performed annually to ensure that all logical accesses are appropriately authorized. Pass Sep 22
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) |  | IT IFR P1 | Individuals may have excessive or unauthorized access to operating system, database, network or application. This permits individuals or malicious parties with access to the individuals' account to perform functions and execute transactions that may be inconsistent with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | A record of all users access is maintained in the ticketing system which contains an audit trail for all change in access requirements (Add, Changes, Terminations of Users). | IT IFR-C2 | Key | Preventative | Manual | Weak | Adequate | Weak | Annually | Annually | 25 15- New /Changed Access 10-Terminated Users | Very High | Decreasing | Pass | (2020 Issue) The Help Desk ticket system is not consistently used for New, modified and Terminated changes. There was no evidence that the “onboarding” requests from business/HR were reconciled against the actual provisioning before closing the ticket. (2021 Update) Issue-0000001389 is closed | IT IFR-F2 | (2020) A formal request for access ticketing system should be used for all access requests, changes and terminations to provide for a permeant record of all access change events (2021 Update) Issue-0000001389 is closed | (2020) The Bank will deploy ServiceNow for centralizing a ticketing system for all access changes. This include employee on-boarding and off-boarding and other access changes recorded through ServiceNow. This include integration with the Bank's HRIS System ( ADP ) (2021) Provisioning/deprovisioning of access to infrastructure is consistently documented in SNOW. However, the provisioning of CORE applications is still documented separately but NOT yet in SNOW. (2021 Update) Issue-0000001389 is closed. There will be no change related to the process of provisioning CORE, because this system will be soon replaced. | Debi Gupta | 2021-06-30 | ServiceNow | In the interim, the Bank will continue to use AppleNet ( and its successor ServiceNow) to manually record all access changes. Pass Sep 22
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) |  | IT IFR P1 | Individuals may have excessive or unauthorized access to operating system, database, network or application. This permits individuals or malicious parties with access to the individuals' account to perform functions and execute transactions that may be inconsistent with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | Role Base permission is in place for critical applications to ensure that a user as access in accordance with their job functions. (Control wording updated in 2021) | IT IFR-C3 | Key | Preventative | Automated | Weak | Adequate | Weak | Annually | Annually | 5 | Very High | Stable | Pass | (2020 Issue) Access may not be a role based approach which depends on the application. This issue is reflective of a decentralized strategy for Application Access Management. (2021 Update) Issue-0000001390 is closed | IT IFR-F3 | (2020) The use of Role Based Security for all applications should be implemented to provide for consistently in access requirements based on the user job function. Further, role based access decreases the risk of inappropriate access and improves overall access security. (2021 Update) Issue-0000001390 is closed | (2020) The Bank will prepare a business case and a formal proposal to centralize access management and role-based access for all applicable applications in one area that will be reviewed by senior management for the next steps. (2021 Update) Issue-0000001390 is closed | Debi Gupta | Business case and proposal to be presented by 6/30/2021 |  | Access recertification will be performed annually to ensure that all logical accesses are appropriately authorized. Pass Sep 22
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Network Access Control | Network Access Control Access to the network will comply to the network security policy. This includes the pre-admission and post-admission security policy that determines where users and devices can go in the network and what they can do once admitted into the network. | IT IFR P5 | Devices could be attached to the Banks Network and go undiscovered. This could result in loss of control over the Network and further infiltrate systems and applications. | IT IFR R5 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | The Bank has implemented Network Access Control (NAC) which would provide the Bank the ability to implement stronger security measures. (Control wording updated in 2021) | IT IFR-C10 | Key | Preventative | Automated | Weak | Weak | Weak | Transactional | Annually | Segmented Network | Very High | Decreasing | Fail | (2020 Issue) The Bank has not completed the Network Access Control (NAC) project. Consequently, the rating of this control remained unchanged from that of 2020. | IT IFR-F4 | (2020) The Bank should develop a strategic approach which may include service providers and tools. The Network should then separated and to into zones to secure each and limit and manage lateral movement. | (2020) The Bank is implementing the NAC project, due to conclude end of June 2021 | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Network Architecture | Network Segmentation Network architecture is designed according to the security principles: domain separation and layering. Domain separation separates network traffic into network segments to mitigate the risk of adversary learning about network design. Network layering segregates the functions (e.g. OSI seven layers) to provide better security assurance. | IT IFR P6 | Proper Network Segmentation would reduce the Network Attack impacts. Without an effective approach, management may not be able to minimize the impact in the event of a malicious attack. | IT IFR R6 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | The Bank has implemented Network Segmentation which would provide the Bank the ability to implement stronger security measures. (Control wording updated in 2021) | IT IFR-C11 | Key | Preventative | Automated | Weak | Weak | Weak | Transactional | Annually | Segmented Network | Very High | Increasing | Fail | (2020 Issue) The Bank has not completed the Network Segmentation project. Consequently, the rating of this control remained unchanged from that of 2020. | IT IFR-F5 | (2020) The Bank should develop a strategic approach which may include service providers and tools. The Network should then separated and to into zones to secure each and limit and manage lateral movement. | (2020) The Bank is implementing the network segmentation project, due to conclude end of June 2021 | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Vendor Security | IT Vendor Management 1. The Bank maintains an inventory of all IT Service Providers for monitoring contract maturity dates which includes key contacts. The inventory is updated as changes in relationships occur and is reviewed annually. This will be covered in a separate Vendor Management Risk Assessment | IT IFR P7 | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | Access is only granted to employees of a Service Provider that is listed in ABS Vendor Management's "vendor list". (Control wording updated in 2021) | IT IFR-C12 | Key | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 1 | Low | Stable | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Vendor Security | Third Party Network Access 2. Service Providers do not have access to any of the systems. This control prevents Third Party relationships for modifying data, software and parameters. | IT IFR P7 | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | Service providers are not permitted access to the Bank. When vendors are provided access, it is monitored and revoked up on completion. Contractors are provided access and access is disabled at 90 days, where approvals are required for the contractor to continue to have access. (Control wording updated in 2021) | IT IFR-C13 | Key | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 8 accounts granted to non-permanent employees + all access to CORE applications | Low | Stable | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) | Network Privilege Access 1. Network Administrators access is restricted and reviewed to ensure that access is consistent with each users functional role. 2. An Active directory group - "network admin" - is created and this grants access to network devices. Additional authorization is provide via OKTA for Multi Factor Authentication. | IT IFR P8 | Access to the privilege accounts of the Bank's infrastructure, if unauthorized or inadequately managed, may expose the Bank to privilege misuse and attacks from both internal and external malicious actors | IT IFR R8 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Moderate | Possible/Adverse Stress | Low | Access to privileged Network accounts is limited to appropriate individuals | IT IFR-C14 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 100% Domain Admins | Low | Stable | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Identity and Access Management (Infrastructure) | Single Sign-On 1. Bank has implemented OKTA as a single sign on. OKTA ties into active directory for user sign-on information. 2. When a new application is purchase a review is done to determine if the application can be integrated into OKTA pool for single sign-on. 3. The application pool contains all applications that utilize single sign -on | IT IFR P9 | Users access may not be tied to a single sign on solution, which increases the risk to the Bank via multiple paths of access to the Banks Systems. | IT IFR R9 | 8.4.5 - Operational Risk - Systems - Identity Access Management | High | Probable/Baseline Conditions | High | The Bank implements Single-Sign On, which would provide the ability to implement stronger security measures. (Control wording updated in 2021) | IT IFR-C15 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | Single Sign on | Low | Stable | Pass | None | None | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Network Security | Remote Access 1. Remote access is provided to limited Users of which these are provided access via VPN which are defined in Active Directory via LDAP which are authenticated via Okta Multifactor Authentication. | IT IFR P10 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Systems as controls may not be in place to authenticate remote access users. | IT IFR R10 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Moderate | Possible/Adverse Stress | Low | Remote access communications to the Bank’s Corporate Systems are authenticated, encrypted and monitored. Remote access to ABS information assets using bank-issued devices is secured by Virtual Private Network (VPN). Authentication of remote access using bank-issued devices is secured by MFA (multi-factor authentication) in OKTA, which is integrated with ABS Active Directory. Idle access session requires user to re-authenticate Remote access to ABS information assets using non bank-issued devices is secured by Virtual Desktop Infrastructure (VDI). Remote Desktop Protocol (“RDP”) to connect to their Computing Devices is restricted (Control wording updated in 2021) | IT IFR-C16 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | Okta Configuration VPN Configuration | Low | Stable | Pass | N/A | N/A | None | None | None | None | None
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Change Control and Configuration Management | Firewall Management Firewall changes 1. Requests for changes are made to the networking infrastructure group for a firewall change. 2. Networking performs a due diligence which includes inspecting the current rules to determine if there is a rule that is already current and can address the request. 3. The group ensures that the request is complete – source and destination IP, Port Opening etc. 4. Network infrastructure completes a firewall request form and submits to Info security for their approval. Form is emailed to Info sec general mail box – At the same time a service now ticket is generated at the same time. 5. The change is presented and approved by the CAB - Documentation is discussed reviewed and attached to the service now change ticket. 6. Once the request is approved at the CAB meeting the change is tested within a window. 7. Testing is provided at end of implementation window. 8. Validation is performed by info security of all fire wall changes. | IT IFR P11 | Access may not be appropriately restricted to the firewall which could lead to unauthorized changes. Palo Alto / CISO FTD - FirePower Threat Defense Only the Networking group is authorized to make changes to the firewall configuration. Info Security has only read access to the firewall configuration/rule sets. | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | Access to firewalls is restricted to designated IT professionals. All changes to the firewalls must follow the Bank's Change Management Policy (Control wording updated in 2021) | IT IFR-C17 | Key | Preventative | Manual | Adequate | Adequate | Adequate | Transactional | Annually | 1. Firewall Permissions 2. Sample Changes | Moderate | Stable | Pass | None | None | None | None | None | None | Palo Alto / CISO FTD - FirePower Threat Defense
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending |  |  | IT IFR P11 |  | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Moderate | Possible/Adverse Stress | Low | The Solar Winds Tool is used to provide performance monitoring and capture changes | IT IFR-C18 | Non Key | Preventative | Automated | Adequate | Weak | Weak | Annually | Annually | 0 Not a Key Control | Low | Stable | Pass | None | None | None | None | None | None | Palo Alto / CISO FTD - FirePower Threat Defense
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending |  |  | IT IFR P11 |  | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | A reconcilliation is performed between the changes in Firewall rules and the Solar Wind Log. (Control wording updated in 2021) | IT IFR-C19 | Key | Detective | Automated | Adequate | Weak | Weak | Transactional | Annually | 2. Sample Changes 1 SolarWinds Report Reconciliation | High | Stable | Pass | (2021 Issue) There was no re-conciliation of the Solar winds or similar report to the firewall rule changes as of the date of the review. However a new process in being implemented for the 3rd quarter using Firemon. (2021 Update) Issue-0000003394 is closed | None | (2021) Continue to develop a revised reconciliation process between the firewall rule step and monitoring software - i.e. Firemon. (2021 Update) Issue-0000003394 is closed | (2021 Update) Issue-0000003394 is closed | Max Tumarinson | None | Palo Alto / CISO FTD - FirePower Threat Defense | Pass Sep 22
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Threat and Vulnerability Management (Infrastructure) | Virus and Malicious Software Protection 1. For non Core Application Symantec monitoring is being completed. This is primarily used to ensure that Virus definitions and Advanced Protection are up to date on workstations and servers. | IT IFR P13 | IT resources could be compromised and business operations could be disrupted due to a virus without effective updates to servers and workstations | IT IFR R13 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | High | Possible/Adverse Stress | Moderate | All network devices have an endpoint protection solution installed. Daily automatic local scans for potential threats are scheduled. Anti-malware software and definition files are set to automatically receive the latest updates. The ability to disable or remove anti-malware programs is restricted. (Control wording updated in 2021) | IT IFR-C21 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 1 Symantec Report | Low | Stable | Pass | None | None | None | None | None | None | Symantec
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Threat and Vulnerability Management (Infrastructure) | Patch Management 1. The KACE tool is used to identify the Patch requirements for the Bank's Technology. 2. Patches are tested in development environment and confirmation is received from the end users before being moved to production. This done on Patch Tuesday of where the released patches are reviewed and scheduled. 3. A Daily report that is run to determined status of patches – the results are then match to KACE to schedule implementation of patches based on the schedule – Wednesdays and Friday. Workstations are schedule during the week. | IT IFR P14 | Without an effective patch management identification process IT resources could be compromised and business operations could be disrupted. | IT IFR R14 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Moderate | Possible/Adverse Stress | Low | Required security patches are regularly identified and assessed by regularly reviewing and assessing threats and vulnerabilities Security patches are tested before being installed to the production environment . A remediation/validation scan is performed to ensure that the vulnerabilities are eliminated due to the installation of the patch (Control wording updated in 2021) | IT IFR-C22 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 1 KACE Report | Low | Stable | Pass | None | None | None | None | None | None | KACE
IT IFR 1 | IT Infrastructure | Progress since last RCSA and resulting risk trending | Information Transfer | Email 1. Email is controlled and managed by the BNK through a relationship with Google of which the G-Suite tools are used. All new users that require access go through the access control process as noted above. 2. The email System has controls in place to restrict unauthorized individuals from communicating with individuals and entities outside of the Bank. In addition, the email system shall scan for, then prevent all unauthorized outgoing messages containing Not Public Information (NPI). | IT IFR P15 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Email System. Further, malware could be introduced which could lead to a disruption in processing | IT IFR R15 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | E-mails and e-mail systems are protected from unauthorized access, modification or denial of service, spam and phishing emails, malicious e-mails, attachments and the leaking of non-public information. E-mails with non-public information must be authorized. Its information is masked or encrypted. (Control wording updated in 2021) | IT IFR-C23 | Key | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 1 GMAIL Configuration 1 NETSKOPE Configuration 1 VIRTRU Configuration | Low | Stable | Pass | None | None | None | None | None | None | GMAIL, NETSPOKE, VIRTRU
Possible/ Adverse
Probable/Baseline
Frequency
Remote / Severe Stress
[8 empty] | Frequency | Event occurs in exceptional situations
[8 empty] | Definition: | (e.g. tail risk, beyond 10 years)
[8 empty] | Impact | VH
H
M
L
Residual Risk Rating
[22 empty] | Very High | 4
[22 empty] | High | 3
[22 empty] | Moderate | 2
[22 empty] | Low | 1
[24 empty] | Adequate | Weak
[22 empty] | Design Effectiveness | Strong | Adequate | Weak
[23 empty] | Adequate | Adequate | Weak
[23 empty] | Weak | Weak | Weak

## IF2020
RCSA # | Key Process | Key Steps in the Process | Process ID | Key Risks | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control | Key or Non Key | Control ID | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved | Notes
RCSA ID Number | Name of the key process that is being performed. | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bankwide risk taxonomy | What is the impact of this risk? Select from: Very High , High, Medium, Low | What is the probability of the risk occurring? Select from: Possible/Adverse Stress, Probable/Baseline Conditions | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low | Describe the control in detail. A key control that is significant and deemed critical to a given process, and must be performed effectively to reduce the inherent risk that it is associated with, to an acceptable level. | Is this a Key Control? Select From: Key, Non Key | Control ID Number | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often is this Control invoked? Select From: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing or decreasing? Select from: Increasing Decreasing Stable | What are the results of this RCSA? | What is the issue or gap for this key process? | Issue Number | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Which application is performing the key control
IT IFR 1 | IT Infrastructure | Access Request/Change/Terminations (logical access) 1.The new, change and Termination access process is decentralized. Certain applications/systems go through a central repository for access requests and changes, however not all. In addition, do to the vast number of applications, the logical access may not be role based. 2. Miser, WirePro, BAM and FCM - New, Change and Termination Access changes follow the same process. Request for Access change is initiated by a Business Unit Leader, which is documented in the same system. There are separate forms, however each provides for a historical record of the event. 3. Role Based permissions are designed and user access is granted based on the individuals responsibility. Should additional access be required outside the defined roles | IT IFR P1 | Individual may have excessive or unauthorized operating system, database, network or application access. This permits individuals to perform transaction and function that may be inconsistently with the individuals job function. | IT IFR R1 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Probable/Baseline Conditions | Very High | User access is authorized and appropriately established for all in-scope applications. Controls relating to appropriate segregation of duties over requesting and granting access to systems and data exist and are followed. | Key | IT IFR-C1 | Preventative | Manual | Weak | Weak | Weak | Daily | Daily | 0 | Very High | Increasing | Fail | A centralized approach for capturing and recording all access change requests has not been established. | IT IFR-F1 | Having a centralized approach for access management would provide for a uniform approach over all applications. | The Bank will prepare a business case and a formal proposal to centralize access management and role-based access for all applicable applications in one area that will be reviewed by senior management for the next steps. | Debi Gupta | Business case and proposal to be presented by 6/30/2021 |  | Access recertification will be performed annually to enusre that all logical accesses are appropiately authorized.
[7 empty] | Very High | Probable/Baseline Conditions | Very High | A record of all users access is maintained in the ticketing system which contains an audit trail for all change in access requirements. | Key | IT IFR-C2 | Preventative | Manual | Weak | Weak | Weak | Annually | Annually | 25 15- New /Changed Access 10-Terminated Users | Very High | Increasing | Fail | The Help Desk ticket system is not consistently used for New, modified and Terminated changes. | IT IFR-F2 | A formal request for access ticketing system should be used for all access requests, changes and terminations to provide for a permeant record of all access change events. | The Bank will deploy ServiceNow for centralizing a ticketing system for all access changes. This include employee on-boarding and off-boarding and other access changes recorded through ServiceNow. This include integration with the Bank's HRIS System ( ADP ). | Debi Gupta | 2021-06-30 | ServiceNow | In the interim, the Bank will comtinue to use AppleNet ( and its successor ServiceNow) to manually record all access changes.
[7 empty] | Very High | Probable/Baseline Conditions | Very High | Role Base permission is in place for limited applications to ensure a consistent approach for access is used. Role Based permissions over all applications has not been established. This is a control design deficiency. | Key | IT IFR-C3 | Preventative | Automated | Weak | Weak | Weak | Annually | Annually | 4 | Very High | Increasing | Fail | Access may not be a role based approach which depends on the application. This issue is reflective of a decentralized strategy for Application Access Management. | IT IFR-F3 | The use of Role Based Security for all applications should be implemented to provide for consistently in access requirements based on the user job function. Further, role based access decreases the risk of inappropriate access and improves overall access security. | The Bank will prepare a business case and a formal proposal to centralize access management and role-based access for all applicable applications in one area that will be reviewed by senior management for the next steps. | Debi Gupta | Business case and proposal to be presented by 6/30/2021 |  | Access recertification will be performed annually to enusre that all logical accesses are appropriately authorized.
IT IFR 1 | IT Infrastructure | Application Baseline 1. Standard Production Reports are generated and provided to the Business Units daily. This is part of the output from the Nightly Job Schedule. 2. Reports are used by the Bank for Daily Business activities. The report contents were validated as part of the Testing when implementing the applications. | IT IFR P2 | Reports may not be produced or may contain inaccurate information to meet the needs of the Business. As decisions are determined on the output misinformation could result in ineffective outcomes. | IT IFR R2 | 8.4.6 - Operational Risk - Systems - Data Integrity and Quality | High | Possible/Adverse Stress | Moderate | Reports are generated directly from the Applications and are distributed to the Business Units with out alterations. | Key | IT IFR-C4 | Preventative | Automated | Strong | Strong | Strong | Annually | Annually | 5 days | Low | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | High | Possible/Adverse Stress | Moderate | For each new release, upon User Acceptance testing the Reports contents are validated to ensure that the output is accurate. | Non Key | IT IFR-C5 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 0 Not a Key Control | Low | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Uptime/Performance 1. Daily System Performance Metrics are produced via a report that includes: - Response time - Uptime Management - Tools and Reporting These reports are reviewed and changes to load balancing, disc space etc. are completed when necessary. | IT IFR P3 | Performance not monitored could lead to a degradation in performance of the use of technology. | IT IFR R3 | 8.4.6 - Operational Risk - Systems - Data Integrity and Quality | High | Possible/Adverse Stress | Moderate | Daily system performance is captured and monitored to ensure that the systems have the necessary technology resources for peak performance. | Key | IT IFR-C6 | Detective | Automated | Adequate | Strong | Strong | Annually | Annually | 1 - Miser 1 - Network | Low | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | In house Managed Systems 1. Automated Job schedules for the Miser application is in place to ensure, that the daily interfaces and backup process complete without human interaction. 2. In the event of a Job Failure or disruption, an alert is sent to the Night Operator for actions to be taken to correct the incident. 3. Daily reports are generated nightly and provided to the Agency electronically as a result of the job schedule. | IT IFR P4 | Night processing of Interface updates, backups and Report Generation may not be completed fully, which could result in data completeness and accuracy. | IT IFR R4 | 8.4.6 - Operational Risk - Systems - Data Integrity and Quality | Very High | Possible/Adverse Stress | High | An Automated Job Schedule Tool is used which enforces the system to complete the Night processing without the requirements of the Operator | Key | IT IFR-C7 | Preventative | Automated | Adequate | Strong | Strong | Annually | Annually | 1. Banktel 2. Q2 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | An Operator is available to support the Night Process and make any corrections in processing if necessary. An Automated control is in place to notify the Night Operator in the event of a job schedule disruptions. | Non Key | IT IFR-C8 | Detective | Manual | Adequate | Strong | Strong | Annually | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | Reports are generated, reviewed and approved for the completion of Night Processing | Non Key | IT IFR-C9 | Detective | Manual | Adequate | Strong | Strong | Annually | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | New Devices Added/Captured (NAC) 1. A NAC is not in place and this is a Self Identified Issue | IT IFR P5 | Devices could be attached to the Banks Network and go undiscovered. This could result in loss of control over the Network and further infiltrate systems and applications. | IT IFR R5 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | A Network Access Control (NAC) has not been implemented. This is a self identified control GAP | Key | IT IFR-C10 | Detective | Automated | Weak | Weak | Weak | Transactional | Annually | NAC | Very High | Increasing | Fail | The Bank has not implemented a Network Access Control to automatically detect and report devices that are attached the Bank's Network. | IT IFR-F4 | The Bank should implement a NAC to have real-time visibility of devices, users and applications that are accessing network. Such devices would provide the Bank the ability to immediately respond to unknown network events. | The Bank will implement a Network Access Control device ( NAC ) | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Network Segmentation 1. The Network has not been segmented and therefore is not in place and this is a Self Identified Issue | IT IFR P6 | Proper Network Segmentation would reduce the Network Attack impacts. Without an effective approach management may not be able to minimize the impact in the event of a malicious attack. | IT IFR R6 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Probable/Baseline Conditions | Very High | The Bank has not implemented Network Segmentation which would provide the Bank the ability to implement stronger security measures. | Key | IT IFR-C11 | Preventative | Automated | Weak | Weak | Weak | Transactional | Annually | Segmented Network | Very High | Increasing | Fail | The Bank has not implemented Network Segmentation to improve the security posture of the Bank. Network Segmentation will limit the range of access provided to individuals that gain Network Access. | IT IFR-F5 | The Bank should develop a strategic approach which may include service providers and tools. The Network should then separated and to into zones to secure each and limit and manage lateral movement. | The Bank is implementing a DMZ and at the same time, executing a plan for network segmentation that is currently under way. | Debi Gupta | 2020-12-31
IT IFR 1 | IT Infrastructure | Vendor Supported Systems 1. The Bank maintains an inventory of all IT Service Providers for monitoring contract maturity dates which includes key contacts. The inventory is updated as changes in relationships occur and is reviewed annually. This will be covered in a separate Vendor Management Risk Assessment 2. Service Providers do not have access to any of the systems. This control prevents Third Party relationships for modifying data, software and parameters. | IT IFR P7 | The company may not have a complete list of their Service Providers which could allow services to continue without review and permit ongoing vendor access to their systems. | IT IFR R7 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | The Bank has a separate Vendor Management program outside of IT. | Non Key | IT IFR-C12 | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 0 Not a Key Control | Low | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | High | Possible/Adverse Stress | Moderate | Service providers are not permitted access by the Bank. When vendors are provided access is monitored and revoked up on completion of the effort. Contractors are provided access and access is disabled at 90 days, where approvals are required for the contractor to continue to have access. | Key | IT IFR-C13 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 4 | Low | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Network Administrator Rights 1. Network Administrators access is restricted and reviewed to ensure that access is consistent with each users functional role. | IT IFR P8 | Unauthorized persons may have Administrator rights and therefore could impact data integrity. | IT IFR R8 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | Access to privileged Network accounts is limited to appropriate individuals. | Key | IT IFR-C14 | Preventative | Manual | Strong | Strong | Strong | Annually | Annually | 100% Domain Admins | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Single Sign on 1.The Bank has not implemented Single Sign. This is a self identified issue. | IT IFR P9 | Users access may be not be tied to a single sign on solution, which increases the risk to the Bank via multiple paths of access to the Banks Systems | IT IFR R9 | 8.4.5 - Operational Risk - Systems - Identity Access Management | High | Probable/Baseline Conditions | High | The Bank has not implemented Single Sign. This is due to the distributed approach of managing application access and that some of those systems do not adopt Active Directory Security Policy. | Key | IT IFR-C15 | Preventative | Manual | Weak | Weak | Weak | Annually | Annually | Single Sign on | High | Increasing | Fail | Single Sign on has not been implemented. While many applications adopt Active Directory Security, not all do. This is due to the decentralized approach for application management. Through discussions, as applications are upgraded/replaced these are required to adopt the AD Security Policy. | IT IFR-F6 | The Bank should continue to upgrade and replace the applications with those that can be bound to Active Directory. | The Bank will continue to implement single sign-on for all applications that support SSO with Active Directory. However, there are legacy applications ( like the core Miser ) and some outsourced applications that would not support SSO with Active Directory and can't be migrated or converted easily, without business impact. | Debi Gupta | 2021-06-30
IT IFR 1 | IT Infrastructure | Remote Access 1. Remote access is provided to limited Users of which these are provided access via VPN which are defined in Active Directory via LDAP which are authenticated via Okta Multifactor Authentication. | IT IFR P10 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Systems as controls may not be in place to authenticate remote access users. | IT IFR R10 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | Users access is controlled via the Virtual Private Network, of which all user who remote access in are authenticated via Okta multifactor authentication. | Key | IT IFR-C16 | Preventative | Automated | Strong | Strong | Strong | Transactional | Annually | 1 Okta Configuration 5 Remote Access Requests | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Firewall Management 1, Firewall changes are driven through requests or security related activities and are communicated on a manual form by the Network Group to the Information Security Group prior to change. Upon approval only authorized individuals can make changes to firewall. 2. The Information Security Group reviews the manual form and approves the change. This is communicated back to the Network Group via email. 3. The Solar Winds tool completes a nightly spool of which the report on firewall changes is sent to the Information Security group where each change on the report is reconciled back to the Ticket. | IT IFR P11 | Access may not be appropriately restricted to the firewall which could lead to unauthorized changes. | IT IFR R11 | 8.4.5 - Operational Risk - Systems - Identity Access Management | Very High | Possible/Adverse Stress | High | The firewall is configured to limit the number of users who can make changes. | Key | IT IFR-C17 | Preventative | Manual | Adequate | Strong | Adequate | Transactional | Annually | 1. Firewall Permissions 2. Sample Changes | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | The Solar Winds Tool is used to provide performance monitoring and capture changes | Non Key | IT IFR-C18 | Preventative | Manual | Adequate | Adequate | Adequate | Annually | Annually | 0 Not a Key Control | Moderate | Stable | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | All Firewall Changes are reviewed by the Info Sec Group and are reconciled back to the Solar Winds Report | Key | IT IFR-C19 | Detective | Automated | Adequate | Strong | Adequate | Transactional | Annually | 2. Sample Changes 1 SolarWinds Report Reconciliation | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Performance Metric Reporting 1. Performance Reports are assembled for presentation to the CTO. This reports are provided monthly to the CTO to ensure that management is made aware of the quality of processing | IT IFR P12 | Performance metric's may not be reported to the CTO to ensure that the systems health is communicated. Without the communication, the systems performance could degragate. | IT IFR R12 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | High | Possible/Adverse Stress | Moderate | Performance reports are provided to the CTO to communicate the health of the network, core and servers. | Key | IT IFR-C20 | Detective | Manual | Adequate | Strong | Adequate | Monthly | Monthly | 2 | Low | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Virus Protection 1. For non Core Application Symantec monitoring is being completed. This is primarily used to ensure that Virus definitions and Advanced Protection are up to date on workstations and servers. | IT IFR P13 | IT resources could be compromised and business operations could be disrupted due to a virus without effective updates to servers and workstations. | IT IFR R13 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | Symantec Security Monitoring Tool has been implemented and is used to capture virus protection security events for workstations and servers. | Key | IT IFR-C21 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | 1 Symantec Report | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Patch Management 1. The KACE tool is used to identify the Patch requirements for the Bank's Technology. 2. Once the patch is obtained each week the change/update is scheduled and applied to the appropriate server, workstation, printer and/or network component. | IT IFR P14 | Without an effective patch management identification process IT resources could be compromised and business operations could be disrupted. | IT IFR R14 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | Security threats and vulnerabilities are identified and assessed through the use of a tool. | Key | IT IFR-C22 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | 1 KACE Report | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT IFR 1 | IT Infrastructure | Email 1. Email is controlled and managed by the BNK through a relationship with Google of which the G-Suite tools are used. All new users that require access go through the access control process as noted above. 2. The email System has controls in place to restrict unauthorized individuals from communicating with the Agency. Further the email scans for each outgoing for Not Public Information (NPI). | IT IFR P15 | Access controls may not be in place to prevent unauthorized individuals from gaining entry into the Bank's Email System. Further, malware could be introduced which could lead to a disruption in processing | IT IFR R15 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | The Email Server is outsourced to G-Suite of which security controls are in place to monitor content that is leaving the Bank the contains NPI | Key | IT IFR-C23 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | 3 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Lists for Data Validation
Risk Taxonomy | Impact Rating | Probability Rating | Inherent Risk Rating | Type of Control (Preventive or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Testing Frequency | Residual Risk Rating | Direction of Risk | Key Non Key | Control Occurrence
1.0.0 - Credit Risk | Very High | Possible/Adverse Stress | Very High | Preventative | Automated | Strong | Strong | Strong | Daily | Very High | Increasing | Key | Daily
1.1.0 - Credit Risk - Counterparty | High | Probable/Baseline Conditions | High | Detective | Manual | Adequate | Adequate | Adequate | Weekly | High | Decreasing | Non Key | Weekly
1.2.0 - Credit Risk - Concentration | Moderate |  | Moderate |  |  | Weak | Weak | Weak | Monthly | Moderate | Stable |  | Monthly
1.3.0 - Credit Risk - Settlement | Low |  | Low | [5 empty] | Quarterly | Low |  |  | Quarterly
1.4.0 - Credit Risk - Collateral / Credit Mitigation | [8 empty] | Annually |  |  |  | Annually
2.0.0 - Liquidity Risk | [12 empty] | Transactional
2.1.0 - Liquidity Risk - Funding Liquidity
2.2.0 - Liquidity Risk - Non Traded Market
3.0.0 - Capital Risk
3.1.0 - Capital Risk - Capital Adequacy
4.0.0 - Market Risk
4.1.0 - Market Risk - Interest Rate
4.1.1 - Market Risk - Interest Rate - Delta
4.1.2 - Market Risk - Interest Rate - Gamma (Convexity)
4.1.3 - Market Risk - Interest Rate - Vega
4.1.4 - Market Risk - Interest Rate - Theta
4.1.5 - Market Risk - Interest Rate - Correlation
4.1.6 - Market Risk - Interest Rate - Event
4.1.7 - Market Risk - Interest Rate - Discount Rate
4.1.8 - Market Risk - Interest Rate - Prepayment
4.2.0 - Market Risk - FX/Currency
4.2.1 - Market Risk - FX/Currency - Delta
4.2.2 - Market Risk - FX/Currency - Gamma (Convexity)
4.2.3 - Market Risk - FX/Currency - Vega
4.2.4 - Market Risk - FX/Currency - Theta
4.2.5 - Market Risk - FX/Currency - Correlation
4.2.6 - Market Risk - FX/Currency - Event
4.3.0 - Market Risk - Equity
4.3.1 - Market Risk - Equity - Delta
4.3.2 - Market Risk - Equity - Gamma (Convexity)
4.3.3 - Market Risk - Equity - Vega
4.3.4 - Market Risk - Equity - Theta
4.3.5 - Market Risk - Equity - Correlation
4.3.6 - Market Risk - Equity - Event
4.3.7 - Market Risk - Equity - Dividend
4.3.8 - Market Risk - Equity - Borrow Cost
4.4.0 - Market Risk - Commodity
4.4.1 - Market Risk - Commodity - Delta
4.4.2 - Market Risk - Commodity - Gamma (Convexity)
4.4.3 - Market Risk - Commodity - Theta
4.4.4 - Market Risk - Commodity - Correlation
4.4.5 - Market Risk - Commodity - Event
5.0.0 - Model Risk
5.1.0 - Model Risk - Intrinsic Uncertainity
5.2.0 - Model Risk - Model Design
5.3.0 - Model Risk - Model Usage
6.0.0 - Business Risk
6.1.0 - Business Risk - Failure to Meet Earnings Target
6.2.0 - Business Risk - Failure to Adapt to Long-Term Strategic Trends
6.3.0 - Business Risk - New Business and Change Management
6.4.0 - Business Risk - Investment
7.0.0 - Reputational Risk
7.1.0 - Reputational Risk - Customer
7.2.0 - Reputational Risk - Product
8.0.0 - Operational Risk
8.1.0 - Operational Risk - Financial Crime
8.1.1 - Operational Risk - Financial Crime - Fraud, Theft or Misappropriation of Assets
8.1.2 - Operational Risk - Financial Crime - Data Theft or Misuse
8.1.3 - Operational Risk - Financial Crime - Data Protection & Customer Confidentiality
8.1.4 - Operational Risk - Financial Crime - False Representation & Suitability and Appropriateness
8.1.5 - Operational Risk - Financial Crime - AML, BSA and Sanctions Risk
8.1.6 - Operational Risk - Financial Crime - Compliance with Laws and Regulations
8.2.0 - Operational Risk - People and Conduct
8.2.1 - Operational Risk - People and Conduct - Employment Laws and HR Practices
8.2.2 - Operational Risk - People and Conduct - Discrimination, Harassment or Bullying
8.2.3 - Operational Risk - People and Conduct - Diversity, Code of Conduct and Ethical Behavior
8.2.4 - Operational Risk - People and Conduct - Compliance with Policies and Procedures
8.3.0 - Operational Risk - Processes
8.3.1 - Operational Risk - Processes - Branch and ATM Operations
8.3.2 - Operational Risk - Processes - Funds Deposit and Transfers/Transactions
8.3.3 - Operational Risk - Processes - Credit Origination
8.3.4 - Operational Risk - Processes - Account Setup and Opening
8.3.5 - Operational Risk - Processes - Customer Communications and Marketing Material
8.3.6 - Operational Risk - Processes - Account Maintenance and Servicing
8.3.7 - Operational Risk - Processes - Customer Protection
8.3.8 - Operational Risk - Processes - Record Keeping and Customer Reporting
8.3.9 - Operational Risk - Processes - Corporate/Business Practices
8.3.10 - Operational Risk - Processes - Regulatory Reporting
8.3.11 - Operational Risk - Processes - Internal Reporting and Monitoring
8.4.0 - Operational Risk - Systems
8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability
8.4.2 - Operational Risk - Systems - Application Maintenance and Change Control
8.4.3 - Operational Risk - Systems - Application Development and Testing
8.4.4 - Operational Risk - Systems - End User Computing
8.4.5 - Operational Risk - Systems - Identity Access Management
8.4.6 - Operational Risk - Systems - Data Integrity and Quality
8.4.7 - Operational Risk - Systems - Data Architecture and Governance
8.4.8 - Operational Risk - Systems - Cyber
8.4.9 - Operational Risk - Systems - DR / BCP
8.4.10 - Operational Risk - Systems - Natural Disasters, Terrorism, Vandalism and Physical Security
8.5.0 - Operational Risk - Third-Party (Suppliers, Vendors and Outsourcing)
8.5.1 - Operational Risk - Third-Party - Selection
8.5.2 - Operational Risk - Third-Party - Contracting
8.5.3 - Operational Risk - Third-Party - Due Dilligence
8.5.4 - Operational Risk - Third-Party - Inadequate Monitoring

## Testing Frequency (hidden)
Control Frequency | Assumed Population size | Minimum Sample Size
Annual | 1 | 1
Quarterly | 4 | 2
Monthly | 12 | 3
Weekly | 52 | 5
Daily | 250 | 20

## Residual Risk Rating
Residual Risk
|  | Weak | Low | Moderate | High | Very High
| Control | Adequate | Low | Low | Moderate | High
|  | Strong | Low | Low | Low | Moderate
|  |  | Low | Moderate | High | Very High
Inherent Risk

## Impact & Likelihood Matrix
| Frequency |  | Financial Impact
| Possible / Adverse Stress | Probable / Baseline Conditions | Profit and Loss Impact | Core Equity Impact | Balance Sheet Impact
Frequency | Event may occur over a business cycle (e.g. within 5~10 years) | Event occurs in business-as-usual situations |  | (CET-1)
Definition: |  | (e.g. every year)
Impact | VH | VH | >$5mm (~ 5% Earnings) | > 50 bps | > 5%
| H | H | $2mm - $5mm | 20 bps - 50 bps | 2% - 5%
| M | M | $1mm - $2mm | 10 bps - 20 bps | 1% - 2%
| L | L | < $1mm | < 10 bps | < 1%
| Frequency |  | Non-Financial Impact
| Possible / Adverse Stress | Probable / Baseline Conditions | Regulatory Impact | Customer Impact | Reputational Impact
Impact | VH | VH | Significant regulatory scrutiny; potential loss of business license; significant fines | Significant impact / loss of customers; likely litigation / compensation claims; significant loss of deposits | Trustee impact, deterioriation of Bank owner's value
| H | H | Regulatory scrutiny; possible legal action/regulatory fines; likely to result in improvement order | Potential financial detriment to customers / loss of customers | Negative media coverage in general public
| M | M | Internal compliance issues; possibly reportable to regulator; could result in improvement order | Moderate impact to customers, limited to a relatively small number | Negative coverage within industry
| L | L | Disciplinary warning; minimal regulator action | Minimal potential for customers impact | Negative press unlikely
Materiality Framework During Exceptional Situations
| Frequency |  | Financial Impact
| Remote / Severe Stress |  | Profit and Loss Impact | Core Equity Impact | Balance Sheet Impact
Frequency | Event occurs in exceptional situations |  |  | (CET-1)
Definition: | (e.g. tail risk, beyond 10 years)
Impact | VH |  | >$10mm (~ 10% Earnings) | > 100 bps | > 10%
| H |  | $4mm - $10mm | 40 bps - 100 bps | 4% - 10%
| M |  | $2mm - $4mm | 20 bps - 40 bps | 2% - 4%
| L |  | < $2mm | < 20 bps | < 2%

## Control Rating (hidden)
Control Rating
Operating Effectiveness
|  | Strong | Adequate | Weak
Design Effectiveness | Strong | Strong | Adequate | Weak
| Adequate | Adequate | Adequate | Weak
| Weak | Weak | Weak | Weak