## SDLC2022
RCSA # | Key Process | Key Steps in the Process | Process ID (2021) | Key Risks | Risk ID (2021) | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control Objective | Control Activity | Key or Non Key | Control Test # | MS Control ID | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendations | Remediation Plan | Owner | Due Date | Application Involved | Confirmations | Proposed Enhancements
RCSA ID Number | Name of the key process that is being performed. | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bank wide risk taxonomy | What is the impact of this risk? Select from: Very High, High, Moderate, Low | What is the probability of the risk occurring? Select from: Possible/Adverse, Probable/Baseline | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low | Describe the control objective in detail. The objective of the control in addressing the corresponding risk. | Describe the control in detail. A key control that is significant and deemed critical to a given process, and must be performed effectively to reduce the inherent risk that it is associated with, to an acceptable level. |  | Control ID Number | Metric Stream Identification | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often does the control occur? Select from: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing, decreasing or stable? | What are the results of this RCSA? | What is the issue or gap for this key process? | Finding ID Number | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Reference the application involved (for key risks only)
IT-SDLC-01 | Governance of SDLC Projects |  | IT-SDLC-P1 | Inadequate System Development Life Cycle (SDLC) Policy The Bank may fail to adequately and securely develop, implement, manage, monitor newly developed systems because the System Development Life Cycle (SDLC) policy is inadequate in providing guidance, consistency, accountability, efficiency, and clarity on how the SDLC is managed and how problems should be resolved. This may result in broad and negative impact to the Bank. | IT-SDLC-R1 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | In place System Development Life Cycle (SDLC) policy The System Development Life Cycle (SDLC) Policy is developed and effectively implemented. | In place System Development Life Cycle (SDLC) policy The System Development Life Cycle (SDLC) Policy (the “Policy”) applies to the development, implementation, management, monitoring, and compliance with System(s) Development at the Bank, in accordance with applicable state and federal statutes, rules and regulations. All Bank employees and third party resources engaged by the Bank that perform System(s) Development under the auspices of the Bank comply with the terms of this Policy to the degree applicable to them. Other third-party resources (vendors/manufacturers) have appropriate and secure SDLC processes in place, in-line with this Policy and considering a risk-based approach, to be reviewed through the vendor management onboarding and review process The Policy Owner monitors this Policy. Any non-compliance with this Policy is escalated to the Designated Management Committee for resolution. | Key | IT-SDLC-C01 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate Management of System Development Life Cycle (SDLC) Projects The Bank may fail to adequately and securely develop, implement, manage, monitor newly developed systems because the System Development Life Cycle (SDLC) of the projects are not adequately managed. This may result in broad and negative impact to the Bank. | IT-SDLC-R2 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Effective management of SDLC projects SDLC projects are adequately managed through feasibility study and the four phases: plan, create, test and deployment. If facilitated and managed by the Enterprise Project Management Office (EPMO), the SDLC projects follow the EPMO project management process. | Effective management of SDLC projects SDLC projects adhere to the four SDLC phases: plan, create, test and deployment. SDLC projects that are facilitated and managed by the Enterprise Project Management Office (EPMO) follow the EPMO project management process. Prior to planning an SDLC project, a feasibility study (an assessment of the practicality and pre-determined justification of the system) are performed by the business / product owner. The outcome results from the SDLC feasibility study are approved by the CTO. | Key | IT-SDLC-C02 |  | Preventative | Manual
IT-SDLC-01 | Planning of SDLC Projects |  | IT-SDLC-P2 | Absence of a Deployment Strategy for System Development Life Cycle (SDLC) Projects The Bank may develop application systems that are not aligned with the Bank's objectives and strategies because the deployment strategy of the System Development Life Cycle (SDLC) projects are not developed. This may result in broad and negative impact to the Bank. | IT-SDLC-R3 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Development of the deployment strategy for SDLC projects After a system development project is identified, a viable strategy for deployment is developed. | Development of the deployment strategy for SDLC projects After a system development project is identified, a viable strategy for deployment is developed. The strategy for deployment includes exploring how new functionality may improve the Bank’s presence in our market, impact operations and impact Bank employees after the proposed deployment of new systems. | Key | IT-SDLC-C03 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate Depth and Formality of the Plan for SDLC Projects The Bank may fail to adequately develop, implement, manage, monitor application systems because the planning of the SDLC projects lack adequate depth and formality. This may result in broad and negative impact to the Bank. | IT-SDLC-R4 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Depth and formality of the plan for SDLC projects The depth and formality of the plan commensurate with the characteristics and risks of the project. | Depth and formality of the plan for SDLC projects The depth and formality of the plan commensurate with the characteristics and risks of the project. | Key | IT-SDLC-C04 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequately documented project plan The Bank may develop application systems that are not aligned with the Bank's objectives and strategies because the requirements of business and of the System Development Life Cycle (SDLC) phases are not documented in the project plan. This may result in broad and negative impact to the Bank. | IT-SDLC-R5 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Project plan documentation of the requirements of business and project phases SDLC project plans clearly document the requirements for the business and for each additional phase (creation, testing and deployment). | Project plan documentation of the requirements of business and project phases SDLC project plans clearly document the requirements for the business. SDLC project plans clearly document the requirements for each additional phase (creation, testing and deployment). The requirements depend on the scope of the project. | Key | IT-SDLC-C05 |  | Preventative | Manual
IT-SDLC-01 | Creating of SDLC Projects |  | IT-SDLC-P3 | Absence of segregated environments The Bank may fail to adequately and securely develop, implement, manage, monitor newly developed systems because the environments are not appropriately segregated to support the System Development Life Cycle (SDLC) phases. This may result in broad and negative impact to the Bank. | IT-SDLC-R6 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Segregation of environments Segregated environments are established, including: development, test, production, and deployment testing . | Segregation of environments Segregated environments are established for: development, test, production, etc. in accordance with the plan. A system is created in preparation for deployment testing. | Key | IT-SDLC-C06 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Undocumented software development plan The Bank may fail to adequately and securely develop, implement, manage, monitor application systems because the software development plan does not adequately document the key areas pertaining to the development. This may result in broad and negative impact to the Bank. | IT-SDLC-R7 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Documentation of software development plan The software development plan documents the key areas pertaining to the development | Documentation of software development plan The software development plan is documented to address the following areas: - preliminary analysis or feasibility study; - risk identification and mitigation; - systems analysis; - general design; - detailed design; - development; - quality assurance and acceptance testing; - implementation; and - post-implementation maintenance and review | Key | IT-SDLC-C07 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Undefined Application Controls The newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the applications do not provide appropriate controls that are designed to prevent errors, loss, unauthorized modification or misuse of sensitive information.. This may result in broad and negative impact to the Bank. | IT-SDLC-R8 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Application controls Appropriate controls are designed into the software to prevent errors, loss, unauthorized modification or misuse of sensitive information. | Application controls Appropriate controls are designed into the software to prevent errors, loss, unauthorized modification or misuse of sensitive information. Application controls include: - validation with respect to the handling of input data, - validation of internal processing, - validation of inter-process messaging, - validation of message integrity, and - validation of output data | Key | IT-SDLC-C08 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate adoption of IT secure coding practices The newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the development of applications does not adequately adopt the IT secure coding practices. This may result in broad and negative impact to the Bank. | IT-SDLC-R9 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Adoption of IT secure coding practices IT secure coding practices are adopted in SDLC development. | Adoption of IT secure coding practices SDLC development is performed in accordance with IT secure coding requirements inclusive of regulatory requirements, Bank policy and industry best-practices. | Key | IT-SDLC-C09 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Participation of Information Security in SDLC development The newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because Information Security Department is not consulted for the coding and testing standards and guidelines. This may result in broad and negative impact to the Bank. | IT-SDLC-R10 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Participation of Information Security in SDLC development Information Security Department is consulted for the coding and testing standards and guidelines. | Participation of Information Security in SDLC development Information Security Department is consulted for the coding and testing standards and guidelines. | Key | IT-SDLC-C10 |  | Preventative | Manual
IT-SDLC-01 | Testing SDLC projects |  | IT-SDLC-P4 | Inadequate testing of newly developed systems The newly developed systems may fail to deliver the expected business value or introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the application systems are not adequately tested. This may result in broad and negative impact to the Bank. | IT-SDLC-R11 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Testing of newly developed systems The newly developed system is tested against the Test Plan and the stakeholders’ requirements | Testing of newly developed systems A Test Plan is created for the newly developed system The stakeholders’ requirements are documented to include functionality, interoperability (i.e., with vendor-supplied technology) and security. The newly developed system is tested against the Test Plan and the stakeholders’ requirements | Key | IT-SDLC-C11 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequately secured testing environment for newly developed systems The testing of the newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the testing is not performed in a non-production, testing environment. This may result in broad and negative impact to the Bank. | IT-SDLC-R12 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Secured testing environment for newly developed systems Newly developed systems are tested in a non-production, testing environment. | Secured testing environment for newly developed systems Testing is performed in a non-production, testing environment Appropriate security controls are implemented and operated effectively on the testing environment. The testing environment is physically and/or logically segregated from the production environment. Development and quality assurance/test staff are not be permitted access to production systems, unless absolutely required by their respective job duties/descriptions and only after approval by the CTO. | Key | IT-SDLC-C12 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate testing coverage The newly developed systems may fail to deliver the expected business value or introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the testing of the code components that address the business and other stakeholder’s requirements is not adequately covered. This may result in broad and negative impact to the Bank. | IT-SDLC-R13 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Adequate testing coverage The code components that address the business and other stakeholder’s requirements are identified and tested. | Adequate testing coverage The code components that address the business and other stakeholder’s requirements are identified. The test plan documents the approach to test the code components that address the business and other stakeholder’s requirements are identified. The testing coverage of the code components that address the business and other stakeholder’s requirements are identified is tracked. | Key | IT-SDLC-C13 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Unrestricted, unsecured and imprudent use of live data in testing The testing of the newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the use of live data in testing is not adequately restricted, secured and prudent. This may result in broad and negative impact to the Bank. | IT-SDLC-R14 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Restricted, secured and prudent use of live data in testing The use of live data in testing is restricted, secured and prudent. | Restricted, secured and prudent use of live data in testing The threat to the confidentiality and/or integrity of the live and sensitive (confidential and/or restricted) data is assessed before its use is permitted in testing. If possible, test data is anonymized (e.g., encrypted, masked, etc.) to mimic the characteristics of real data. Real data with any sensitive (confidential and/or restricted) data are appropriately sanitized, obfuscated or otherwise protected before being used for testing. | Key | IT-SDLC-C14 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate assessment of risk related to test data The testing of the newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the risk related to test data, including the risk of disclosure is inadequately assessed before the use of test data. This may result in broad and negative impact to the Bank. | IT-SDLC-R15 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Assessment of risk related to test data The risk related to test data, including the risk of disclosure is assessed before the use of test data. | Assessment of risk related to test data The risk related to test data, including the risk of disclosure is assessed before the use of test data. Information Security and related Data Protection Policies are consulted for guidance. | Key | IT-SDLC-C15 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate validation of data output from applications The newly developed systems may fail to deliver the expected business value or introduce new vulnerabilities to the Bank that can be exploited by threat vectors because data output from applications are inappropriately validated. This may result in broad and negative impact to the Bank. | IT-SDLC-R16 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Validation of data output from applications Data output from applications are appropriately validated. | Validation of data output from applications Data output from applications are validated to confirm that the processing of stored information is correct. Data output from applications are validated to confirm that the processing of stored information is appropriate to the circumstances. | Key | IT-SDLC-C16 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate management of defects from testing The newly developed systems may fail to deliver the expected business value or introduce new vulnerabilities to the Bank that can be exploited by threat vectors because defects found within the system during testing are inappropriately addressed before software is moved into production. This may result in broad and negative impact to the Bank. | IT-SDLC-R17 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Management of defects from testing Defects found within the system during testing are appropriately addressed before software is moved into production. | Management of defects from testing Defects found within the system during testing are addressed before software is moved into production. Defects found within the system during testing are risk-assessed before software is moved into production. Defects found within the system during testing are prioritized for resolution before software is moved into production. | Key | IT-SDLC-C17 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate documentation for the use of the system The newly developed systems may fail to deliver the expected business value or introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the governance documentation regarding the use of the system are inadequately developed, reviewed and accepted. This may result in broad and negative impact to the Bank. | IT-SDLC-R18 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Relevant documentation for the use of the system Governance documentation regarding the use of the system are developed, reviewed and accepted. | Relevant documentation for the use of the system Governance documentation regarding the use of the system (i.e., procedures and/or user manuals) are developed. Governance documentation regarding the use of the system (i.e., procedures and/or user manuals) are reviewed and accepted by the application stakeholders. | Key | IT-SDLC-C18 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate protection of private information The newly developed systems may introduce new vulnerabilities to the Bank that can be exploited by threat vectors because new product/service/technology systems with processing activities that involve personal information, aka private personal information (PPI) or personally identifiable information (PII), are not submitted to the Data Protection Impact Assessment (DPIA). This may result in broad and negative impact to the Bank. | IT-SDLC-R19 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Protection of private information New product/service/technology systems with processing activities that involve personal information, aka private personal information (PPI) or personally identifiable information (PII), are submitted to the Data Protection Impact Assessment (DPIA). | Protection of private information The Privacy Office is consulted to determine whether a Data Protection Impact Assessment (DPIA) is required for new product/service/technology systems with processing activities that involve personal information, aka private personal information (PPI) or personally identifiable information (PII). | Key | IT-SDLC-C19 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Absence of business approval before deployment The newly developed systems may fail to deliver the expected business value because business line management approval is not provided before the deployment of the systems. This may result in broad and negative impact to the Bank. | IT-SDLC-R20 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Business approval before deployment Business line management approval is required before moving the newly developed application on to the deployment phase | Business Approval before deployment Business line management approval is required before moving the newly developed application on to the deployment phase. | Key | IT-SDLC-C20 |  | Preventative | Manual
IT-SDLC-01 | Deploying SDLC projects |  | IT-SDLC-P5 | Incomplete User Acceptance Testing (UAT) after deployment The newly developed systems may fail to deliver the expected business value or introduce new vulnerabilities to the Bank that can be exploited by threat vectors because the User Acceptance Testing (UAT) is not completed after the system is moved into production. This may result in broad and negative impact to the Bank. | IT-SDLC-R21 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Completion of User Acceptance Testing (UAT) The User Acceptance Testing (UAT) is completed after the system is moved into production. | Completion of User Acceptance Testing (UAT) The User Acceptance Testing (UAT) is completed after the system is moved into production. The User Acceptance Testing (UAT) results and resolutions are approved and signed off by the relevant authorities after the system is moved into production. | Key | IT-SDLC-C21 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Incomplete user training after deployment The Bank may not be able to support or draw benefits from the new application because the user training is not completed after the system is moved into production. This may result in broad and negative impact to the Bank. | IT-SDLC-R22 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Completion of User Training The user training is completed after the system is moved into production. | Completion of User Training The user training is completed after the system is moved into production. | Key | IT-SDLC-C22 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Absence of post implementation evaluation The Bank may not be able to fully assess the benefits and shortcomings associated with the new application because a post Implementation evaluation is not performed to ensure the system is functioning properly per stakeholder requirements. This may result in broad and negative impact to the Bank. | IT-SDLC-R23 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Performance of post implementation evaluation A post Implementation evaluation is performed to ensure the system is functioning properly per stakeholder requirements. | Performance of post implementation evaluation A post Implementation evaluation is performed to ensure the system is functioning properly per stakeholder requirements. A report is completed. Any modifications, configuration changes and/or bug fixes, as the results of the post implementation evaluation, are performed or closed to the satisfaction of the stakeholders. | Key | IT-SDLC-C23 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Absence of post implementation user satisfaction survey The Bank may not be able to fully assess the benefits and shortcomings associated with the new application because a user satisfaction survey is not performed to gather user feedback on the system. This may result in broad and negative impact to the Bank. | IT-SDLC-R24 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Performance of post implementation user satisfaction survey An user satisfaction survey is performed after the system has been in production. | Performance of post implementation user satisfaction survey An user satisfaction survey is performed after the system has been in production. The user satisfaction survey is performed after the users have ample time to use to gauge usefulness and productivity of the system. | Key | IT-SDLC-C24 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | System documentation not finalized before SDLC project completion The Bank may not be able to support or draw benefits from the new application because the documentation regarding the use of the system (i.e., procedures and/or manuals) is not finalized before the SDLC project is complete. This may result in broad and negative impact to the Bank. | IT-SDLC-R25 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | System documentation finalized before SDLC project completion Documentation regarding the use of the system (i.e., procedures and/or manuals) is finalized before the SDLC project is complete. | System documentation finalized before SDLC project completion Documentation regarding the use of the system (i.e., procedures and/or manuals) is finalized before the SDLC project is complete. Documentation regarding the use of the system (i.e., procedures and/or manuals) is approved before the SDLC project is complete. | Key | IT-SDLC-C25 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | System not recorded in IT asset inventory The newly developed system may not be adequately supported because it is not recorded in the IT asset inventory and subject to the ITAM (IT Asset Management) project. This may result in broad and negative impact to the Bank. | IT-SDLC-R26 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | System recorded in IT asset inventory The system is recorded in the IT asset inventory and subject to the ITAM (IT Asset Management) project | System recorded in IT asset inventory The system is recorded in the ITAM (IT Asset Management) data repository. The system is subject to the ITAM (IT Asset Management) process for: - maintenance, security, support, End of Life (EoL) / End of Support (EoS) planning, etc. | Key | IT-SDLC-C26 |  | Preventative | Manual
IT-SDLC-01 |  |  |  | Inadequate update, maintenance and archiving of SDLC project documentation The Bank may not be able to support or draw benefits from the new application because the SDLC project documentation regarding the use of the system (i.e., procedures and/or manuals) is inadequately updated, maintained and archived. This may result in broad and negative impact to the Bank. | IT-SDLC-R27 | 8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing | Moderate | Probable/Baseline | Moderate | Update, maintenance and archiving of SDLC project documentation All SDLC project documentation is updated, maintained and archived in accordance with retention requirements. | Update, maintenance and archiving of SDLC project documentation The list of all SDLC project documentation is updated during the project. All SDLC project documentation is updated and maintained during all phases of the project. All SDLC project documentation is archived in accordance with retention requirements, for at least the life of the system. | Key | IT-SDLC-C27 |  | Preventative | Manual

## Aggregate
|  |  | Risk Rating | Count Inherent Risk | Count Residual Risk |  | Control Rating | Count Control Rating
|  |  | Very High | 0 | 0 |  | Strong | 0
|  |  | High | 0 | 0 |  | Adequate | 0
|  |  | Moderate | 14 | 0 |  | Weak | 0
|  |  | Low | 0 | 0
|  |  |  | 14 | 0 |  |  | 0
|  |  | Aggregate | Moderate | Low |  |  | Weak
|  |  |  | 5 | 6 |  |  | 5
|  |  | Final Assessment | High | Moderate |  |  | Adequate
2022 | [10 empty] | Residual Rating Verification |  |  |  | LOOKUP Table
Risk ID | Risk Description | Control ID | Control Description | Inherent Risk | Design Effectiveness | Operating Effectiveness | Control Rating | Test Results | Residual Rating | Risk Trending | Inherent Risk Rating | Combination <Control-Inherent Risk> | Residual Rating (Calculated) | Matching ("L" vs. "R")? | Combination <Control-Inherent Risk>
IT-SDLC-R1 | Inadequate System Development Life Cycle (SDLC) Policy | IT-SDLC-C01 | In place System Development Life Cycle (SDLC) policy | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Weak-Low | Low
IT-SDLC-R2 | Inadequate Management of System Development Life Cycle (SDLC) Projects | IT-SDLC-C02 | Effective management of SDLC projects | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Weak-Moderate | Moderate
IT-SDLC-R3 | Absence of a Deployment Strategy for System Development Life Cycle (SDLC) Projects | IT-SDLC-C03 | Development of the deployment strategy for SDLC projects | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Weak-High | High
IT-SDLC-R4 | Inadequate Depth and Formality of the Plan for SDLC Projects | IT-SDLC-C04 | Depth and formality of the plan for SDLC projects | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Weak-Very High | Very High
IT-SDLC-R5 | Inadequately documented project plan | IT-SDLC-C05 | Project plan documentation of the requirements of business and project phases | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Adequate-Low | Low
IT-SDLC-R6 | Absence of segregated environments | IT-SDLC-C06 | Segregation of environments | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Adequate-Moderate | Low
IT-SDLC-R7 | Undocumented software development plan | IT-SDLC-C07 | Documentation of software development plan | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Adequate-High | Moderate
IT-SDLC-R8 | Undefined Application Controls | IT-SDLC-C08 | Application controls | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Adequate-Very High | High
IT-SDLC-R9 | Inadequate adoption of IT secure coding practices | IT-SDLC-C09 | Adoption of IT secure coding practices | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Strong-Low | Low
IT-SDLC-R10 | Participation of Information Security in SDLC development | IT-SDLC-C10 | Participation of Information Security in SDLC development | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Strong-Moderate | Low
IT-SDLC-R11 | Inadequate testing of newly developed systems | IT-SDLC-C11 | Testing of newly developed systems | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Strong-High | Low
IT-SDLC-R12 | Inadequately secured testing environment for newly developed systems | IT-SDLC-C12 | Secured testing environment for newly developed systems | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A | Strong-Very High | Moderate
IT-SDLC-R13 | Inadequate testing coverage | IT-SDLC-C13 | Adequate testing coverage | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R14 | Unrestricted, unsecured and imprudent use of live data in testing | IT-SDLC-C14 | Restricted, secured and prudent use of live data in testing | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R15 | Inadequate assessment of risk related to test data | IT-SDLC-C15 | Assessment of risk related to test data | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R16 | Inadequate validation of data output from applications | IT-SDLC-C16 | Validation of data output from applications | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R17 | Inadequate management of defects from testing | IT-SDLC-C17 | Management of defects from testing | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R18 | Inadequate documentation for the use of the system | IT-SDLC-C18 | Relevant documentation for the use of the system | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R19 | Inadequate protection of private information | IT-SDLC-C19 | Protection of private information | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R20 | Absence of business approval before deployment | IT-SDLC-C20 | Business approval before deployment | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R21 | Incomplete User Acceptance Testing (UAT) after deployment | IT-SDLC-C21 | Completion of User Acceptance Testing (UAT) | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R22 | Incomplete user training after deployment | IT-SDLC-C22 | Completion of User Training | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R23 | Absence of post implementation evaluation | IT-SDLC-C23 | Performance of post implementation evaluation | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R24 | Absence of post implementation user satisfaction survey | IT-SDLC-C24 | Performance of post implementation user satisfaction survey | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R25 | System documentation not finalized before SDLC project completion | IT-SDLC-C25 | System documentation finalized before SDLC project completion | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R26 | System not recorded in IT asset inventory | IT-SDLC-C26 | System recorded in IT asset inventory | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A
IT-SDLC-R27 | Inadequate update, maintenance and archiving of SDLC project documentation | IT-SDLC-C27 | Update, maintenance and archiving of SDLC project documentation | Moderate | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | 0-Moderate | #N/A | #N/A

## SDLC Policy _Procedure
# | MetricStream Control Id # | [A] Policy [B] Procedures | Page /Section | Control Statement - AFH System Development Life Cycle Policy (Nov '2021) AFH System Development Life Cycle Procedure (May 2021) | Mandatory? | SDLC Control ID | Control Title
1 |  | [A] | Chapter III, Page 6, Section 3 "Key Components of Policy" | 3A. SDLC Phases: Some SDLC projects will be facilitated and managed by the Enterprise Project Management Office (EPMO) and must follow the EPMO project management process in addition to adhering to the SDLC phases. The four SDLC phases are: plan, create, test and deployment. Prior to planning an SDLC project, a feasibility study (an assessment of the practicality and pre-determined justification of the system) must be performed by the business / product owner and the outcome results in system development as a viable option as approved by the CTO. | Yes
2 |  | [A] | Chapter III, Page 6, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 1. Plan After a system development project is identified, a viable strategy for deployment must be developed. This includes exploring how new functionality may improve the Bank’s presence in our market, impact operations and impact Bank employees after the proposed deployment of new systems. | Yes
3 |  | [A] | Chapter III, Page 6, Section 3 "Key Components of Policy" | A. SDLC Phases: 1. Plan The depth and formality of the plan should be commensurate with the characteristics and risks of the project. | No
4 |  | [A] | Chapter III, Page 6, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 1. Plan All SDLC project plans must clearly define the requirements for the business and for each additional phase (creation, testing and deployment), depending on the scope of the project. | Yes
5 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 2. Create The necessary segregated environments must be established (i.e., development, test and production) in accordance with the plan; and the system is created in preparation for deployment testing. | Yes
6 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 2. Create Software development plan must be documented to address the areas of preliminary analysis or feasibility study; risk identification and mitigation; systems analysis; general design; detailed design; development; quality assurance and acceptance testing; implementation; post-implementation maintenance and review | Yes
7 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 2. Create Appropriate controls must be designed into the software to validate correct processing with respect to their handling of input data, internal processing, inter-process messaging, and message integrity and output data, to prevent errors, loss, unauthorized modification or misuse of sensitive information. | Yes
8 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 2. Create Development must be performed in accordance with IT secure coding requirements inclusive of regulatory requirements, Bank policy and industry best-practices. | Yes
9 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 2. Create Information Security Department should be consulted for these coding and testing standards and guidelines. | No
10 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test After creation, the new system must be tested in accordance with the documented test plan and the stakeholders’ requirements to include functionality, interoperability (i.e., with vendor-supplied technology) and security. | Yes
11 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test Testing must be performed in a non-production, test environment. Development and quality assurance/test staff must not be permitted access to production systems unless absolutely required by their respective job duties/descriptions and only after approval by the CTO. | Yes
12 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test Where software development is required, software test engineers must perform appropriate testing to confirm each component of the code works in accordance with business and other stakeholder’s requirements. | Yes
13 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test The Bank must strive to not test with live, sensitive (confidential and/or restricted) data, due to the threat to its confidentiality and/or integrity. If the system allows it, testing of systems must be accomplished with anonymized (e.g., encrypted, masked, etc.) data that mimics the characteristics of real data, or on copies of real data with any sensitive (confidential and/or restricted) data appropriately sanitized, obfuscated or otherwise protected. | Yes
14 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test As a general principle, the risk of test data disclosure should be less than that of the production environment. Information Security and related Data Protection Policies should be consulted for guidance, as needed. | No
15 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test Data output from applications should be validated to confirm that the processing of stored information is correct and appropriate to the circumstances. | No
16 |  | [A] | Chapter III, Page 7, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test Application testing must occur and any defects found within the system during testing must be addressed, risk-assessed and prioritized for resolution before software is moved into production. | Yes
17 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test Governance documentation regarding the use of the system (i.e., procedures and/or user manuals) must be developed. | Yes
18 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test New product/service/technology systems involving personal information processing activities may require a Data Protection Impact Assessment (DPIA); consult the Privacy Office to obtain a determination. Its purpose is to ensure appropriate controls are implemented. | No
19 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 3. Test Business line management approval is required before moving on to the Deployment phase | Yes
20 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 4. Deployment After the system is moved into production, User Acceptance Testing (UAT) should be completed as well as user training. | No
21 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 4. Deployment A Post Implementation Evaluation Report should also be completed to ensure the system is functioning properly per stakeholder requirements. If required per evaluation results, any modifications, configuration changes and/or bug fixes should also be performed. | No
22 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 4. Deployment After the system has been in production with ample time for use, a user satisfaction survey should also be completed to gauge usefulness and productivity of the system. | No
23 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 4. Deployment Documentation regarding the use of the system (i.e., procedures and/or manuals) must also be finalized and approved before the SDLC project is complete. | Yes
24 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3A. SDLC Phases: 4. Deployment The system must be appropriately recorded (i.e., inventoried) for future maintenance, security, support and End of Life (EoL) / End of Support (EoS) planning and other requirements. | Yes
25 |  | [A] | Chapter III, Page 8, Section 3 "Key Components of Policy" | 3B. System Support and Disposal All SDLC project documentation must be updated and maintained during all phases of the project. Documentation must be archived in accordance with retention requirements, for at least the life of the system. | Yes
26 |  | [B] | Chapter III, Page 7, Section 3 "Key Components of Procedure" | 3D. Test Phase During this phase, application testing will occur and any defects found within the system during testing must be addressed, risk-assessed and prioritized for resolution before software is moved into the production environment | Yes
27 |  | [B] | Appendix A – Feasibility Study Template, Page 11 | Risks: Where are the Risks? Can they be minimized? Technical risks - There must be an outline plan with a rough timetable and staff allocation. The plan must have a very large margin for contingencies. (Projects typically require twice the staff and/or time envisaged in the feasibility plan.) | Yes
28 |  | [B] | Appendix C – Functional Requirements Document Template, Page 13 | Operational Requirements: Do not state how these requirements will be satisfied. For example, in the Reliability section, answer the question, “How reliable must the system be”? | Yes
29 |  | [B] | Appendix C – Functional Requirements Document Template, Page 13 | Recoverability: How soon after a failure must the system be restored? | Yes
30 |  | [B] | Appendix C – Functional Requirements Document Template, Page 13 | Capacity: How much {storage, bandwidth, memory utilization, etc.} must the system have to support all resource and compliance requirements? | Yes
31 |  | [B] | Appendix C – Functional Requirements Document Template, Page 13 | Data Retention: Describe the length of time various forms of data must be retained and the requirements for its destruction. | Yes

## DevAcq2020 (hidden)
RCSA # | Key Process | Key Steps in the Process | Process ID | Key Risks | Risk ID | Type of Risk | Impact Rating | Probability Rating | Inherent Risk Rating | Control Description | Key or Non Key | Control ID | Type of Control (Preventative or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Control Occurrence | Testing Frequency | Sample Size | Residual Risk Rating | Direction of Risk | Testing Results | Findings | Finding ID | Recommendation | Remediation Plan | Owner | Due Date | Application Involved | Notes
RCSA ID Number | Name of the key process that is being performed. | Describe the key activity or tasks performed within this process. | Process ID Number | Describe the risk in detail. A key risk that is significant and deemed critical to a process, and is a result in the process that is not desired. It can be identified as previously disclosed errors, losses, failed internal processes, people, systems, or from external events. | Risk ID Number | Select the risk category based on the bankwide risk taxonomy | What is the impact of this risk? Select from: Very High , High, Medium, Low | What is the probability of the risk occurring? Select from: Possible/Adverse Stress, Probable/Baseline Conditions | What is the level of risk before controls, based on the impact and probability? Select from: Very High High Moderate Low | Describe the control in detail. A key control that is significant and deemed critical to a given process, and must be performed effectively to reduce the inherent risk that it is associated with, to an acceptable level. | Is this a Key Control? Select From: Key, Non Key | Control ID Number | Is the control preventative or detective? Select from: Preventative, Detective | Is the control automated or manual? Select from: Automated, Manual | Is the design of the control complete and effective? Select from: Strong Adequate Weak | Is the control operating as designed and effective? Select from: Strong Adequate Weak | What is the control rating? Select from: Strong Adequate Weak | How often is this Control invoked? Select From: Daily, Weekly, Monthly, Quarterly, Annually, Transactional | How often is this control(s) being tested? Select from: Daily, Weekly, Monthly, Quarterly, Annually | What is the sample size for control testing? | What is the level of risk after controls? Select from: Very High High Moderate Low | Is the residual risk level increasing or decreasing? Select from: Increasing Decreasing Stable | What are the results of this RCSA? | What is the issue or gap for this key process? | What is the issue or gap for this key process? | Based on the issue identified, what is the recommendation to mitigate the risk? | Describe the actions being taken to close the finding. | Name of the owner of the issue. | The date when the remediation action will be completed. | Which application is performing the key control
IT DEV 1 | IT Development & Acquisition | IT Asset Inventory 1. The KACE Software is used to Automatically capture everything that is attached to the Network. This is effective as there is an agent located on each server and workstation. 2. For New Servers, Workstations, Printers, Monitors and Laptops equipment is ordered through the ticketing system which is manually entered to capture the request and is retained as a permanent record. When the Device is provided the PC Name is matched with the KACE. 3.When an asset is decommissioned it is communicated to Finance. 4.IT Assets have not been compared to Accounting records. Self Identified | IT DEV-P1 | Management may not have a process to capture the Hardware devices that are in place at the Bank. Therefore, a vendor may no longer support the device which could present a security risk to the Bank | IT DEV-R1 | 8.4.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability | Very High | Possible/Adverse Stress | High | Management uses a Tool to Capture and record Devices that are resident at the Bank to ensure completeness and accuracy. | Key | IT DEV-C1 | Detective | Automated | Adequate | Strong | Adequate | Daily | Annually | 1 - Extract Kace | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | The Bank does not conduct a periodic reconciliation of the IT Hardware owned to the financial statement records | Key | IT DEV-C2 | Detective | Manual | Weak | Weak | Weak | Annually | Annually | IT Asset Reconciliation | High | Increasing | Fail | Hardware inventory not periodically reviewed to accounting records. IT DEV-F3 | IT DEV-F3 | The Bank should annually conduct an review of the IT Assets and compare this to the Accounting Records | The Bank will be implementing Hardware Asset Management module that is available for ServiceNow and these will allow the Bank to reconcile the inventory to fixed assets data maintained by Accounting Department. Apple Bank is conducting a physical Inventory of Hardware Assets. | Debi Gupta/Jose Mendez | 2020-12-31 | ServiceNow
IT DEV 1 | IT Development & Acquisition | Software OS Inventory 1. The Bank has an end of life policy that is in place to provide guidance for monitoring operating system and application software end-of-life. 2.Operating system software is captured and reported through the use of technology. This is completed through multiple means including: - Ongoing Monitoring - Internal and External Vulnerability Scans 3. All Operating systems that are reaching the end of life are replaced with upgraded supported operating systems. | IT DEV-P2 | Operating System Software may no longer be supported by the Vendor and may no longer provide security patches. | IT DEV-R2 | 8.4.2 - Operational Risk - Systems - Application Maintenance and Change Control | Very High | Possible/Adverse Stress | High | Management Maintains an Inventory of Operating Systems and versions to ensure that these are monitored for End Of Life. This is achieved so that there is a process in place to ensure that each is supported by the vendor | Key | IT DEV-C3 | Preventative | Automated | Strong | Strong | Strong | Daily | Daily | Internal Vulnerability Scans | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[7 empty] | Very High | Possible/Adverse Stress | High | Operating Systems that reach end-of-life are upgraded to ensure that these are supported by the vendor. | Key | IT DEV-C4 | Preventative | Manual | Weak | Weak | Weak | Daily | Daily | Internal Vulnerability Scans Follow-up | High | Increasing | Fail | Application software resides on Operating Systems that are no longer supported by the vendor. These include two instances of Windows 7 desktops for data center door access and the document imaging system. These unsupported systems have been discovered by IT control processes, however these systems are managed outside the IT group. | IT DEV F2 | Management should develop a process to communicate when not supported systems are identified the appropriate business owners. | The Bank will be implementing Software Asset Management module that is available for ServiceNow. ServiceNow SAM will go out to the software vendor portals to collect data about EOL timeline and allow the Bank to monitor this well before EOL. Once that is done, IT will reach out to these application owners to identify a path forward for upgrading/replacing these applications running EOL operating systems. | Debi Gupta/Jose Mendez | 2020-12-31 | ServiceNow
IT DEV 1 | IT Development & Acquisition | Application Inventory 1. The Bank has an end of life policy that is in place to provide guidance for monitoring operating system and application software end-of-life. 2.Application software is captured and reported through the use of technology. This is completed through multiple means including: - Ongoing Monitoring - Internal and External Vulnerability Scans 3. All Applications that are reaching the end of life are replaced with upgraded supported operating systems. | IT DEV-P3 | Application Software may no longer be supported by the Vendor and may no longer provide security patches. | IT DEV-R3 | 8.4.2 - Operational Risk - Systems - Application Maintenance and Change Control | Very High | Possible/Adverse Stress | High | Management Maintains an Inventory of Applications so that there is a process in place to ensure that each is supported by the vendor | Key | IT DEV-C5 | Detective | Automated | Weak | Weak | Weak | Daily | Daily | Application Inventory | High | Increasing | Fail | Application Inventory is incomplete. The Bank will need to develop a process to inventory and maintain a complete list of both In-house and Vendor Supported Applications. This should include details i.e. version, purpose, developer etc. | IT DEV F1 | The Bank is I the process of compiling all the applications at the Bank to create a centralized list. This effort will need to be completed. | The Bank has implemented ServiceNow/CMDB module that scans the Bank's IT universe and identifies all software applications that running, This list will be used to eliminate software that are no longer needed and help standardize the application vendors. | Debi Gupta/Jose Mendez | 2020-09-30 | ServiceNow
[7 empty] | Very High | Possible/Adverse Stress | High | Applications that reach end-of-life are upgraded to ensure that these are supported by the vendor. | Key | IT DEV-C6 | Preventative | Manual | Adequate | Adequate | Adequate | Transactional | Daily | Vulnerability Scan | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT DEV 1 | IT Development & Acquisition | Budget Vs Actual Management 1. The CTO receives reports that provide the Budget vs Actual Spend for technology. These are reviewed by the CTO to ensure that the are significant changes in Month to Month expenses for 2. Monthly reports are provide to the CTO, which are included to the Board of Directors a. Software b Hardware c IT Vendor Expenses | IT DEV-P4 | The CTO may not have the necessary support for monitoring ongoing expenses to ensure the Actual expenses are in align with budget. | IT DEV-R4 | 8.4.0 - Operational Risk - Systems | High | Possible/Adverse Stress | Moderate | Reports are generated from the Finance Group which are used by the CTO to monitor ongoing expenses. | Key | IT DEV-C7 | Detective | Manual | Strong | Strong | Strong | Monthly | Monthly | 1 | Moderate | Stable | Pass | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Inherent Risk Rating (hidden)
Inherent Risk Determination
If the Probabliity = Possible/ Adverse Stress, then the Inherent Risk Value is reduced 1 level from from the Impact Rating
If the Probablity = If Probable/Baseline Conditions the Inherent Risk Value the same as the Impact Rating

## Testing Frequency (hidden)
Control Frequency | Assumed Population size | Minimum Sample Size
Annual | 1 | 1
Quarterly | 4 | 2
Monthly | 12 | 3
Weekly | 52 | 5
Daily | 250 | 20

## Residual Risk Rating (hidden)
Residual Risk
| Weak | Low | Moderate | High | Very High
Control | Adequate | Low | Low | Moderate | High
| Strong | Low | Low | Low | Moderate
|  | Low | Moderate | High | Very High
Inherent Risk

## Formula (hidden)
Residual Risk
| Weak | Low | Moderate | High | Very High
Control | Adequate | Low | Low | Moderate | High
| Strong | Low | Low | Low | Moderate
|  | Low | Moderate | High | Very High
Inherent Risk

## Impact & Likelihood Matrix (hidden)
| Frequency |  | Financial Impact
| Possible / Adverse Stress | Probable / Baseline Conditions | Profit and Loss Impact | Core Equity Impact | Balance Sheet Impact
Frequency | Event may occur over a business cycle (e.g. within 5~10 years) | Event occurs in business-as-usual situations |  | (CET-1)
Definition: |  | (e.g. every year)
Impact | VH | VH | >$5mm (~ 5% Earnings) | > 50 bps | > 5%
| H | H | $2mm - $5mm | 20 bps - 50 bps | 2% - 5%
| M | M | $1mm - $2mm | 10 bps - 20 bps | 1% - 2%
| L | L | < $1mm | < 10 bps | < 1%
| Frequency |  | Non-Financial Impact
| Possible / Adverse Stress | Probable / Baseline Conditions | Regulatory Impact | Customer Impact | Reputational Impact
Impact | VH | VH | Significant regulatory scrutiny; potential loss of business license; significant fines | Significant impact / loss of customers; likely litigation / compensation claims; significant loss of deposits | Trustee impact, deterioriation of Bank owner's value
| H | H | Regulatory scrutiny; possible legal action/regulatory fines; likely to result in improvement order | Potential financial detriment to customers / loss of customers | Negative media coverage in general public
| M | M | Internal compliance issues; possibly reportable to regulator; could result in improvement order | Moderate impact to customers, limited to a relatively small number | Negative coverage within industry
| L | L | Disciplinary warning; minimal regulator action | Minimal potential for customers impact | Negative press unlikely
Materiality Framework During Exceptional Situations
| Frequency |  | Financial Impact
| Remote / Severe Stress |  | Profit and Loss Impact | Core Equity Impact | Balance Sheet Impact
Frequency | Event occurs in exceptional situations |  |  | (CET-1)
Definition: | (e.g. tail risk, beyond 10 years)
Impact | VH |  | >$10mm (~ 10% Earnings) | > 100 bps | > 10%
| H |  | $4mm - $10mm | 40 bps - 100 bps | 4% - 10%
| M |  | $2mm - $4mm | 20 bps - 40 bps | 2% - 4%
| L |  | < $2mm | < 20 bps | < 2%

## Lists for Data Validation (hidden)
Risk Taxonomy | Impact Rating | Probability Rating | Inherent Risk Rating | Type of Control (Preventive or Detective) | Control (Automated or Manual) | Control Design Effectiveness | Control Operating Effectiveness | Control Rating | Testing Frequency | Residual Risk Rating | Direction of Risk | Key/Non Key | Control Occurrence
1.1.0 - Credit Risk - Counterparty | Very High | Possible/Adverse | Very High | Preventative | Automated | Strong | Strong | Strong | Daily | Very High | Increasing | Key | Daily
1.2.0 - Credit Risk - Concentration | High | Probable/Baseline | High | Detective | Manual | Adequate | Adequate | Adequate | Weekly | High | Decreasing | Non Key | Weekly
1.3.0 - Credit Risk - Settlement | Moderate |  | Moderate |  |  | Weak | Weak | Weak | Monthly | Moderate | Stable |  | Monthly
1.4.0 - Credit Risk - Collateral / Credit Mitigation | Low |  | Low | [5 empty] | Quarterly | Low |  |  | Quarterly
2.1.0 - Liquidity Risk - Funding Liquidity | [8 empty] | Annually |  |  |  | Annually
2.2.0 - Liquidity Risk - Non Traded Market | [8 empty] | Transactional |  |  |  | Transactional
3.1.0 - Capital Risk - Capital Adequacy
4.1.1 - Market Risk - Interest Rate - Delta
4.1.2 - Market Risk - Interest Rate - Gamma (Convexity)
4.1.3 - Market Risk - Interest Rate - Vega
4.1.4 - Market Risk - Interest Rate - Theta
4.1.5 - Market Risk - Interest Rate - Correlation
4.1.6 - Market Risk - Interest Rate - Event
4.1.7 - Market Risk - Interest Rate - Discount Rate
4.1.8 - Market Risk - Interest Rate - Prepayment
4.2.1 - Market Risk - Foreign Exchange/Currency - Delta
4.2.2 - Market Risk - Foreign Exchange/Currency - Gamma (Convexity)
4.2.3 - Market Risk - Foreign Exchange/Currency - Vega
4.2.4 - Market Risk - Foreign Exchange/Currency - Theta
4.2.5 - Market Risk - Foreign Exchange/Currency - Correlation
4.2.6 - Market Risk - Foreign Exchange/Currency - Event
4.3.1 - Market Risk - Equity - Delta
4.3.2 - Market Risk - Equity - Gamma (Convexity)
4.3.3 - Market Risk - Equity - Vega
4.3.4 - Market Risk - Equity - Theta
4.3.5 - Market Risk - Equity - Correlation
4.3.6 - Market Risk - Equity - Event
4.3.7 - Market Risk - Equity - Dividend
4.3.8 - Market Risk - Equity - Borrow Cost
4.4.1 - Market Risk - Commodity - Delta
4.4.2 - Market Risk - Commodity - Gamma (Convexity)
4.4.3 - Market Risk - Commodity - Theta
4.4.4 - Market Risk - Commodity - Correlation
4.4.5 - Market Risk - Commodity - Event
5.1.0 - Model Risk - Intrinsic Uncertainty
5.2.0 - Model Risk - Model Design
5.3.0 - Model Risk - Model Usage
5.4.0 - Model Risk - Model Documentation
5.5.0 - Model Risk - Model Validation
6.1.0 - Business Risk - Failure to Meet Earnings Target
6.2.0 - Business Risk - Failure to Adapt to Long-Term Strategic Trends
6.3.0 - Business Risk - New Business and Change Management
6.4.0 - Business Risk - Investment
7.1.1.1 - Reputational Risk - Product - Product Liability - Financial Product Safety
7.1.1.2 - Reputational Risk - Product - Product Liability - Responsible Investment
7.2.1.1 - Reputational Risk - Environmental - Climate Change - Greenhouse Gas (GHG) Emissions
7.2.2.1 - Reputational Risk - Environmental - Natural Resources - Operating from Resource Stressed Locations - Water availability, etc.
7.2.3.1 - Reputational Risk - Environmental - Pollution and Waste - Carbon Footprint
7.2.3.2. - Reputational Risk - Environmental - Pollution and Waste - Energy Efficiency
7.3.1.1 - Reputational Risk - Societal - Human Capital - Diversity and Inclusion (MBE owned, etc.)
7.3.1.2 - Reputational Risk - Societal - Human Capital - Health and Safety
7.3.1.3 - Reputational Risk - Societal - Human Capital - Economic Contribution - Community Re-investment
7.4.1.1 - Reputational Risk - Governance - Corporate Behavior - Anti Bribery Policy
7.4.1.2 - Reputational Risk - Governance - Corporate Behavior - Anti Corruption Policy
7.4.1.3 - Reputational Risk - Governance - Corporate Behavior - Protected Ethics Advice & Reporting Mechanisms
8.1.1 - Operational Risk - Financial Crime - Fraud, Theft or Misappropriation of Assets
8.1.2 - Operational Risk - Financial Crime - Data Theft or Misuse
8.1.3 - Operational Risk - Financial Crime - Data Protection & Customer Confidentiality
8.1.4 - Operational Risk - Financial Crime - False Representation & Suitability and Appropriateness
8.1.5 - Operational Risk - Financial Crime - AML ¦ BSA
8.1.6 - Operational Risk - Financial Crime - Sanctions
8.2.1 - Operational Risk - Compliance - Branch and ATM Operations
8.2.2 - Operational Risk - Compliance - Funds Deposit and Transfers/Transactions
8.2.3 - Operational Risk - Compliance - Credit Origination
8.2.4 - Operational Risk - Compliance - Account Setup and Opening
8.2.5 - Operational Risk - Compliance - Customer Communications and Marketing Material
8.2.6 - Operational Risk - Compliance - Account Maintenance and Servicing
8.2.7 - Operational Risk - Compliance - Customer Protection
8.2.8 - Operational Risk - Compliance - Record Keeping and Customer Reporting
8.2.9 - Operational Risk - Compliance - Corporate/Business Practices
8.2.10 - Operational Risk - Compliance - Regulatory Reporting
8.2.11 - Operational Risk - Compliance - Internal Reporting and Monitoring
8.3.1 - Operational Risk - People and Conduct - Employment Laws and HR Practices
8.3.2 - Operational Risk - People and Conduct - Discrimination, Harassment or Bullying
8.3.3 - Operational Risk - People and Conduct - Diversity, Code of Conduct and Ethical Behavior
8.3.4 - Operational Risk - People and Conduct - Compliance with Policies and Procedures
8.4.1 - Operational Risk - Processes - Branch and ATM Operations
8.4.2 - Operational Risk - Processes - Funds Deposit and Transfers/Transactions
8.4.3 - Operational Risk - Processes - Credit Origination
8.4.4 - Operational Risk - Processes - Account Setup and Opening
8.4.5 - Operational Risk - Processes - Customer Communications and Marketing Material
8.4.6 - Operational Risk - Processes - Account Maintenance and Servicing
8.4.7 - Operational Risk - Processes - Customer Protection
8.4.8 - Operational Risk - Processes - Record Keeping and Customer Reporting
8.4.9 - Operational Risk - Processes - Corporate/Business Practices
8.4.10 - Operational Risk - Processes - Regulatory Reporting
8.4.11 - Operational Risk - Processes - Internal Reporting and Monitoring
8.5.1 - Operational Risk - Systems - IT Technology, Infrastructure and Platform Stability
8.5.2 - Operational Risk - Systems - Application Maintenance, Asset Management and Change Control
8.5.3 - Operational Risk - Systems - Application & Process Design, Development and Testing
8.5.4 - Operational Risk - Systems - End User Computing
8.5.5 - Operational Risk - Systems - Identity Access Management
8.5.6 - Operational Risk - Systems - Data Integrity and Quality
8.5.7 - Operational Risk - Systems - Data Architecture and Governance
8.6.1 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Selection
8.6.2 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Contracting
8.6.3 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Due Diligence
8.6.4 - Operational Risk - Third-Party Suppliers, Vendors and Outsourcing - Inadequate Monitoring
8.6.5 - Operational Risk - Third Party Suppliers, Vendors and Outsourcing - Supplier Failure
8.6.6 - Operational Risk - Third Party Suppliers, Vendors and outsourcing - Fourth Party
8.6.7 - Operational Risk - Third Party Suppliers, Vendors and Outsourcing - Offboarding
8.7.1 - Operational Risk - Cyber - Appropriate Hardening
8.7.2 - Operational Risk - Cyber - Secure Configuration/ Configuration Management
8.7.3 - Operational Risk - Cyber - Patch Management
8.7.4 - Operational Risk - Cyber - Security Architecture
8.7.5 - Operational Risk - Cyber - Vulnerability Management/ Zero-Day Vulnerabilities
8.7.6 - Operational Risk - Cyber - Anomalies & Events
8.7.7 - Operational Risk - Cyber - Protective Technology
8.7.8 - Operational Risk - Cyber - Security Continuous Monitoring
8.8.1 - Operational Risk - Resiliency - Business Continuity Plan
8.8.2 - Operational Risk - Resiliency - Disaster Recovery
8.8.3 - Operational Risk - Resiliency - Backups
8.8.4 - Operational Risk - Resiliency - Terrorism, Vandalism and Physical Security
8.8.4 - Operational Risk - Terrorism, Vandalism and Physical Security

## Control Rating (hidden)
Control Rating
Operating Effectiveness
|  | Strong | Adequate | Weak
Design Effectiveness | Strong | Strong | Adequate | Weak
| Adequate | Adequate | Adequate | Weak
| Weak | Weak | Weak | Weak