## Slide 1: IT Risk & Control Self Assessment 2022 Plan
Debi Gupta, EVP, CTO
February 2022
Draft

## Slide 2: Agenda
Background
Proposed Approach
Proposed Execution Plan
IT RCSA 2022 Schedule
Additional IT RCSAs
Appendix: Key IT RCSA Activities

## Slide 3: Proposed IT RCSA 2022 Approach
Residual Risk (Per 2021 RCSA) | No Change (Low Risk Impact) | Minor Change (Moderate Risk Impact) | Major Change (High Risk Impact)
Low | Business Attestation No Test | Walk-through Test of Design | Walk-through Risk-based Sample Testing
Moderate | Business Attestation Test of Design | Walk-through Risk-based Sample Testing | Walk-through Risk-based Sample Testing
High / Very High | Walk-through Risk-based Sample Testing | Walk-through Risk-based Sample Testing | Walk-through Risk-based Sample Testing
RCSA approach: (a) Business Attestation: business confirmation in writing that there has been no material change since RCSA 2021; (b) Test of Design: 1 sample required; (c) Risk-based Sample Testing: number of samples proportional to the residual risk rating of the process.
On change level assessment: (a) Three change areas are assessed: ownership, process, and technology; (b) Three levels of change are considered: no change, minor change and major change. For each change level, the risk rating will be based on the materiality level of the changes, in alignment with the Bank’s Materiality Framework.

## Slide 4: Proposed IT RCSA 2022 Execution Plan
IT RCSA Process Area | Anticipated Change Rates in 2022 | Residual Risk at End of 2021 | Proposed RCSA Approach in 2022
1. IT Strategy and Governance | No change (O-No, P-No, T-No) | Low | Attest (Q1) No Test
2. IT Operations – Physical Security (*) No IT RCSA Performed in 2021 | No Change (O-No, P-No, T-No) | Low | Attest (Q1) No Test
3. IT Operations - Resource Monitoring SolarWinds, NOC | No Change (O-No, P-No, T-No) | Low | Attest (Q1) No Test
4. IT Infrastructure - Router/ Patch Management | No change (O-No, P-No, T-No) | Moderate | Attest (Q1) TOD (Q2)
5. Electronic Banking | No Change (O-No, P-No, T-No) | Low | Attest (Q1) No Test
6. IT Development and Acquisition 2 weak controls in 2021 SNOW ITAM in development in 2021 | Minor Change (O-No, P-Yes, T-Yes) | Moderate | WT (Q2) RBST (Q3)
Change Area: Ownership (O), Process (P), Technology (T)
Abbreviations: Walk-Through (WT), Test of Design (TOD), Risk-based Sample Testing (RBST), Disaster Recovery (DR), Network Access Control (NAC)
(*) The review includes the BC/DR Team Physical Site Security Assessment and other relevant assessments

## Slide 5: Proposed Execution Plan, Continued
IT RCSA Process Area | Anticipated Change Rates in 2022 | Residual Risk at End of 2021 | Proposed RCSA Approach in 2022
7. Business Continuity/ Disaster Recovery 5 weak controls in 2021 | Minor Change (O-Yes, P-Yes, T-Yes) | Moderate | WT BCP (Q1) RBST BCP (Q2) WT DR (Q2) (*) RBST DR (Q3)
8. IT Operations – Backup/Recovery Anticipated change related to DR in AWS | Major Change (O-No, P-Yes, T-Yes) | Low | WT (Q2) (*) RBST (Q3)
9. Change Management 1 weak control in 2021, 2 high residual risks SNOW workflow applicable to bank wide TripWire Implementation (Q2) | Major Change (O-Yes, P-Yes, T-Yes) | Moderate | WT (Q2) RBST (Q3)
10. IT Infrastructure - Segmentation, NAC 2 weak controls in 2021, 2 very high residual risks Project in progress in 2021 | Major Change (O-No, P-Yes, T-Yes) | Very High | WT (Q1) RBST (Q2)
(*) The RCSA of Disaster Recovery (DR) and IT Operations Backup/Recovery are synchronized to account for the overlapping of the changes in these process in 2022
Change Area: Ownership (O), Process (P), Technology (T)
Abbreviations: Walk-Through (WT), Test of Design (TOD), Risk-based Sample Testing (RBST), Disaster Recovery (DR), Network Access Control (NAC)

## Slide 6: Proposed Execution Plan, Continued
IT RCSA Process Area | Anticipated Change Rates in 2022 | Residual Risk at End of 2021 | Proposed RCSA Approach in 2022
11. IT Operations - Logical Access 2 high residual risks User entitlement 2022 Q2 Role-Based Access Phase 1 2022 Q2 | Major Change (O-Yes, P-Yes, T-Yes) | Moderate | WT (Q3) RBST (2022 Q4)
12. IT Operations IBS CORE Implementation in Q3 | Major Change (O-No, P-Yes, T-Yes) | Low | WT (Q4) (*) RBST (2022 Q4 - 2023 Q1)
(*) The IT Operations RCSA will leverage Internal Audit’s evaluation of the CORE internal controls and testing of the related processes
Change Area: Ownership (O), Process (P), Technology (T)
Abbreviations: Walk-Through (WT), Test of Design (TOD), Risk-based Sample Testing (RBST), Disaster Recovery (DR), Network Access Control (NAC)

## Slide 7: IT RCSA 2022 Schedule (Illustration)
IT RCSA Process Area | 2022 Q1 | 2022 Q2 | 2022 Q3 | 2022 Q4 | 2023 Q1
1. IT Strategy and Governance |  |  |  |  | 
2. IT Operations - Physical security |  |  |  |  | 
3. IT Operations – Resource Monitoring |  |  |  |  | 
4. IT Infrastructure - Router/Patch management |  |  |  |  | 
5. Electronic Banking |  |  |  |  | 
6. IT Development and Acquisition |  |  |  |  | 
7. Business Continuity/ Disaster Recovery |  |  |  |  | 
8. IT Operations – Backup/Recovery |  |  |  |  | 
9. Change Management |  |  |  |  | 
10. IT Infrastructure Segmentation, NAC |  |  |  |  | 
11. IT Operations - Logical Access |  |  |  |  | 
12. IT Operations - IBIS CORE |  |  |  |  | 
Attest
Test of Design
Walk through
Risk-based Sample Test
DR
BC
BC
DR

## Slide 8: Additional IT RCSAs
In addition to the IT RCSA process areas reviewed during 2021, the following initiatives are outlined on the IT Strategic Plan and will be included in the IT RCSA as follows:
Network Infrastructure
  Wi-Fi Network – Target Completion Q2, 2022
  IP Address Management (IPAM) – Target Completion Q4, 2022

## Slide 9: Key IT RCSA Activities
Attest
Purposes: To obtain business confirmation that no material changes have occurred. A written form will be submitted to the business owners with key process controls. The owner will attest that as of the date no material changes in controls or associated processes have occurred.
Walk-Through
Purpose: Planning sessions with the process owners to confirm the control objectives and design, including handshakes with other areas. Discussions include changes from prior year, anticipated changes during the year as well as follow ups on issues that were reported in the prior year.
Input
  Prior year’s Risk and Control Matrix for the key process
  Relevant and applicable policies, procedures and standards
  Related issues and remediation that are outstanding from the prior year
  Artifacts relevant and related to the design of the controls
Output
  Business Attestation for “no change” areas in key processes
  Confirmed test schedule for the key process
  Confirmed in-scope test areas and related in-scope controls
  Updated Risk and Control Matrix for the key process, risk and control
  Assessment of the design effectiveness of the in-scope controls in the in-scope test areas

## Slide 10: Key IT RCSA Activities, Continued
  Risk-Based Sampling Testing
  Purpose: Detailed testing to assess the operating effectiveness of the in-scope controls in the in-scope test areas. Number of test samples is proportioned to the risk rating of the related process.
  Input
    Confirmed in-scope test areas and controls from Walkthrough sessions
    Evidence relevant and related to the operating of the controls
      Evidence is obtained during the interim testing period (12/1/2021 – 2/28/2022)
  Output
    Assessment of the operating effectiveness of the in-scope controls during the interim testing period
  Test of Design (Limited Testing)
  Purpose: A test of one sample to assess the design effectiveness of the in-scope controls that have had material changes.
  Input
    Confirmed in-scope test areas and controls
    One (1) sample selected randomly by the RCSA team
  Output
    Assessment of the design effectiveness of the in-scope controls during the interim testing period

## Slide 11: Key IT RCSA Activities, Continued
Remediation Testing
Purpose: Testing throughout the year of the remediation of the issues to confirm the effective operation of the remediated controls.
  Year-End Rating of Testing of Controls and Residual Risks
  Purpose: Final rating of the in-scope controls in the in-scope test areas before the year-end report of the RCSA program.
  Input:
    Results of the testing of the in-scope controls in the in-scope test areas
    Results of the remediation testing
    Significant changes related to the in-scope controls since the interim testing
    Re-performance of the testing of the in-scope controls in the in-scope test areas (if necessary)
  Output:
    Final rating of the key process based on the in-scope controls and residual risks
  Reporting
  Purpose: Presentation of IT RCSA testing results in 2022 to the Information Security Committee